## Slide 1: BD Controls
Status and Schedule

## Slide 2: Contents
Overview
  Monitors
  Internal software
  FEC software
FEC software
  ITS concept
  Final concept
Schedule
Summary

## Slide 3: Overview - Monitors (reminder)
Monitor type | LEBT | RFQ + LINAC | MEBT | Synchrotron | HEBT
Faraday Cups | ✕ |  | ✕ |  | 
Slit Plates | ✕ |  | ✕ |  | 
Wire Scanners | ✕ |  |  |  | 
Faraday Cup Cylindrical | ✕ |  |  |  | 
AC Current Transformers | ✕ | ✕ | ✕ | ✕ | 
DC Current Transformers |  |  |  | ✕ | 
Profile/Harp Grids | ✕ |  | ✕ |  | 
Position Pickups |  |  | ✕ | ✕ | 
Phase Probe Pickups |  | ✕ | ✕ |  | 
Schottky Pickups |  |  |  | ✕ | 
Residual Gas Profile Monitor |  |  |  | ✕ | 
Diamond Detector (PIN) |  |  |  | ✕ | 
Luminescent Screens |  |  |  | ✕ | 
Qualification Monitor |  |  |  |  | ✕
Scintillating Fiber Hodoscopes |  |  |  |  | ✕

## Slide 4: Overview – Internal software
Several applications needed for internal use
  Various test applications for PCBs
  Brushless motion calibration application
  Universal test application (“Trottinette” software)
Internal software has highest priority
  Needed to test monitors (Calibration)
  Will be used as the CO independent local debug SW, fallback solution if FEC or monitor fails (Trottinette)
Different scheduling approaches
  Test applications are developed on demand
  All other applications have a schedule
  Calibration and Trottinette development in progress

## Slide 5: Overview – FEC software
Development of FECs has high priority
  Will start after internal applications are done
Issues and topics concerning MACS are handled on demand
Work on XML device descriptions and MACS interfaces started

## Slide 6: FEC software (ITS)
FEC software will be developed using FECOS
Communication using NI SV-OPC and MAPS
Preliminary “Tier 2” provided by WP CO
LabVIEW user interfaces (FEC specific)
These interfaces may later be used for debugging

## Slide 7: FEC software (final)
Tier 1 interfaces can be tested during ITS
Tier 2 can be changed during ITS
Transition to final system possible at any time
Changes to T1 and T2 transparent for FECs

## Slide 8: Schedule
Schedule is preliminary
WP BD goal: Provide monitors for ITS in time
Internal applications
  CW 14: Calibration software done
  CW 20: Trottinette software done
FEC software for ITS
  CW 24: WSX FEC software done
  CW 28: FCN FEC software done
  CW 30: SLX FEC software done
  CW 34: Tier 3 Emittance procedure implemented
  CW 36: ITS integration tests finished for WSX, FCN, SLX

## Slide 9: Summary
Internal software is being developed
MACS interface designs are underway
FEC concept for ITS is finished
Schedule for BD CO in respect to ITS standing