## BI workunits status
| Comments from Markus's file | Dep | Group | WBS | Type | Description | Workunit ID (only for pending) | WU holder | Motivation | Impact if not done | Budget code | Category | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | Total | Mail de | Comments | MAT/PERS | WP | Category detail | Priority | Comments from Markus's file
| Profile from CSSR'23 | SY | SY-BI | NA 3.1.1 | Active from MTP2021-2022 | PRIMARY-CONS : FSU & Student BSI / BTV | 234914 | jocelyn.tan@cern.ch |  |  | 64312 | MPA | 36 | 0 | 44 | 44 | 44 | 11 | 179 |  |  | Material | NA 3 | Initial Scope | High | Profile from CSSR'23
stil in the simulations to understand what we can improve (luana) + activation foils calibration campaigns) | Profile from CSSR'23 | SY | SY-BI | NA 3.1.1 | Active from MTP2021-2022 | PRIMARY-CONS : BSI 4 new units | 234918 | aurelie.goldblatt@cern.ch |  |  | 64321 | Material | 9 | 66 | 57 | 23 | 4 | 1 | 160 |  |  | Material | NA 3 | Initial Scope | High | Profile from CSSR'23
Baseline: upgrade detector head (with bands) to modern version based on flex cables. Trying to have a prototype (detector head upgraded version) installed in TT20 next YETS. Option: tungsted or carbon wires instead of bands. 2023 beam tests beging analyzed. Could be a solution for only some locations wehre high spatial resolution is required. | Profile from CSSR'23 | SY | SY-BI | NA 3.1.1 | Active from MTP2021-2022 | PRIMARY-CONS : BSP replacement with 4 SEM grids units | 234919 | aurelie.goldblatt@cern.ch |  |  | 64322 | Material | 26.476 | 35.561 | 93.476 | 53.899 | 40.405 | 10.184 | 260 |  |  | Material | NA 3 | Initial Scope | High | Profile from CSSR'23
Comments as above. These are for upstream the TBIUs | this is not only required for HI -> RP optimization required in any case, thus requiring better steering (challenge: resources, cost/unit, timeline, numbers) | SY | SY-BI | NA 3.1.1 | From HI-ECN3 | Replacement of 6 BSPs by SEM grids in TT20-TT25 lines, in addition to the 4 SEMs already approved (remaining 15 units > LS3) |  | aurelie.goldblatt@cern.ch | For high intensity beams | beam line optics cannot be measured accurately leading to beam loss | tbc | Material | 0 | 100 | 200 | 100 | 100 | 0 | 500 | aurelie.goldblatt@cern.ch | 65k /monitor*21 + 42kCHF for decabling From EDMS 2113420 : 21 more BSPs in TT20-TT25 lines should be converted to SEM grids (in addition of the 4 SEMs in the baseline WU Id 234919) | Material | NA 3 | New Request | High | this is not only required for HI -> RP optimization required in any case, thus requiring better steering (challenge: resources, cost/unit, timeline, numbers)
Comments as above, phase 2 | pushed back to post-LS3 | SY | SY-BI | NA 3.1.1 | Not approved | Replacement of remaing 15 BSPs by SEM grids in TT20-TT25 lines post LS3 |  | aurelie.goldblatt@cern.ch | For high intensity beams | beam line optics cannot be measured accurately leading to beam loss | 64322 | Material | 20 | 120 | 290 | 292 | 165 | 20 | 907 | aurelie.goldblatt@cern.ch | 65k /monitor*21 + 42kCHF for decabling From EDMS 2113420 : 21 more BSPs in TT20-TT25 lines should be converted to SEM grids (in addition of the 4 SEMs in the baseline WU Id 234919) | Material | NA 3 | New Request | Medium | pushed back to post-LS3
Comments as above, phase 2 (?) | pushed back to post-LS3 | SY | SY-BI | NA 3.1.1 | Not approved | Replacement of 5 BBS in SPS-LSS2 by SEM grids |  | aurelie.goldblatt@cern.ch |  | beam line optics cannot be measured accurately leading to beam loss | 64322 | Material | 5 | 53 | 118 | 94 | 64 | 1 | 335 | aurelie.goldblatt@cern.ch |  | Material | NA 3 | New Request | Medium | pushed back to post-LS3
| not approved by ATS-MB, no M2P for STAFF | SY | SY-BI | NA 3.1.1 | Not approved | 1x new staff technician (5-year LD contract, 2024-28) for SEM production and development of new tooling to optimise the production process |  | aurelie.goldblatt@cern.ch | For high intensity beams | beam line optics cannot be measured accurately leading to beam loss | 64322 | Staff | 0 | 150 | 150 | 150 | 150 | 150 | 750 | aurelie.goldblatt@cern.ch | STAFF required to assemble SEM grids | STAFF | NA 3 | New Request | Medium | not approved by ATS-MB, no M2P for STAFF
| not approved by ATS-MB, no M2P for STAFF | SY | SY-BI | NA 3.1.1 | Not approved | 1x new staff technician (5-year LD contract, 2024-28) for design and production of electronics and for integration and coordination |  | aurelie.goldblatt@cern.ch | For high intensity beams | beam line optics cannot be measured accurately leading to beam loss | 64322 | Staff | 0 | 150 | 150 | 150 | 150 | 150 | 750 | aurelie.goldblatt@cern.ch | STAFF required to assemble SEM grids | STAFF | NA 3 | New Request | Medium | not approved by ATS-MB, no M2P for STAFF
| needs discussion with essential scope and required timeline (can/will be gradually implemented) | SY | SY-BI | NA 3.1.1 | From HI-ECN3 | 1xFTE.Y.year DSS for assembly and installation |  | aurelie.goldblatt@cern.ch |  |  | tbc | MPA | 0 | 0 | 0 | 0 | 50 | 30 | 80 | jocelyn Tan |  | Material | NA 3 | New Request | Medium | needs discussion with essential scope and required timeline (can/will be gradually implemented)
| timeline and final number of detectors to be discussed | SY | SY-BI | NA 3.1.1 | From HI-ECN3 | 3xFTE.Y for Origin 2026-28 for assembly and test support. |  | aurelie.goldblatt@cern.ch |  |  | tbc | Origin | 0 | 0 | 0 | 80 | 80 | 80 | 240 | jocelyn Tan |  | Personnel | NA 3 | New Request | Medium | timeline and final number of detectors to be discussed
| timeline and final number of detectors to be discussed | SY | SY-BI | NA 3.1.1 | From HI-ECN3 | 3xFTE.Y for Origin 2026-28 for software integration and commissioning |  | aurelie.goldblatt@cern.ch |  |  | tbc | Origin | 0 | 0 | 0 | 80 | 80 | 80 | 240 | jocelyn Tan |  | Personnel | NA 3 | New Request | Medium | timeline and final number of detectors to be discussed
| completed in 2023 | SY | SY-BI | NA 3.1.1 | Completed | PRIM-UPGRADE : P42 SEM installation of 3 units | 234922 | aurelie.goldblatt@cern.ch |  |  | 64325 | Material | 26 | 0 | 0 | 0 | 0 | 0 | 26 |  |  | Material | NA 3 | Re-scoped | High | completed in 2023
Refurbish with new version as above | Profile from CSSR'23 | SY | SY-BI | NA 3.1.1 | Active from MTP2021-2022 | PRIM-UPGRADE : P42 SEM production of 3 units | 248568 | aurelie.goldblatt@cern.ch |  |  | 64325 | Material | 0 | 0 | 53 | 0 | 0 | 0 | 53 |  |  | Material | NA 3 | Re-scoped | High | Profile from CSSR'23
| completed in 2021 | SY | SY-BI | NA 3.1.2 | Completed | PRIM-UPGRADE : Long. BLM detector R&D, based on Cherenkov light Part1 | 234916 | belen.salvachua@cern.ch |  |  | 64313 | Material | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Material | NA 3 | Initial Scope | High | completed in 2021
| out of the scope of NA-CONS / transferred to PBC | SY | SY-BI | NA 3.1.1 | Cancelled | PRIM-UPGRADE : Long. BLM detector R&D, based on Cherenkov light Part2 + 1 LSS2 | 234923 | belen.salvachua@cern.ch | Covered by PBC |  | 99460 | Material | 0 | 40 | 40 | 0 | 0 | 0 | 80 | G.Arduini du 06.04.2023 | SY-BI to charge PBC on BC99460 for the material expenses in 2024 (40 kCHF) and 2025 (40 kCHF) in addition to PhD student from March 2023 for 3y | Material | NA 3 | Out of Scope | High | out of the scope of NA-CONS / transferred to PBC
| Profile from CSSR'23 | SY | SY-BI | NA 3.1.1 | From HI-ECN3 | PRIM-UPGRADE: Long. BLM production of 3 operational detectors: 1 TDC2 and 2 TCC2 |  | belen.salvachua@cern.ch | HI intensity operation |  | tbc | Material | 0 | 0 | 36 | 17.667 | 50 | 100 | 203.667 | belen.salvachua@cern.ch -> mail du 16.12.2022 |  | Material | NA 3 | New Request | High | Profile from CSSR'23
| Profile from CSSR'23 | SY | SY-BI | NA 3.1.1 | Active from MTP2021-2022 | PRIMARY-CONS : TT20 BLMs (replace exisiting units) | 234927 | ewald.effinger@cern.ch |  |  | 64330 | Material | 0 | 17.868 | 71.472 | 67.005 | 67.005 | 0 | 223 |  | to be renamed to TDC2 BLMs | Material | NA 3 | Initial Scope | High | Profile from CSSR'23
|  | SY | SY-BI | NA 3.1.1 | From HI-ECN3 | BLM (TT23, TT24 & TT25) = 13 new units |  | Christos Zamantzas |  |  | tbc | Material | 0 | 19 | 29 | 32 | 69 | 0 | 149 | Christos Zamantzas |  | Material | NA 3 | New Request | High
|  | SY | SY-BI | NA 3.1.1 | In HI-ECN3 | P42 BLM Part 2 (19 units remaining to be installed) |  | Christos Zamantzas |  |  | tbc | Material | 0 | 39 | 27 | 60 | 139 | 0 | 265 | Christos Zamantzas |  | Material | NA 3 | HI-ECN3 | High
|  | SY | SY-BI | NA 3.1.1 | In HI-ECN3 | P42 BLM Part 2 Tech Student |  | Christos Zamantzas |  |  | tbc | MPA | 0 | 28 | 14 | 0 | 0 | 0 | 42 | Christos Zamantzas |  | Material | NA 3 | HI-ECN3 | High
on going as planned, will double check with SB when he is back if budget still ok | Profile from CSSR'23 | SY | SY-BI | NA 3.1.1 | Active from MTP2021-2022 | PRIMARY-CONS : BTV general consolidation | 234920 | stephane.burger@cern.ch |  |  | 64323 | Material | 0.453 | 0.775 | 75.772 | 0 | 1.597 | 0.403 | 79 |  |  | Material | NA 3 | Re-scoped | High | Profile from CSSR'23
on going as planned | Profile from CSSR'23 | SY | SY-BI | NA 3.1.1 | Active from MTP2021-2022 | PRIMARY-CONS : BTV230925 upgrade | 248567 | stephane.burger@cern.ch |  |  | 64323 | Material | 0.906 | 1.549 | 27.763 | 21.782 | 23.961 | 6.039 | 82 |  |  | Material | NA 3 | Re-scoped | High | Profile from CSSR'23
protyping ~as planned. New proto 2023-24 YETS. Possible overcost due to cables known by Yacine | Profile from CSSR'23 | SY | SY-BI | NA 3.1.1 | Active from MTP2021-2022 | PRIMARY-UPGRADE : Fast spill detector production | 234921 | federico.roncarolo@cern.ch |  |  | 64324 | Material | 11.656 | 26.298 | 14.571 | 24.339 | 12.017 | 2.462 | 91 |  |  | Material | NA 3 | Initial Scope | High | Profile from CSSR'23
| Completed in 2020 | SY | SY-BI | NA 3.1.2 | Completed | LS2 URGENT items | 234915 | jocelyn.tan@cern.ch |  |  | 64313 | Material | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Material | NA 3 | Initial Scope | High | Completed in 2020
| Profile from CSSR'23 | SY | SY-BI | NA 3.1.2 | Active from MTP2021-2022 | NA-CONS : FSU & Students | 234917 | jocelyn.tan@cern.ch |  |  | 64313 | MPA | 0.038 | -0.038 | 40 | 51.871 | 88.337 | 0 | 180 |  |  | Material | NA 3 | Initial Scope | High | Profile from CSSR'23
|  | SY | SY-BI | NA 3.1.2 | Active from MTP2023 | Six months extension for Fellow working on XBPF and RadHard monitors (for a total of three years) | 234917 | Jocelyn.Tan@cern.ch |  |  | 64313 | Quest | 0 | 0 | 0 | 25 | 25 | 0 | 50 | Jocelyn Tan |  | Personnel | NA 3 | Extra Cost | High
|  | SY | SY-BI | NA 3.1.2 | Active from MTP2023 | Additional twelve months for FSU working on XBPF and RadHard monitors (for a total of 24 months) | 234917 | Jocelyn.Tan@cern.ch |  |  | 64313 | Material | 0 | 0 | 0 | 40 | 40 | 0 | 80 | Jocelyn Tan |  | Material | NA 3 | Extra Cost | Medium
|  | SY | SY-BI | NA 3.1.2 | Active from MTP2023 | Request for technical student 1MY for prototype validation and test rig building | 234917 | Jocelyn.Tan@cern.ch |  |  | 64313 | MPA | 14 | 28 | 0 | 0 | 0 | 0 | 42 | Jocelyn Tan |  | Material | NA 3 | Extra Cost | High
|  | SY | SY-BI | NA 3.1.2 | Completed | NA-CONS M2P resources NA 3.1.2 | 248936 | jocelyn.tan@cern.ch |  |  | SC64313 | Quest | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Emma Buchanan | Personnel | NA 3 | Initial Scope | High
|  | SY | SY-BI | NA 3.1.2 | Active from MTP2021-2022 | NA-CONS FELL & GRAD | 249008 | jocelyn.tan@cern.ch |  |  | 64313 | Quest | 93 | 0 | 0 | 0 | 0 | 0 | 93 |  | Emma Buchanan | Personnel | NA 3 | Initial Scope | High
| Profile from CSSR'23 | SY | SY-BI | NA 3.1.2 | Active from MTP2021-2022 | NA-CONS : electronics boards | 234924 | mark.mclean@cern.ch |  |  | 64327 | Material | 61.48 | 119.59 | 70.444 | 336.448 | 0 | 0 | 588 |  |  | Material | NA 3 | Initial Scope | High | Profile from CSSR'23
| Profile from CSSR'23 | SY | SY-BI | NA 3.1.2 | Active from MTP2021-2022 | NA-CONS : XBPF for M2, K12 & partly EHN1 | 234925 | inaki.ortega@cern.ch |  |  | 64328 | Material | 57.409 | 154.391 | 108.933 | 57.479 | 5 | 0 | 383 |  |  | Material | NA 3 | Initial Scope | High | Profile from CSSR'23
| Profile from CSSR'23 | SY | SY-BI | NA 3.1.2 | Active from MTP2021-2022 | NA-UPGRADE : Radiation tolerant profile monitor | 234926 | inaki.ortega@cern.ch |  |  | 64329 | Material | 26.014 | 26.086 | 58.285 | 39.615 | 25 | 0 | 175 |  |  | Material | NA 3 | Initial Scope | High | Profile from CSSR'23
| OK to shift post-LS3, will focus only on R&D + 1 or 2 prototypes | SY | SY-BI | NA 3.1.2 | Not approved | NA-UPGRADE : Radiation tolerant profile monitor |  | inaki.ortega@cern.ch |  |  | 64329 | Material | 0 | 155 | 234 | 50 | 10 | 0 | 449 | inaki.ortega@cern.ch |  | Material | NA 3 | Extra Cost | Medium | OK to shift post-LS3, will focus only on R&D + 1 or 2 prototypes
ongoing | detector part only (TBIU only, will be discussed next week: alignment, operation steering needs) | SY | SY-STI | NA 3.2.3 | From HI-ECN3 | New TBIU/D CONS : replacement of halo detector by SEM grids in T2, T4 and T6 (3 units only) |  | jean-louis.grenard@cern.ch | Improve beam steering on targets and fiducialisation, recommendation from TCC2 review | Misteer beam onto the target, faster ageing, higher activation, | tbc | Material | 0 | 0 | 100 | 150 |  | 0 | 250 | Jocelyn Tan | Change from BI to STI | Material | NA 3 | New Request | Medium | detector part only (TBIU only, will be discussed next week: alignment, operation steering needs)
| pushed back to post-LS3 | SY | SY-STI | NA 3.2.3 | Not approved | New TBIU/D CONS : remaining units |  | jean-louis.grenard@cern.ch | Improve beam steering on targets and fiducialisation, recommendation from TCC2 review | Misteer beam onto the target, faster ageing, higher activation, | 63312 | Material | 0 | 0 | 85 | 112 | 40 | 5 | 242 | Jocelyn Tan | Change from BI to STI | Material | NA 3 | New Request | Medium | pushed back to post-LS3
| 28 | Total | [10 empty] | 387.432 | 1330.08 | 2187.716 | 2152.105 | 1523.322 | 647.088 | 8226.667 | [6 empty] | 28
|  | Type | MAT/PERS | Sum of 2023 | Sum of 2024 | Sum of 2025 | Sum of 2026 | Sum of 2027 | Sum of 2028 | Sum of Total
|  | From HI-ECN3 | Material | 0 | 119 | 365 | 299.667 | 269 | 130 | 1182.667
|  |  | Personnel | 0 | 0 | 0 | 160 | 160 | 160 | 480
|  | From HI-ECN3 Total |  | 0 | 119 | 365 | 459.667 | 429 | 290 | 1662.667
|  | Not approved | Material | 25 | 328 | 727 | 548 | 279 | 26 | 1933
|  |  | STAFF | 0 | 300 | 300 | 300 | 300 | 300 | 1500
|  | Not approved Total |  | 25 | 628 | 1027 | 848 | 579 | 326 | 3433
|  | Active from MTP2021-2022 | Material | 229.432 | 448.08 | 714.716 | 719.438 | 311.322 | 31.088 | 2453
|  |  | Personnel | 93 | 0 | 0 | 0 | 0 | 0 | 93
|  | Active from MTP2021-2022 Total |  | 322.432 | 448.08 | 714.716 | 719.438 | 311.322 | 31.088 | 2546
|  | Completed | Material | 26 | 0 | 0 | 0 | 0 | 0 | 26
|  |  | Personnel | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Completed Total |  | 26 | 0 | 0 | 0 | 0 | 0 | 26
|  | Cancelled | Material | 0 | 40 | 40 | 0 | 0 | 0 | 80
|  | Cancelled Total |  | 0 | 40 | 40 | 0 | 0 | 0 | 80
|  | Active from MTP2023 | Material | 14 | 28 | 0 | 40 | 40 | 0 | 122
|  |  | Personnel | 0 | 0 | 0 | 25 | 25 | 0 | 50
|  | Active from MTP2023 Total |  | 14 | 28 | 0 | 65 | 65 | 0 | 172
|  | In HI-ECN3 | Material | 0 | 67 | 41 | 60 | 139 | 0 | 307
|  | In HI-ECN3 Total |  | 0 | 67 | 41 | 60 | 139 | 0 | 307
|  | Grand Total |  | 387.432 | 1330.08 | 2187.716 | 2152.105 | 1523.322 | 647.088 | 8226.667
Note on F1: Pending; New request; Rescoping; HI ECN3
Note on M1: Material; Staff; MPA; Origin; Quest