## Slide 1: HEARTS WP Leaders Meeting #4
7 November 2023
https://indico.cern.ch/event/1331441/
Pablo Lopez, WP1
CERN

## Slide 2: WP1 Milestones and Deliverables (1)
Reached milestones since the last WP Leaders meeting:
MS4: Appointment of the Advisory Panel (M6 = June 30)
Upcoming milestones in 2023:
MS5: 1st HEARTS annual meeting and interim technical review (M12 or December 31st).
Note: This is the theoretical date. In practice, this milestone will be reached in February 2024 (M14).

## Slide 3: WP1 Milestones and Deliverables (2)
Reached deliverables since the last WP Leaders meeting:
None.
Upcoming deliverables in 2023:
None.
The next WP1 deliverable is D1.1 (Assessment of high-energy heavy ion operation in CHARM during CERN proton physics periods) due in June 2024.

## Slide 4: WP1 Implementation Status and Plans
Recent achievements:
Guidelines on the use of digital collaboration tools  Contact the Project Office, may you have questions.
Submission of the COSYLAB Proposal on 28 September.  If COSYLAB is selected for funding, the EU Office will open and submit an amendment to the HEARTS Grant Agreement. The results are expected in January 2024 (M13).
The Kick-off Meeting of the Advisory Panel was held on 9 October. The next AP meeting will be held during the 1st HEARTS Annual Meeting.
The 3rd Project Office meeting was held on 12 October.  The minutes are available on Indico.
Short-term plans until the end of the year:
Complete the Advisory Panel NDA signature process (5/6 are currently signed).
Finalise the agenda definition of the 1st Annual Meeting (February 6-7, 2024). The dates might slightly change and the event will likely be planned on a full day instead of two half days (waiting on the PO’s feedback). Nonetheless, the structure remains the same (WPs presentations and discussion on the first year’s achievements and prospects for the second year of the project).
Complete the formalisation of University of Oldenburg’s involvement in the Consortium as Associate Partner.