## Slide 1: FAT Tests at MC Uldall for collimator supports - 22/10/2024
Thibaut Parmentier

## Slide 2: Supports for X-series and masks
Installed collimator (TCLPX)
Collimator support
Produced by MC Uldall

## Slide 3: Supports for TCSPM and TCTPM
Installed collimator (TCSPM 45°)
Collimator support
Produced by MC Uldall

## Slide 4: Schedule
Week 49 2024: Delivery of the Pre-series units
          3 Supports for X-series and masks
          1 Support for TCSPM
          7 Supports for tests at CERN
          Loose parts for linear stage
Week 27 2025: Delivery of the Series units
          28 Supports for X-series and masks
          11 Supports for TCSPM
          10 Supports for TCTPM

## Slide 5: Description of the FAT
Visual inspection
Torque verification
Ball support movement check
Label verification
Hypertac - and BPM connector integration test
Fixation test
Insertion test

## Slide 6: Description of the FAT
Visual inspection

## Slide 7: Description of the FAT
Torque verification

## Slide 8: Description of the FAT
Ball support movement check

## Slide 9: Description of the FAT
Labelling verification

## Slide 10: Description of the FAT
Hypertac - & BPM connector integration test

## Slide 11: Description of the FAT
Fixation test

## Slide 12: Description of the FAT
Insertion test

## Slide 13: Results of the FAT
Excellent overall
Minor remarks (mostly CERN design):
    Hypertac female connector integration
    Fischer connector guiding pins
    Cable support thread length

## Slide 14: Next steps: SAT
Repeat of the FAT
Insertion test with prototype collimators
Assembly of commercial and CERN-made components

## Slide 15: Questions