## Slide 1
WP9: Innovative superconducting cavities
Oleg B. Malyshev (UKRI) / Claire Antoine (CEA)
WP9 coordinators
Meeting opening:
Objectives, Milestones and Deliverables

## Slide 2
WP9 objectives
Define a strategy for innovative superconducting RF (SRF) cavities coated with a superconducting film.
  Deposition techniques: PVD and ALD
  Superconducting films: Nb, NbN, Nb3Sn, V3Si (and others) and SIS
  Optimization of flat SRF thin films production procedure
Optimise and industrialise the production
  of seamless copper cavities and
  of the deposition techniques.
Produce and test prototypes of SRF (single-cell elliptical) cavities:
  Initially with pre-prototypes with f = 6 and 3 GHz
  Scaling up for f = 1.3 GHz.
Test a new laser treatment of Nb coated cavity.
Main goal:
  Improving the performance and reducing the cost of acceleration systems
    both production and operation

## Slide 3
Task 9.1: Coordination and strategy for innovative superconducting accelerating cavities
  CEA, INFN, HZB, HZDR, LancU, UKRI, USI, JLab…
    Task Leaders: C. Antoine (CEA), O. Malyshev (UKRI)

## Slide 4
IFAST WP9 Milestones |  | IFAST WP9 Deliverables | 
MS37 International thin film workshop organization (web site + Report) Report by Claire, Cristian and Oliver? delay (Oct 2024) M42 | M28 | D9.1: Thin-Film SRF roadmap report. Summaries of the results obtained within the workpackage and prospective inspired from WP advances as well as discussions at TF-SRF 2022. Report by Claire and Oleg with contribution from all partners by Jan. 2024 | M35 M45 Jan 25
MS38 First seamless copper 1.3 GHz cavity produced as substrate for the coating of the SC film (Report - done) | M12 | D9.2: RF test on coated resonant cavity. Resonant cavity coated and tested with an alternative material to Niobium with a Q0 > 109 at 4.2 K and 1.3 GHz. | M46 M48
M39 Coating facility built and tested at STFC, USI and INFN (Report - done) | M12 | D9.3: First 6 GHz cavity coated and characterised. Results from the morphological and SC characterisation of first coated cavity with an alternative material to Niobium. AS for delay Report by Cristian and Reza by end of Dec. 2024 | M36 M46
MS40 Construction and operation of the cavity dedicated ALD system (Report - done) | M24 | D9.4: Deposition of superconducting multilayers on cavities. 1.3 and 3 GHz Nb and Cu cavities coated and tested with multilayers. | M46
MS41 A facility for laser operation for complex 3D treatment is tested on 1.3 GHz cavity (Report) Report by Artur, Cristian and Reza by mid-March 2024 | M36 | D9.5: 1.3 GHz Nb-coated cavity irradiated by laser in Ar atmosphere and RF tested. Increasing of the field of magnetic flux entry in Nb coated 1.3 GHz cavity irradiated by laser in argon atmosphere. Standard RF testing. | M45
MS42 ARIES samples prepared for renewed SC film deposition (Report) | M6 | D9.6: Test of thin-film samples. Four thin film samples reprocessed by 4 different techniques and tested with QPR. | M46
Coordination
Notes: Number of partners increased from 7 in ARIES WP9 to 15 in IFAST WP9

## Slide 5
Task 9.1: Coordination and Strategy for innovative superconducting accelerating cavities
  CEA, INFN, HZB, HZDR, LancU, UKRI, USI, JLab…
    Task Leaders: C. Antoine (CEA), O. Malyshev (UKRI)
This tool is now used for participation in Accelerator R&D Panel for implementation of the Accelerator R&D Roadmap of the European Strategy for Particle Physics (ESPP)
  The Large Particle Physics Laboratory Directors Group (LDG) was mandated by the CERN Council in 2020 to develop an Accelerator Research and Development roadmap.
    This Roadmap (Annex 1, https://cds.cern.ch/record/2800190?ln=it) was presented to the Council at its meeting in December 2021 and the Council invited LDG to elaborate a detailed implementation plan.
  C. Antoine and O. Malyshev are co-chairs in WP2: SC TF cavities

## Slide 6: Some updates from Accelerator R&D Panel
To study:
How big or small is the thin film SRF community in Europe,
What are we going,
What is an annual budget,
How well we are integrated,
Is there any duplication,
If we have a larger budget would it give a greater impact on deliverables.
In June 2023, we invited 1 or 2 leaders from each partner in Europe (including CERN and DESY) to fill an EXCELL table
The results were analysed and reported to Giovanni Bisoffi (INFN) and Peter McIntosh (STFC), the coordinators of LDG RF Implementation Panel
They reported a summary of this at Community Report on Accelerators Roadmap on 12–13 Jul 2023 at INFN-FNL
CERN Council Report (“short” report) - Nov 2023 includes these results.
More work is expected in spring-summer 2024

## Slide 7: NEXT WP11 meeting
In-Person meeting
  In Daresbury Laboratory
  on 18-19 January 2024
  Starting at 14:00 CET on 18th Jan
  Finishing not later than 16:00 on 19th Jan
  Hybrid (in person and zoom)

## Slide 8: 2024 IFAST Annual Meeting
In-Person meeting
  on 15 to 19 April 2024
  Near Paris
  12th WP9 meeting is on 16th April
    from 9:00 to 18:00
    in-person (preferable) and zoom