## Slide 1: Getting ready for Run 2c
Eloïse Guran, CERN
AWAKE Collaboration meeting
11-13 March 2024

## Slide 2: Getting to run 2c
Run2c
2 Plasma Cells
2 Electron Sources
Klystrons
Spectrometer
Laser beam compressor 1
Laser beam compressor 2
2 WDL Chiller Units
AWAKE CNGS Area Dismantling is before & during LS3 (2025-2026)
Run2c Integration/installation/commissioning is during LS3 (2026-2028)
Run1
&
Run2ab
TSG42
TSG43
TSG44
TSG45
CNGS area – to be dismantled
UV laser room
Ans’ talk

## Slide 3: Getting to run 2c
Run2
2 Plasma Cells
2 Electron Sources
Klystrons
Spectrometer
Laser beam compressor 1
Laser beam compressor 2
2 WDL Chiller Units
AWAKE CNGS Area Dismantling is before & during LS3 (2025-2026)
Run2c Integration/installation/commissioning is during LS3 (2026-2028)
Run1
Step 1: dismantling of run 2b
TSG42
TSG43
TSG44
TSG45
UV laser room
Step 2: CNGS dismantling
Step 3: Run2c installation

## Slide 4: Timeline for AWAKE dismantling & decabling
Decabling = all cables linked to a dismantled equipment + obsolete cables
Step 1
End of Awake operations: September 2024
Run 2b dismantling: 2months of decommissioning + 3 months of transport
Decabling: ~2 months of works

## Slide 5: Timeline for AWAKE dismantling & decabling
If the 2 additional weeks of beam approved  ~1month shift
Step 1
End of Awake operations: October 2024
Run 2b dismantling: 2months of decommissioning + 3 months of transport
Decabling: ~2 months of works
DRAFT

## Slide 6: Run 2b dismantling
Estimated:
15T of equipment
  11 racks
  8 optical tables
  17 BTVs + 6 BPMs
  28 magnets
  RF gun + klystron + waveguides
  Plasma source
  ~20 girders
50T of shielding blocks (~90blocks)
Step 1

## Slide 7: Dismantling sequence for transport
1. Klystron area (klystron + racks)
2. Bunker structure :
a. doors
b. shielding blocks
3. Items inside the bunker :
a. electron injector assembly
b. etc
5. Streak room
a. walls & doors
b. optical table
c. 2 racks
d. 2nd optical table
6. Optical line
a. Horizontal support
b. Vertical structures (x2)
7. TCC4 shielding
4. Dismantling of sector door
8. Spectrometer structure
9. Electron line
10. TCC4 equipment area

## Slide 8: Motivation for decabling
Cable trays in Awake are 400% full
Main goal of decabling: ensure a clean infrastructure for future cables needed for run2c
Step 1

## Slide 9: Decabling process
List of cables (given by EN-EL)
Pre-identification at the office
Finding the cables on-site + identifying with yellow tape
Final list of cables to give back to EN-EL
Preparation of lockout document
Validation of lockout
Decabling campaign
February 2024
March 2024
March/April 2024
May/June 2024
Summer 2024
December 2024 /January 2025
February & March 2025
Two main documents of work :
the cable list (DEC): it states clearly which cable should be removed or not
  approved on edms by all equipment owners
the lockout document: it states which equipment/racks are going to be locked out
  approved on edms by equipment owners, group and department leaders
Example of cable list
NEXT STEP
Input received
Important steps to take before the summer
Step 1

## Slide 10: CNGS dismantling
Step 2
Ans’ talk

## Slide 11: Run 2c installation
Installing run 2c during LS3 brings some constraints:
  Availability of resources
  Respect deadlines linked to LS3 even though the project is not yet approved
For AWAKE, next milestones:
  PLAN activities by 31.03.2024
  Cabling request by 15.04.2024
  Electrical network request by 15.04.2024
  Review of run2c schedule for June 2024
Step 3
Run2b operation
CNGS dismantling
Run 2c installation
Run2b dismantling

## Slide 12: General Awake roadmap
2023 | 2024 |  |  |  |  |  |  |  |  |  |  |  | 2025 |  | 
Dec. | Jan. | Feb. | March | April | May | June | July | Aug. | Sept. | Oct. | Nov. | Dec. | Jan. | Feb. | March
Inventory of equipment
Establish sequence for dismantling
Decommissioning
Transport out
Listing cables for decabling
Pre-identification of cables
Identification of cables (purple tape)
Decabling
Run 2b dismantling
Decabling
Preparation of lockout document
Input Awake activities in PLAN
Cabling requests
Review installation planning
Review integration layout of run2c
Run2c preparation
EL network request
12
Draft schedule
LS3 readiness review

## Slide 13: Summary
3 Main steps towards run 2c readiness:
Step 1: AWAKE run 2b dismantling & decabling
  Takes place from October 2024 to January 2025
  Decabling : Pre-identification of cable list
Step 2: CNGS dismantling
Step 3: new installation  Next milestones to prepare the path for run 2c:
  Before 31.03.2024
    Enter your activity in PLAN
  Before 15.04.2024
    Send cabling request
    Send request for new electrical network
  For June 2024
    Review run 2c installation schedule

## Slide 14: Back up slides

## Slide 15: Girders re-usability
QTLF412208
QTLF412200
All girders currently in use from QTLF.412208 to plasma cell will need an adaptation to be re-used for run 2c.

## Slide 16: Girders re-usability
Missing height ranges from 162mm to 613mm.

## Slide 17: AWAKE run 2c installation schedule
As presented in the CSR of 2021
To be updated