## Slide 1
HL-LHC Upgrade Project
ENEA Visit to CERN, February 2024
O.Brüning, on Behalf of the HL-LHC Project

## Slide 2: Outline
HL-LHC Introduction: Goals, Schedule and Collaborations
Status of key technologies towards the HL upgrade
  Civil engineering
  New Superconducting Insertion Magnets
  Superconducting Link
  Crab Cavity System
  Collimation: Crystal & Low impedance collimators
Inner Triplet String in SM18 @ CERN
Conclusions

## Slide 3
Run3 operation
Approval of
HL-LHC Project
EU funded HiLumi
Design Study
HL-LHC Operation
We are here
< 2 years until start of Long Shutdown 3
The project is ready for installation start in 2026!  endorsed by 2023 C&SR

## Slide 4: Goal of HL-LHC upgrade project
The main objective of the HL-LHC is to determine and build a hardware configuration and a set of beam parameters that will allow the LHC to reach the following targets:
Prepare machine for operation beyond 2025 and up to 2040
Devise beam parameters and operational scenarios for:
# enabling at total integrated luminosity of 3000 fb-1
# implying an integrated luminosity of 250 fb-1 per year,
# design oper. for μ ≤ 140 ( peak luminosity 5 x 1034 cm-2 s-1)
 A challenge as well for the experiments!
 Operation with levelled luminosity!

## Slide 5: New HL-LHC Triplet Layout:
70mm  8T peak  Nb-Ti
150mm  12T peak  Nb3Sn

## Slide 6: The Insertion Region (up to Q4)
Q1
Q2a
Q2b
Q3
CP
D1
DFX
DFM
Connection to LHC (UL)
Service gallery (UR)
TAXS
Crab cavities
UA Gallery
Q4
Collimators
TAXN
Service cavern
SC Links
D2

## Slide 7
Technology
Landmarks
Separation / Recombination
dipole magnets: D1 & D2
Finished in 2023
Finished in 2023
Successfully deployed in 2023 Pb-Pb run
½ system already installed for Run3
Series production in Industry well underway
Complete Prototype System installed in SM18 and under testing
Fully validated in 2023 and first magnets ready for installation
Prototype and first series delivered to CERN
Prototype cryostated @ CERN

## Slide 8: New Underground construction: Ceremony for completion of CE 2023
Notes: To be updated with latest plans for Ceremony

## Slide 9: Completion of Surface buildings in 2023
SF17
SHM17
SD17
SE17
SU17
Example Point 1
20th January 2023
Celebration Ceremony: Point 5
Work Ended Spring 2023

## Slide 10: Status MQXFB – Q2 - Assemblies at CERN
MQXFBP1: test at CERN in 2020
  Failed to reach nominal current @ 1.9K But:
    Reached 6.4TeV equivalent without Quench; limitation only in one coil, all concepts validated @ 15.15kA
     Plan to exchange the limiting coil  procedure test for 4+1  MQXFBMT4 July 2023 ✓
    MQXFBP2: test at CERN in 2021
        Limited at around nominal current and eventually reached nominal current at 1.9K at lower ramp rates
         review of assembly  3 Phase Improvement plan
        1) Stainless Steel prestress; 2) Assembly procedure of Cold-Mass; 3) Coil production
MQXFBP3: test at CERN in 2022 – Lower shell pre-stress  1) but after disassembling 01
  Nominal +300A @ 1.9K and 3 TC ✓
  Still limited at 4.5K  but compatible with powering at ultimate current at 1.9K
MQXFB02 test at CERN in 2023 – 1) plus New Magnet Assembly procedure  1) & 2)
  nominal +300A @ 1.9K and 3 TC ✓ Still limited at 4.5K but compatible with ultimate at 1.9K!
MQXFB03 test at CERN in 2023 – New coil production  1) & 2) & 3)
  Nominal + 300A @ 1.9K and 4.5K and after TC!  Full validation of magnet concept!
10
Decision to use P2 and P3 for the IT-String in SM18 @ CERN even though they are limited @ 4.5K
Re-cryostating of the cold-masses in final cryostat configuration
Lost one coil during preparation for cold-test in final cryostat configuration
 Plan to exchange the damaged coil and keep 02 as a spare
First Magnet that will go into the machine!
Magnets produced  None showing degradation!
3 [last 3] consecutive Magnets passed acceptance criterial!!!
Notes: Simplify for ENEA!

## Slide 11: Status MQXFA – Q1 & Q3- Assemblies at AUP
8 out of 20 magnets build, tested and validated!
From 15 that were produced – 3 during COVID  all non-conformed being repaired  2 repaired validated
MQXFA08b & MQXFA14b repaired and validating coil replacement procedure and coil production planning
Endurance test on MQXFA05: 50 quenches, 5 TC  magnet remains @ nominal! ✓
Unscheduled mechanical robustness test for MQXFA11  road accident ✓
Magnet passed acceptance criteria at vertical test station ✓
CA-01: First cold mass reaching nominal performance – no retraining after thermal cycle
Nonconformities but accepted in close collaboration with AUP to assure in-time delivery for IT-String
 Shipped in November  Arrived @ CERN in December [acceptable for IT-String, not yet for machine]
Cabling completed: https://newscenter.lbl.gov/2023/08/30/cabling-for-lhc-upgrade-wraps-up/
Second Cold-Mass Assembly being prepared for testing at FNAL  second out of 10 CMA
CA01 Leaving FNAL October 30th 2023
CA01 Arriving @ CERN November 28th 2023
Notes: Simplify for ENEA!

## Slide 12
D2 Cold-Mass Assembly
Cryogenics by-pass
D2 Prototype Cold-Mass @ CERN in Hall 180
D2 Prototype on the test bench in SM18: reached ultimate current after TC without quench
First D2 series magnet at ASG factory in Genoa, 2023

## Slide 13: Non-Linear Corrector Package Production by LASA in Milan
SAES RIAL Vacuum
as Industrial partner
Production already completed!
Excellent performance of the delivered magnets!!!

## Slide 14: HL-LHC cavity designs
RF Dipole: Waveguide or
waveguide-coax couplers
Double ¼-wave: Coaxial couplers with
hook-type antenna
2 Designs with
Different Coupler concepts and
Deflection planes
Present baseline: 4 cavities / IP / side  16 total
Crab-Cavity
Cryomodule containing
2 Crab Cavities
Produced by AUP with Zanon
as industrial partner
Produced by CERN with RI
as industrial partner

## Slide 15: Cold Powering System
D2
DSHM
DFHM
Q1
Q2A
Q2B
Q3
CP
D1
DCM
DFM
DFX
DSHX
DFHX
140 m
89.5 m
Power converters: (18, 7, 2) kA
Power converters: (18, 0.6) kA
Power converters: (60, 120, 200) A

## Slide 16: MgB2 Superconductor and Superconducting link
Cable production complete !
Assembly of the first complete
system incl. flexible cryostats
is ongoing
Demo-3 in SM18
Successfully Demonstrated
Concept between 2020 / 22
with > 120kA @ 30K
16

## Slide 17
SC-Link-DFHX assembly in pictures
Complete System Test planned for Q1 2024 in SM18 @ CERN
Industrial partners in Italy: ASG and TRATOS

## Slide 18: Collimation upgrades
Over 100 Collimators and absorbers to protect the SC magnets!!!
Ion physics debris: DS collimation
Cleaning: Crystal collimators for Pb ion beam operation
Low-impedance, high robustness secondary collimators
Completely new layouts Novel materials. IR1+IR5, per beam:
4 tertiary collimators 3 physics debris collimators fixed masks
56 new collimators to be produced by LS3!
SAES CINEL
as Industrial partner for the LS1 and LS2 production

## Slide 19: Xray machine for crystal characterization
Four primary crystal collimators installed in the LHC for ion beam collimation
First operational deployment in the LHC lead ion run 2023  Factor 5 to 6 beam loss
improvement!
Bent crystal produced by PNPI and by INFN (Ferrara)
X-ray characterization at CERN
Crystal primary collimator in the LHC tunnel

## Slide 20
HL-LHC IT STRING: P5L
P5
P5L
P5R
SPS
HL-LHC
P1
P2
P3
P4
P5
P6
P7
P8

## Slide 21: HL-LHC testing facilities in SM18
SRF Section
Magnet Testbenches
Cold-powering Test Area
IT Test Area

## Slide 22: IT String Status in pictures
On top of the empty metallic structure
Under the metallic structure
PC and Energy Extraction racks installed on the metallic structure
Cryo Distribution
Q4 2024
Q2-Q4 2025
Q1’26
Q2’26
Q1’25

## Slide 23: THE IT-STRING INGREDIENTS ARE GETTING READY
Dates given in schedule change request, EDMS 2898265
  Q1: magnet cold mass being welded  Available in September 2024
  Q2a: MQXFBP3b completed  Available for Testbench Jan.  April 2024
  Q2b: MQXFBP2b completed  On SM18 Testbench  Available April 2024
  Q3: arrived at CERN December 2023  Available July 2024
  CP cryostating Phase II ongoing  Available August 2024
  D1 cryostating completed  On SM18 Testbench  Available March 2024
CP
Q2a
(in SMI2)
CP
(SMI2)
Q3
(in FNAL)
D1
(in SMI2)
Q2b
(in SM18)
Q2b
In SM18
Notes: To be updated by Ezio’s PSM presentation

## Slide 24
HL-LHC Highlights
Available beginning of 2024
Open Access Publication
https://doi.org/10.1142/13487
ISBN: 978-981-127-894-5

## Slide 26: Bent crystal for particle accelerators
If the protons have pT < Umax
Critical angle
LHC 450 GeV = 9.4 μrad
LHC 6.5 TeV = 2.4 μrad
FCC-hh 50 TeV = 0.9 μrad
Pure crystals with regular lattices
Straight crystal: hadron oscillate, “trapped” between planes
Bent crystal
Mechanical bending of crystal produces a net kick of trajectories of the particles trapped between planes.
50μrad at 7 TeV proton
(4mm length, curvature r = 80m)
LHC design parameters for Silicon crystals
4mm
1mm
50mm
Bending 50μrad
Beam
TCP = primary collimator
TCSG = secondary collimator
TCLA = shower absorber
Crystal collimation: Needed at the HL-LHC for the collimation of lead ion beams!
Crystal collimation scheme

## Slide 27: 1st CERN-DQW Series, Qualified
3rd test beyond the specification with additional chemistry of HOMs & deg vacuum bake

## Slide 28: Industrial DQW Series (RI)
1st pre-series jacketed cavity with excellent results, metrology to be finalized before acceptance
2nd cavity in metrology and cold tests soon

## Slide 29: RFD Cold Mass Assembly – UK1 Collaboration
Lowering of Top plate to Cavity String successful !!
Since last PSM (July), important alignment issue between top plate and cavity string corrected with some non-conformities (not ideal but ok)
Delivered to CERN in time in October for installation deadline in the SPS Test-facility!
Unfortunately observed major Nonconformities following reception tests @ CERN
Electrical Short of coupler to ground / housing & vacuum leak
Will NOT be installed in the SPS in YETS 23 / 24
But important lessons learned for series production with UK and AUP / TRIUMF!!!!!!

## Slide 30: AUP Crab Cavity production with Zanon as Industrial partner