## Slide 1: SPS EYETS 2024
A. Harrison
TE-VSC-IVO

## Slide 2: Accelerator overview
Notes: LINAC (H-) up to 160MeV
PSB (2 electrons stripped) up to 2GeV
PS up to 26GeV
7km ring
~8km Transfer Lines
From 26GeV up to 450GeV
1317 normal conducting magnets
1521 Ion pumps
Ring experiments COLDEX, UA9 & CRAB
Feeds: North Area physics, AWAKE, HiRadMat also injects into LHC in both directions (Ti2 Blue clockwise and Ti8 Red anticlockwise)

## Slide 3: SPS Overview
TT66 windows upgrade
TED upgrade
Vacuum Primary Line
Aperture improvement BPCN,
Re-sectorisation MKE06,
Crab Cavities removal.
Fast Wire Scanners
BGI & re-sectorisation
Pumping Port Shielding
Fast Wire Scanners
EO Pick-up
De-cabling
RF Cavity leak detection
Mode Trap
Ion pump consolidation,
Layout improvement BPVC,
De-cabling.
Aperture improvement BPCN,
Layout improvement BPNC.
MST leak detection.
BSGV 210350,
Spill Monitor.
AWAKE
Notes: Slide to be updated

## Slide 4: SPS – EYETS & Schedule
30.10.2023
09.02.2023
65 working days / 15 weeks including CERN closure
RP Cooldown
IST (Begin of EYETS)
IST (End of EYETS)
43 working days
  Extended Year End Technical Stop (EYETS) 2023/2024.
  Maintenance and upgrade of the accelerators.
  SPS From 31st November 2023 to 9th February 2024
  (general access from 07/11/2023 to 31/01/2024)

## Slide 5: Fast Wire Scanners
During physics run all 4x Wire Scanners carbon wires broke, a Task Force found beam impedance induced high temperatures on carbon wire.
  April - intervention to replace 2x BA4 wire scanners, both failed within several days.
  TS1 2x Wire scanners replaced BA4; 1x Horizontal, 1x vertical including 6x ferrite tiles to dampen beam impedance.
EYETS – replace all 4x scanners, returning to original configuration and install ferrite modification.
Modified configuration (horizontal/vertical)
Ferrite tiles
ECR: SPS-BWSRC-EC-0003
BA4 Original configuration (vertical)
Notes: Measurement of Transversal beam profiles – BA5 horizontal and BA4 vertical
Broke in parking position (out of the beam)
Failed 12th April, replaced 19th April, failed again 21st April.
Induced temperature up to 1700°C

## Slide 6: BGI & re-sectorisation
6.5m downstream
High degassing equipment next to sensitive MKDV.
Simulations to determine acceptable buffer sector length - maintaining 24h recovery after intervention.
New sector & layout.
ECR: SPS-BGI-EC-0001
COMSOL simulation using Temkin adsorption isotherm
(thanks to Anke Stoeltzel!)
Notes: Animations!
Both Wire Scanner and BGI measure Beam Transverse Profiles, the difference is BGI has no limits with Beam energies whereas the Wire would sublimate at higher energies of LHC
Sector opening pressure of 1e-6mbar, with the buffer sector pressure of 1e-8 mbar
Sticking 1e-3, nm=4.9e19 molecules/m^2, E0=28.43 and E1=10 kcal/mol, s0=1
The linearized form of the Temkin isotherm equation is as follows: [ q_e = B \ln(A + B \cdot C_e) ] where:
  (q_e) represents the amount of adsorbate at equilibrium (in mg/g).
  (A) and (B) are the Temkin isotherm constants (in L/g and J/mol, respectively).
  (C_e) denotes the equilibrium concentration of the adsorbate on the adsorbent.

## Slide 7: HiRadMat upgrades
Beam Brightness
ECR: HRM-V-EC-0002
Glassy carbon windows
- Beryllium window failures due to higher intensity beam
- Recommendation from HRM-Be-WG.
- Re-sectorisation of TT66 using in-line GC window.
- Replacement of Beryllium window with GC.
TT66 aperture simulation
Aperture >Ø70mm for future beams.
Position 660418 lower beam brightness.
In-line Ø100mm, 3mm Glassy Carbon.
End window Ø60mm x 3mm Glassy Carbon.
Notes: Animations!

## Slide 8: MKE Re-sectorisation
ECR: SPS-VVS-EC-0001
Re-locating the sector valve to liberate QD_61610 from MKE sector.
QF.61610 magnet exchange for a-C coated.
Impedance improvement and PU Jacks exchanged.

## Slide 9: Magnet exchanges
13 magnets – all refurbished and tested at surface.
MBS.660031
Chamber compressed within C-shaped magnet yolk.
Lab testing showed Δ compression 3.2mm.
QF.61610 Pumping Port Shielding and RF fingers
LSFA.62005
Notes: Chamber compressed within C-shaped yoke – resting space of 56(+/-0.02)mm, passage of 54(+/-0.02)mm
Chamber electrically isolated with Vetronite sheets
Lab testing measured chamber compression of 3.2mm

## Slide 10: General activities
Validation testing of Crab Cavities RFD module in SM18
Removal of Crab Cavities DQW module from BA6
Primary vacuum line manifolds and extension of compressed air line
Collaboration between TE-VSC, SY-STI, SY-BI & BE-EA
ECR: HRM-V-EC-0003

## Slide 11: General activities
E-O Pick up
Aperture restrictions & Obsolete BPM’s
Spill Monitor (TT20)
ECR: SPS-BPM-EC-0002

## Slide 12: Consolidation
72x ion pumps exchanged in synergy with PSU & local boxes
Three Consolidation programs ongoing:
Ion pump Consolidation – SPS ring
Transfer Lines Consolidation
North Area Consolidation – no VSC activities 2023/4
Ti2 ion pump consolidation (6x), exchange of feed-through and lab testing
Repair of known leaks

## Slide 13: Non-conformities
22x non-conformities resolved, ion pumps, penning gauges and incorrect or damaged vacuum chambers
6x new non-conformities identified
Survey and endoscopy (2022), revealed missing PPS and obsolete pick-ups
MST leak/repair

## Slide 14: Start-up
Thanks to Piquet for their help!
1st Beam
MBA.61490 coil short circuit
VVSA.27605 compressor
VVSA.80110 pressure spike

## Slide 15: Thanks