## Slide 1: CHARM user planning 2024
Salvatore Fiore
BE-CEM-EPR

## Slide 2: East Area Irradiation Facilites
CHARM
IRRAD
24 GeV/c
~400ms spill
PS p+
DUMP
  Primary beam line from PS (T08): 24 GeV/c proton beam
  CHARM irradiation area is placed downstream to IRRAD on the T8 line
ENTRANCE

## Slide 3: Irradiation Room
3 KEY ELEMENTS:
Target
Movable Shielding
Positions
Conveyer
Montrac
Iron
Concrete
Target
PRIMARY PROTONS IMPINGE THE TARGET: A SECONDARY RADIATION FIELD IS CREATED
6mt
5mt

## Slide 4: Irradiation Room
RACK
RACK
OVERHEAD
G0

## Slide 5: Users and reference radiation levels per week
In CHARM we can host several users in parallel testing:
The CHARM rack can host up to 2 users
  Up to 500 Gy, 1.8E12 HEH/cm2, 3E12 1-MEVeq n /cm2, 5E11 Th n /cm2 , per week
G0 (grillage close to partch panel) up to 3 users depending on size
  Up to 25 Gy, 7E11 HEH/cm2, 2E12 1-MEVeq n /cm2, 5E11 Th n /cm2 , per week
Overhead up to 1 user
  Up to 100 Gy, 1E12 HEH/cm2, 1.5E12 1-MEVeq n /cm2, 5E11 Th n /cm2 , per week

## Slide 6: Operations: Planning and constraints
Constraints:
  Safety/RP : Reduce at maximum the exposure of users and operators to ionizing radiation
  Organize the accesses to reduce at maximum the overhead
  Deliver the radiation levels requested by the users + environment fitting
Operational constraints
  Upstream IRRAD facility operations follow-up
  CHIMERA/HEARTS (EU Project)  ions in the last 2 weeks of PS EA beam
  RP WEEK
  No more than 2 users in the test rack + EPR activities (dosimetry and testing)
  Additional users in G0 or Overhead, not on the rack

## Slide 7: Weekly Ops
  CHARM irradiation time is divided in Slots: 1 Slot is one week
  Access is ONLY on Wednesday: profiting of the PS MD
  CHARM Target is removed from the beam in accordance with RP recommendation: 24 hours before the access.
  The preparation room allows users to test in advance their setup
    Wednesday -> One-shot installation -> If the setup is not working the user won’t test
  Users are requested to test their equipment in the preparation room one week in advance wrt to their installation

## Slide 8: Protons to PS EA and CHARM
Relevant dates:
March 18: protons to EA
June 12-15 Injectors Technical Stop
October 14/16 end of protons to EA

## Slide 9: CHARM calendar for 2024
Starting from 2024 we adopt the standard week numbering:
A test scheduled for Wxx is foreseen to start on Wednesday of Wxx
Dry run starts on Wednesday W(xx-1)
The first user week is W14
The last user week is W41
W24 is Injectors TS
W38 is dedicated to RP

## Slide 10: 2024 schedule booking
36 test requests so far, with different radiation level goals, through the web-form (still incoming requests)
First calendar version is ready, users being asked for confirmation
45/52 rack slots already filled
86% occupancy
EPR tests for Radiation Test
Service not included: several
test per week
Chart: CHARM test requests
| <100 Gy | >=100 & <500 Gy | >=500 & <1000 Gy | >1000 Gy
2024 (open) | 4.3 | 9 | 13 | 5
2023 (final requests) | 8 | 10 | 21 | 2

## Slide 11: Current CHARM occupancy, as of today
week # | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27
from Wednesday | 03-Apr | 10-Apr | 17-Apr | 24-Apr | 01-May | 08-May | 15-May | 22-May | 29-May | 05-Jun | 12-Jun | 19-Jun | 26-Jun | 03-Jul
to Tuesday | 09-Apr | 16-Apr | 23-Apr | 30-Apr | 07-May | 14-May | 21-May | 28-May | 04-Jun | 11-Jun | 18-Jun | 25-Jun | 02-Jul | 09-Jul
Rack | full | full | half | full | full | full | full | full | full | full | ITS | full | full | full
G0 | full | full | full | free | half | free | free | half | half | half | ITS | free | free | free
week # | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41
from Wednesday | 10-Jul | 17-Jul | 24-Jul | 31-Jul | 07-Aug | 14-Aug | 21-Aug | 28-Aug | 04-Sep | 11-Sep | 18-Sep | 25-Sep | 02-Oct | 09-Oct
to Tuesday | 16-Jul | 23-Jul | 30-Jul | 06-Aug | 13-Aug | 20-Aug | 27-Aug | 03-Sep | 10-Sep | 17-Sep | 24-Sep | 01-Oct | 08-Oct | 15-Oct
Rack | full | full | full | full | full | full | full | half | half | half | RP week | half | half | half
G0 | half | half | half | free | free | free | free | free | free | free | RP week | free | free | free

## Slide 12: Conclusions
PS EA beam to CHARM for 26 usable weeks
CHARM users calendar for 2024 being finalised
Currently 86% of the rack slots are full. Safety and logistics constraints
All the requests have to be sent through https://cern.ch/charm

## Slide 13
Thank you for your attention!