## Slide 1: HEARTS Project Office Meeting #4
13 March 2024
https://indico.cern.ch/event/1385374/
Pablo Lopez CERN, WP1

## Slide 2: Agenda
Open actions since the last Project Office meeting and 1st Annual Meeting
Debriefing of the 1st Annual Meeting & Review
Milestones and deliverables status and outlook
Period 1 (P1) report preparation
Events
AoBs
  Involvement of University of Oldenburg
  Internal budget situation
  Other

## Slide 3: Open actions since the last Project Office meeting & 1st Annual Meeting
Advisory Panel mandate and NDA
6 out of 6 NDA signed. The signature process is completed.
Define the Advisory Panel meeting format (action on Project Office)
HEARTS Promotion video (action on Antoine)
The full video is available with and without subtitles. It is also available on the YouTube CERN channel.
HEARTS general presentation and one-page presentation to pitch the project (action on Antoine)
Follow-up of COSYLAB’s involvement in the consortium (action on EU Office)
GA Amendment + Y1 review are on the EU side now
 should we send a kind email to the PO asking about the status of these 2 items? (action on EU Office)
Reporting Period 1 review (action on Pablo)
Schedule a meeting in September with the PO for the review after the submission of the Period 1 report to the EU (end of August 2024).

## Slide 4: 2. Debriefing of the 1st Annual Meeting & Review
1st HEARTS Annual Meeting agenda, February 6th, 2024.
Summary of the meeting and general impressions.
Congratulations and overall support from Fabio Vitobello and Simon Conticello.
The Project Office should soon receive the review report.

## Slide 5: 3. Milestones and deliverables status and outlook
Chart: HEARTS Y2 Milestones timeline
| 44957 | 44985 | 45016 | 45046 | 45077 | 45107 | 45138 | 45169 | 45199 | 45230 | 45260 | 45291 | 45322 | 45351 | 45382 | 45412 | 45443 | 45473 | 45504 | 45535 | 45565 | 45596 | 45626 | 45657 | 45688 | 45716 | 45747 | 45777 | 45808 | 45838 | 45869 | 45900 | 45930 | 45961 | 45991 | 46022 | 46053 | 46081 | 46112 | 46142 | 46173 | 46203 | 46234 | 46265 | 46295 | 46326 | 46356 | 46387
Total nb of due MS since M1 | 1 | 3 | 5 | 5 | 5 | 6 | 6 | 6 | 6 | 6 | 6 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 10 | 10 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 16 | 16 | 16 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 23
Total nb of delivered MS since M1 | 4 | 5 | 5 | 5 | 5 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 7

## Slide 6: 3. Milestones and deliverables status and outlook
Upcoming milestones in 2024:
MS11: Release of G4SEE VHE ion tool (M24 – 31.12.2024) – WP3
MS12: CERN beam instrumentation and dosimetry installed and running (M24 – 31.12.2024) – WP4
MS20: First external users at CHARM (M24 – 31.12.2024) – WP7
The reminder to draft the milestone reports will be sent to relevant stakeholders in due time according to the defined workflow, i.e. by mid-November (action on Pablo).

## Slide 7: 3. Milestones and deliverables status and outlook
Chart: HEARTS Y2 Deliverables timeline
| 44957 | 44985 | 45016 | 45046 | 45077 | 45107 | 45138 | 45169 | 45199 | 45230 | 45260 | 45291 | 45322 | 45351 | 45382 | 45412 | 45443 | 45473 | 45504 | 45535 | 45565 | 45596 | 45626 | 45657 | 45688 | 45716 | 45747 | 45777 | 45808 | 45838 | 45869 | 45900 | 45930 | 45961 | 45991 | 46022 | 46053 | 46081 | 46112 | 46142 | 46173 | 46203 | 46234 | 46265 | 46295 | 46326 | 46356 | 46387
Total nb of due DV since M1 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 5 | 5 | 5 | 5 | 5 | 5 | 6 | 6 | 6 | 6 | 6 | 6 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 31
Total nb of delivered DV since M1 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 4 | 5

## Slide 8: 3. Milestones and deliverables status and outlook
Upcoming deliverables in 2024:
D1.1: Assessment of high-energy heavy ion operation in CHARM during CERN proton physics periods (M18 – 30.06.2024)
D3.1: Numerical characterization of the CHARM beamline and of detector response (M24 – 31.12.2024)
D3.2: Modelling of shielding materials and configurations for test setup standardisation (M24 – 31.12.2024)
D3.3: GCR/SPE simulator optimizer software (M24 – 31.12.2024)
D4.2: Calibrated CERN beam instrumentation documented and installed in the accelerator (M24 – 31.12.2024)
D5.2: Validation of beam parameter quality of CERN and GSI infrastructures for testing of electronics (M24 – 31.12.2024)
D6.1: GCR/SPE simulator setup (M24 – 31.12.2024)
D7.2: Demonstration of the achievements in terms of beam parameters (energy, LET, range, size) (M24 – 31.12.2024)
The reminder to draft the deliverable reports will be sent to relevant stakeholders in due time according to the defined workflow, i.e. by mid-May for D1.1 and by mid-November for the remaining ones (action on Pablo).

## Slide 9: 4. Period 1 (P1) report preparation
P1 reporting:
Period 1: 01/01/2023 – 30/06/2024
Periodic Report No. 1 is to be submitted by the end of August 2024
  Due to the summer break, we will try to anticipate, but latest results until the end of June will have to be included
Tentative deadlines:
  Templates and instructions will be sent in May at the latest by HEARTS Management Team to WP Leaders and Beneficiaries contacts
  1st version of Technical reports (1 per WP) to be sent back to HEARTS Management Team by mid-July
  Consolidation and possible revisions of Tech. reports for final versions ready by mid-August
  Financial Statements to be submitted by late July
  Consolidation and possible revisions of Financial Statements until mid-August

## Slide 10: 4. Period 1 (P1) report preparation
P1 reporting – Financial part:
1 Excel file per Beneficiary, detailed at WP level, for internal follow-up
1 Financial Statement per Beneficiary, on the EC Portal, for reporting to the EU Agency
Deviations we will ask beneficiaries to explain:
  Any under-use or over-use of budget, at WP level (>15% deviation)
  Any purchase costs above 15% of personnel costs
  Any deviation from the estimated average personnel costs (= personnel costs / PM)

## Slide 11: 5. Events
HEARTS presence at NSREC in Ottawa, Canada (22-26 July 2024)
HEARTS presence at RADECS in Gran Canaria, Spain (16-20 September 2024)
Other major events?

## Slide 12: 6. AoBs
Involvement of University of Oldenburg in the project and Collaboration Agreement status (action on Julia)
Internal budget situation (action on Viktor)
Other?