## Slide 1: LS3 preparations
06 March 2024

## Slide 2: LS3 roadmap

## Slide 3: Global CERN timelines
  The injectors must remain aligned with the global CERN timelines

## Slide 4: PLAN tool : plan.cern.ch
Everyone should have EN-EL in the resources

## Slide 5: PLAN activities
CP | Description | PLAN
CP1 | SPS beam, RF timing | one PLAN activity «Upgrade of SPS beam and RF timing in AWAKE»
CP2 | Proton & Electron beam lines | One PLAN activity «installation of proton and electron lines in AWAKE» Or two PLAN: “installation of proton line in AWAKE” + “installation of electron lines in AWAKE” + PLAN activity for EPC ? “new converters for AWAKE” ? + PLAN activity for magnets ?
CP3 | Electron source | 
CP4 | Infrastructure | 
CP5 | Laser beam line | 
CP6 | Beam instrumentation | 
CP7 | Plasma cell technology | 
To be filled before 31.03.2024

## Slide 6: Cabling requests
Important dates for AWAKE:
Cabling request deadline = 31.03.2024
Electrical network facility deadline = April 2024 ?
To be sent before 31.03.2024

## Slide 7: AWAKE run 2c installation schedule
The LS3 roadmap foresees:
  Master schedule by June 2024
  LS3 readiness review September 2024
For AWAKE, this means:
  Review of run2c schedule
  Identify which groups intervenes when
  Probable bottlenecks = EN-EL & EN-CV activities for 2026
Draft planning expected for June 2024

## Slide 8: Summary
Before 31.03.2024:
  Send cabling requests to EN-EL
  Enter your activity in PLAN
In the coming months, to be finalised by June:
  Review run2c installation schedule