## Slide 1: From AWAKE 2b to AWAKE 2c
De-cabling AWAKE 2b and installation (EN-EL) of AWAKE 2c Discussion with EN-EL, 14/3/2024

## Slide 2
Run2
2 Plasma Cells
2 Electron Sources
Klystrons
Spectrometer
Laser beam compressor 1
Laser beam compressor 2
2 WDL Chiller Units
AWAKE CNGS Area Dismantling is before & during LS3 (2025-2026)
Run2c Integration/installation/commissioning is during LS3 (2026-2028)
Run1
Step 1: dismantling of run 2b
TSG42
TSG43
TSG44
TSG45
UV laser room
Step 2: CNGS dismantling
Step 3: Run2c installation

## Slide 3: Timeline
If the 2 additional weeks of beam approved  ~1month shift
Step 1
End of Awake operations: October 2024
Run 2b dismantling: 2months of decommissioning + 3 months of transport
Decabling: ~2 months of works
DRAFT

## Slide 4: Run 2c installation
Installing run 2c during LS3 brings some constraints:
  Availability of resources
  Respect deadlines linked to LS3 even though the project is not yet approved
For AWAKE, next milestones:
  PLAN activities by 31.03.2024
  Cabling request by 15.04.2024
  Electrical network request by 15.04.2024
  Review of run2c schedule for June 2024
Step 3
Run2b operation
CNGS dismantling
Run 2c installation
Run2b dismantling

## Slide 5: General Awake roadmap
2023 | 2024 |  |  |  |  |  |  |  |  |  |  |  | 2025 |  | 
Dec. | Jan. | Feb. | March | April | May | June | July | Aug. | Sept. | Oct. | Nov. | Dec. | Jan. | Feb. | March
Inventory of equipment
Establish sequence for dismantling
Decommissioning
Transport out
Listing cables for decabling
Pre-identification of cables
Identification of cables (purple tape)
Decabling
Run 2b dismantling
Decabling
Preparation of lockout document
Input Awake activities in PLAN
Cabling requests
Review installation planning
Review integration layout of run2c
Run2c preparation
EL network request
5
Draft schedule
LS3 readiness review

## Slide 6: What we know: cabling
Cable routing study to be done.
  The area will be de-cabled
  New cables can use all 6 TSG4x galleries between TSG4 and TCC4
  TT43 will be empty (formerly e-beam) and can also be used for cable trays
Racks
E-sources
E-magnets
Plasma cells
RF Klystrons
Instrumentation
Beamlines (vac, BI, …)

## Slide 7: What we know: cabling & de-cabling
Estimate of cable amount exists – extrapolated from Run1/Run2ab
Cost and resource estimate from 2021 C&S Review on EDMS 3056166
Reasoning behind cabling & rack estimates (extrapolation) on EDMS 3062059.
WP | Name | GROUP | cost 2022 [kCHF] | cost 2023 [kCHF] | cost 2024 [kCHF] | cost 2025 [kCHF] | cost 2026 [kCHF] | cost 2027 [kCHF] | cost 2028 [kCHF] | cost 2029 [kCHF] | cost 2030 [kCHF] | cost 2031 [kCHF] | cost 2032 [kCHF] | cost TOTAL [kCHF] (incl. grad) |  | workforce 2022 [FTE.yr] | workforce 2023 [FTE.yr] | workforce 2024 [FTE.yr] | workforce 2025 [FTE.yr] | workforce 2026 [FTE.yr] | workforce 2027 [FTE.yr] | workforce 2028 [FTE.yr] | workforce 2029 [FTE.yr] | workforce 2030 [FTE.yr] | workforce 2031 [FTE.yr] | workforce 2032 [FTE.yr] | workforce TOTAL [FTE.yr] |  | cost grads TOTAL [kCHF] 2024-2032
WP24.1 | EL - Electrical System | EN-EL | 0 | 0 | 70 | 199 | 378 | 194 | 0 | 0 | 0 | 0 | 0 | 841 |  | 0.00 | 0.00 | 0.25 | 0.50 | 0.50 | 2.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 3.25 |  | 100
WP24.2 | EL - Cabling AC & DC | EN-EL | 0 | 0 | 0 | 322 | 904 | 211 | 0 | 0 | 0 | 0 | 0 | 1437 |  | 0.00 | 0.00 | 0.00 | 0.09 | 0.21 | 0.06 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.36 |  | 265
WP24.3 | EL - Decabling | EN-EL | 0 | 0 | 40 | 448 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 498 |  | 0.00 | 0.00 | 0.04 | 0.10 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.14 |  | 102

## Slide 8: What we know: electrical infrastructure
Document M. Lonjon March 2021
WP | Name | GROUP | cost 2022 [kCHF] | cost 2023 [kCHF] | cost 2024 [kCHF] | cost 2025 [kCHF] | cost 2026 [kCHF] | cost 2027 [kCHF] | cost 2028 [kCHF] | cost 2029 [kCHF] | cost 2030 [kCHF] | cost 2031 [kCHF] | cost 2032 [kCHF] | cost TOTAL [kCHF] (incl. grad) |  | workforce 2022 [FTE.yr] | workforce 2023 [FTE.yr] | workforce 2024 [FTE.yr] | workforce 2025 [FTE.yr] | workforce 2026 [FTE.yr] | workforce 2027 [FTE.yr] | workforce 2028 [FTE.yr] | workforce 2029 [FTE.yr] | workforce 2030 [FTE.yr] | workforce 2031 [FTE.yr] | workforce 2032 [FTE.yr] | workforce TOTAL [FTE.yr] |  | cost grads TOTAL [kCHF] 2024-2032
WP24.1 | EL - Electrical System | EN-EL | 0 | 0 | 70 | 199 | 378 | 194 | 0 | 0 | 0 | 0 | 0 | 841 |  | 0.00 | 0.00 | 0.25 | 0.50 | 0.50 | 2.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 3.25 |  | 100
WP24.2 | EL - Cabling AC & DC | EN-EL | 0 | 0 | 0 | 322 | 904 | 211 | 0 | 0 | 0 | 0 | 0 | 1437 |  | 0.00 | 0.00 | 0.00 | 0.09 | 0.21 | 0.06 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.36 |  | 265
WP24.3 | EL - Decabling | EN-EL | 0 | 0 | 40 | 448 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 498 |  | 0.00 | 0.00 | 0.04 | 0.10 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.14 |  | 102

## Slide 9: What we know: electrical infrastructure
Document M. Lonjon March 2021 EDMS 2471171
WP | Name | GROUP | cost 2022 [kCHF] | cost 2023 [kCHF] | cost 2024 [kCHF] | cost 2025 [kCHF] | cost 2026 [kCHF] | cost 2027 [kCHF] | cost 2028 [kCHF] | cost 2029 [kCHF] | cost 2030 [kCHF] | cost 2031 [kCHF] | cost 2032 [kCHF] | cost TOTAL [kCHF] (incl. grad) |  | workforce 2022 [FTE.yr] | workforce 2023 [FTE.yr] | workforce 2024 [FTE.yr] | workforce 2025 [FTE.yr] | workforce 2026 [FTE.yr] | workforce 2027 [FTE.yr] | workforce 2028 [FTE.yr] | workforce 2029 [FTE.yr] | workforce 2030 [FTE.yr] | workforce 2031 [FTE.yr] | workforce 2032 [FTE.yr] | workforce TOTAL [FTE.yr] |  | cost grads TOTAL [kCHF] 2024-2032
WP24.1 | EL - Electrical System | EN-EL | 0 | 0 | 70 | 199 | 378 | 194 | 0 | 0 | 0 | 0 | 0 | 841 |  | 0.00 | 0.00 | 0.25 | 0.50 | 0.50 | 2.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 3.25 |  | 100
WP24.2 | EL - Cabling AC & DC | EN-EL | 0 | 0 | 0 | 322 | 904 | 211 | 0 | 0 | 0 | 0 | 0 | 1437 |  | 0.00 | 0.00 | 0.00 | 0.09 | 0.21 | 0.06 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.36 |  | 265
WP24.3 | EL - Decabling | EN-EL | 0 | 0 | 40 | 448 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 498 |  | 0.00 | 0.00 | 0.04 | 0.10 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.14 |  | 102

## Slide 10: Extra: Surface building CNGS dismantling
SCE contact: David Gomez
Services contacts:
Installation services ~March-May 2025, will need cables.
Proposal: dedicated meeting with service contacts and EN-EL cabling
(needed before 15/4 or not?)