## Slide 2: BDF/SHiP at the High Intensity ECN3 facility
M. Fraser (SY-ABT-BTP)
on behalf of the HI-ECN3 Study Project Team
BDF Target & Target Complex Initial Review CERN, Geneva, Switzerland
29th April 2024

## Slide 3: Thoughts for today
Newcomers we will see a complete overview of the most critical system in the Beam Dump Facility:
  Please get involved, be active and share new ideas: profit from this opportunity to discuss
For the experienced BDF WG members, we have a chance to reflect:
  Baseline: what is our baseline today ? Can we converge on a baseline design before LS3 to guarantee reliable & safe operation in 2030 ?
  Baseline R&D: what are the most important problems to solve & test with beam before LS3 ? Scope? Can we converge on a prioritized list of activities with decision points on a timeline?
    Physics performance: what can we optimize further, is it worth it ?
    Reliability: validation with beam before LS3 is necessary / alternative labs for beam time during LS3 ?
    Safety: can we improve the choice of cladding material (LOCA) and reduce free radicals in cooling water ?
  Longer term R&D:
    Strategy for upgradeability: can we stage development to focus on safe/reliable operation at 41013 ppp but leave the door open to installing an upgraded target for ultimate SPS performance closer to 71013 ppp in ~ Run 5 ? … imagine a FIP signal is observed in Run 4 !
M. Fraser BDF/SHiP at the HI-ECN3 29th April 2024

## Slide 4
HI-ECN3 Study Project Team
Project Leader (PL):
Matthew FRASER
Deputy Project Leader (DPL):
Claudia AHDIDA
Project Safety Officer (PSO):
Melenia AVERNA
Project Radiation Safety Officer (PRSO):
TBC
Project Budget Officer:
Sylvie PRODON
Project Planning Officer (PPO):
Fernando PEDROSA
Configuration & Quality Assurance Manager:
Giulia ROMAGNOLI
Integration Support via ICEA:
Michael LAZZARONI
North Area Operation & Experiment Liason:
Dipanwita BANERJEE
SHiP Experiment (EP) Contact Person:
Richard JACOBSSON
SHiP Experiment (EP) Safety Correspondent:
Letizia DI GIULIO
Project & Experiment Safety Support (PESS) Correspondant :
James CURRIE
Admin Support:
Katarina SIGERUD & Diane KIVENDA MOKUBA
+ WPLs
WP2 – Beam Extraction, Transfer and Delivery
Francesco VELOTTI
Deputy Laurie NEVAY
WP3 – Target & Beam Intercepting Devices
Rui XIMENES
WP4 – Target Complex
Jean-Louis GRENARD
WP5 – Exp. Area, Interface & Integration
Francois BUTIN
WP6 – Radiation Protection & Safety
Claudia AHDIDA
WP7 – Infrastructure, Services & Civil Eng.
Fernando PEDROSA
DRAFT
WP8 – Energy Deposition Studies & R2E
Luigi ESPOSITO
WP1 – Project Management
Matthew FRASER
Deputy: Claudia AHDIDA
M. Fraser BDF/SHiP at the HI-ECN3 29th April 2024

## Slide 5: Project WBS v0.1
Planning, Scheduling & Coord.
Fernando PEDROSA
Budget & Resources
Sylvie PRODON
Procurement
Installation
Project Office
Matthew FRASER
Technical Coordination
Matthew FRASER
Configuration & Quality Management
Giulia ROMAGNOLI
Extraction
Pablo ARRUTIA
Primary Beam Line
Laurie NEVAY / Francesco VELOTTI
Power Converters
Ivan JOSIFOVIC
Instrumentation
Machine Protection
Antoine COLINET
Magnets
Philip SCHWARTZ
Operational Controls & Tools
Kevin LI
Beamline Shielding Improvements
Laurie NEVAY
Experiment Requirements
Richard JACOBSSON
Target Design & Engineering
Rui XIMENES
BIDs Design & Engineering
Rui XIMENES
Experiment Requirements
Richard JACOBSSON
Detailled Design & Production
Luca GENTINI
Target Instrumentation
Jerome LENDARO
Material R&D
Stefano SGOBBA
Energy Deposition & Radiation Effects
Luigi ESPOSITO
Target Complex Design & Engineering
Jean-Louis GRENARD
TC & Surface Building Integration
Jean-Louis GRENARD
Service Cell Systems
Jean-Louis GRENARD
Robotic Systems
Luca BUONOCORE
Remote Handling Systems
Roberto RINALDESI
Containment Systems
Jean-Louis GRENARD
Radioactive Components Storage & Disposal
Jean-Louis GRENARD
NA-CONS Synergism
Fernando PEDROSA
Civil Engineering
John OSBORNE
Gas Distribution
Davide JAILLET
Electrical & Fiber Infrastucture
Eva CANO GONZALEZ
Cryogenics
Survey & Alignment
Camille VENDEUVRE
Cooling & Ventilation
Roberto BOZZI
Handling Systems & Operational Support
Roberto RINALDESI
Telecom & Network
Expt Area Design & Engineering
Francois BUTIN
Global Integration (inc. Exp. Area Integration)
Francois BUTIN
TCC8/ECN3 Dismantling
Nicolas QUINQUIS / Francois BUTIN
Experiment Interfaces
Richard JACOBSSON
Accelerator Interfaces
Francois BUTIN
Shielding Proecurement & Recovery
Michael LAZZARONI
Experiment Installation
Francois BUTIN /
Richard JACOBSSON
Experiment Requirements
Richard JACOBSSON
Safety Files
Melania AVERNA
Radiation Protection
Claudia AHDIDA
Radioactive Waste Management
Renaud CHAROUSSET
Access & Safety Systems
Tomaz LADZINSKI / Anna SUWALSKA
Occupational Safety
Simon MARSH
Fire Safety
Oriol RIOS
Prototype Target Beam Test
Rui XIMENES
Accelerator Interfaces
Jean-Louis GRENARD
WP3 – Target & Beam Intercepting Devices
Rui XIMENES
WP4 – Target Complex
Jean-Louis GRENARD
WP5 – Exp. Area, Interface & Integration
Francois BUTIN
WP6 – Radiation Protection & Safety
Claudia AHDIDA
WP7 – Infrastructure, Services & Civil Eng.
Fernando PEDROSA
WP1 – Project Management
Matthew FRASER
Deputy: Claudia AHDIDA
Commissioning
WP2 – Beam Extraction, Transfer and Delivery
Francesco VELOTTI
Deputy: Laurie NEVAY
XTAX Upgrade
Miguel SANTOS
Magnetised Hadron Stopper
Vacuum Upgrade
Miguel SANTOS
WP8 – Energy Deposition Studies & R2E
Luigi ESPOSITO
DRAFT
M. Fraser BDF/SHiP at the HI-ECN3 29th April 2024

## Slide 6: Project Organisation: Modus Operandi
Strong link to NA-CONS:
  STAFF supporting HI-ECN3 were nominated for their involvement in NA-CONS (exception is EN-CV)
Efficient use of time is a guiding principle:
  WPLs are responsible for targeted meeting agendas and invitations, news / round-table to take place first 10 mins so STAFF experts can leave (if agenda not relevant)
GRAD team supported by CERN STAFF experts
SHiP Experiment Technical Coordinator (TC)
WP2 Coordination Meetings
Francesco VELOTTI
WP3 Coordination Meetings
Rui XIMENES
WP4 Coordination Meetings
Jean-Louis GRENARD
WP5 Coordination Meetings
Francois BUTIN
WP6 Coordination Meetings
Claudia AHDIDA
WP7 Coordination Meetings
= adhoc NA-CONS WC4
Fernando PEDROSA
Technical Design Study
Frequency is choice of WPL ~ Biweekly
Project Coordination & Integration
Project Management
Adhoc Meetings
Project Team Meetings
Claudia AHDIDA /
Matthew FRASER
~ Weekly
ICEA
Francois BUTIN /
Jean-Louis GRENARD
~ Biweekly
Joint with NA-CONS ICEA when relevant
HI-ECN3 TCC
Claudia AHDIDA /
Matthew FRASER
~ Monthly
Joint with NA-CONS TCC when relevant
Project Board Meetings
Matthew FRASER
~ Adhoc
NA-CONS / HI-ECN3
Steering Committee Meetings
Roberto LOSITO
~ Quarterly
Reviews:
C&S, Safety, Technical etc.
Joint NA-CONS when relevant
Project Safety Officers
Filipa CARVALHO NACONS
Melania AVERNA
HI-ECN3
CERN Management
IEFC
Brennan GODDARD
when reporting requested
ATS-MB
Mike LAMONT
when reporting requested
NA62 TC
Decommissioning
ICL
(upstream TCC2)
EN-ACE
M. Fraser BDF/SHiP at the HI-ECN3 29th April 2024

## Slide 7: HI-ECN3 Study Project Scope
Study Project (TDR) transitioning into a Project simultaneously:
  Budget profile (2024 - 2031): update already provided and included in MTP2024
  Preparations for Long Shutdown 3:
    Definition of interfaces with NA-CONS: decouple access system and services so that upgrade work on TCC8/ECN3 can carry on in parallel to North Area operation (EHN1 and EHN2)
    Specification / design / installation: upstream equipment, primary zones inc. NA-CONS equipment and installation of beam dump in P42: many items on critical path!
    Dismantling of TCC8 and ECN3: cable/services identification, decabling, radioactive transport/waste mgmt
    (Radioactive) Storage
    Sustainability / cost saving: recovering shielding from PS TT7 Neutrino facility before LS3
WBS:
  AS TDR advances, together we must converge on a WBS with WP descriptions and agree cost & resources with the Budget Plan implemented by end 2025
Civil Engineering already on the critical path:
  Pre-studies ongoing, IRP Due Diligence moving to Design Study
ECN3 High Intensity Study Project Mandate, EDMS #2921486
M. Fraser BDF/SHiP at the HI-ECN3 29th April 2024

## Slide 8: Study Project Milestones
NA-CONS C&S Review: align for MTP2024 – February 2024
Experiment(s) Decision at Research Board – 6 March 2024
  Launch Safety Discussion: start Initial Enquiry for PESS Process
  Launch preparations for dismantling of TCC8 / ECN3
  Launch CERN TT7 Shielding Recovery Project
  Update MTP2024
Formal HI-ECN3 Project Approval (MTP2024) – after CERN RB June 2024
  Mandate including transition from Study → Project
First draft TDR “lite” & WBS – by end 2024
  Work Package Descriptions (first drafts) agreed with groups
  Project roadmap documentation (including budget plan, BC’s, ATS person power plan, etc.)
IRP Due Diligence – May 2024
IRP Authorisation – Q3 2025
Final TDR & WBS – by end 2025
See ECN3 High Intensity Study Project Mandate, EDMS #2921486
… do not forget this is a TDR Study Project transitioning into a Project simultaneously
M. Fraser BDF/SHiP at the HI-ECN3 29th April 2024

## Slide 9
Thank you !
BDF/SHiP at the HI-ECN3

## Slide 10: Study Project (TDR) STAFF Experts (SY)
Group | Contact | Activity | GRAD Support 2024/25
SY-BI | David BELOHRAD | TL & Experiment Specific BI | 
SY-BI | Christos ZAMANTZAS | BLMs | ✓
SY-AR | Katarina SIGERUD | Project Admin Support: Diane KIVENDA MOKUBA (SY-ABT) | 
SY-ABT | Francesco VELOTTI | WP2 | ✓
SY-EPC | Yves GAILLARD | TDR | 
SY-EPC | Ivan JOSIFOVIC | TDR | 
SY-RF | Giulia PAPOTTI | TDR (RF support for slow extraction) | 
SY-STI | Rui FRANQUEIERA XIMENES | WP3 | ✓
SY-STI | Jean-Louis GRENARD | WP4 | 
SY-STI | Ruben ALIA | R2E support TDR | 
SY-HDO | Anne FUNKEN | Safety Support | 
SY-STI | Melania AVERNA | Project Safety Officer | 
SY-STI | Luigi ESPOSITO | FLUKA support for TDR | ✓
Support from CERN groups:
  GRAD support (2 yr) TDR phase, only if STAFF supervision guaranteed (no STAFF M2P)
  Synergy to NA-CONS key (if possible, same STAFF member on both projects)
  WP descriptions (agreed deliverables & resources) to be written with the GRAD support
M. Fraser BDF/SHiP at the HI-ECN3 29th April 2024

## Slide 11
Group | Contact | Activity | GRAD Support 2024/25
BE-CEM | Jerome LENDARO | Target Instrumentation | 
BE-CEM | Luca BUONOCORE | Robotics / Tooling | 
BE-GM | Camille VENDEUVRE | Survey | 
BE-EA | Michael LAZZARONI | Integration (global via ICEA) | ✓
BE-EA | Francois BUTIN | WP5 | ✓
BE-EA | Johannes BERNHARD | WP2 | 
BE-EA | Dipanwita BANERJEE | North Area Operation & Experiment Liason | ✓
BE-EA | Laurence NEVAY | WP2 | ✓
BE-EA | Giulia ROMAGNOLI | Configuration Management | 
BE-OP | Kevin LI | SPS OP | 
BE-ABP | Hannes BARTOSIK | TDR | 
BE-CSS | TBC | TDR | 
Support from CERN groups:
  GRAD support (2 yr) TDR phase, only if STAFF supervision guaranteed (no STAFF M2P)
  Synergy to NA-CONS key (if possible, same STAFF member on both projects)
  WP descriptions (agreed deliverables & resources) to be written with the GRAD support
Study Project (TDR) STAFF Experts (BE)
M. Fraser BDF/SHiP at the HI-ECN3 29th April 2024

## Slide 12
Group | Contact | Activity | GRAD Support 2024/25
EN-AA | Anna SUWALSKA | TDR | 
EN-AA | Tomasz LADZINSKI | TDR | 
EN-ACE | Fernando PEDROSA | Planning / Coordination | ✓
EN-ACE | Frederic GALLEAZZI | Integration for SPS / NA primary | 
EN-CV | Roberto BOZZI / Francesco DRAGONI* | TDR | ✓
EN-EL | Eva CANO GONZALEZ | TDR | ✓
EN-HE | Roberto RINALDESI | TDR | ✓
EN-MME | Luca GENTINI | TDR | 
EN-MME | Stefano SGOBBA | Material R&D for TDR | 
Group | Contact | Activity | GRAD Support 2024/25
TE-MPE | Antoine COLLINET | TDR | 
TE-MSC | Philipp SCHWARZ | TDR | 
TE-VSC | Anthony HARRISON | Primary VSC support for TDR | 
*Not named in NA-CONS WBS – to link with Serge DELEVAL
Support from CERN groups:
  GRAD support (2 yr) TDR phase, only if STAFF supervision guaranteed (no STAFF M2P)
  Synergy to NA-CONS key (if possible, same STAFF member on both projects)
  WP descriptions (agreed deliverables & resources) to be written with the GRAD support
Study Project (TDR) STAFF Experts (EN, TE)
M. Fraser BDF/SHiP at the HI-ECN3 29th April 2024

## Slide 13
Group | Contact | Activity | GRAD Support 2024/25
SCE | John OSBORNE | Preparatory Civil Work | ✓ TEMP → GRAD
HSE-OHS | Simon MARSH | PESS | ✓
HSE-OHS | Oriol RIOS | FIRIA | ✓
HSE-RP | Claudia AHDIDA | DPL / WP5 | ✓
HSE-RP | Renaud CHAROUSSET | Radioactive Waste Management | 
EP | Awaiting EP’s official nomination for SHiP Technical Coordinator |  | 
EP | Hans DANIELSSON | NA62 Technical Coordinator | 
EP | Richard JACOBSSON | SHiP EP Contact Person | 
EP | Letizia DI GIULIO | SHiP EP Safety Correspondantn | 
Study Project (TDR) STAFF Experts (HSE, EP)
Support from CERN groups:
  GRAD support (2 yr) TDR phase, only if STAFF supervision guaranteed (no STAFF M2P)
  Synergy to NA-CONS key (if possible, same STAFF member on both projects)
  WP descriptions (agreed deliverables & resources) to be written with the GRAD support
M. Fraser BDF/SHiP at the HI-ECN3 29th April 2024

## Slide 14: Study Project (TDR) GRAD Team
Person | Role | Group | Supervisor | Programme | BC Description | PRQ | Start Date
Ixone VAQUERO | Planning & Coordination | EN-ACE | Fernando PEDROSA | ORIGIN | HI-ECN3 / NA-CONS | Completed | 1/10/2023
Xavier PALLE | Planning & Coordination | EN-ACE | Fernando PEDROSA | ORIGIN | HI-ECN3 / NA-CONS | Completed | 1/3/2024
Kincso PAL | TDR | SCE | John OSBORNE | TEMP | HI-ECN3 | Completed | 1/1/2024
James CURRIE | TDR | HSE-OHS | Simon MARSH | ORIGIN | HI-ECN3 | Completed | 1/2/2024
TBC | FIRIA | HSE-OHS | Saverio LA MENDOLA | QUEST | HI-ECN3 / HSE | 2024 | Q3 2024
TBC | TDR → Implementation | SCE | Natacha LOPEZ | QUEST | HI-ECN3 | 2025 | Q1 2025
Nikola ZARIC | TDR | EN-CV | Roberto BOZZI | QUEST | HI-ECN3 | Completed | 1/2/2024
Angelo PETRELLESE | Secondary Vacuum | BE-EA | Miguel SANTOS | ORIGIN | HI-ECN3 / NA-CONS / PBC | Completed | 1/4/2024
Fabian METZGER | TDR | BE-EA | Laurence NEVAY | GRAF | HI-ECN3 | Completed | 1/4/2024
TBC | TDR / LS3 prep | BE-EA | Francois BUTIN | ORIGIN | HI-ECN3 | 2024/25 | TBC
Beatriz MARTINEZ | TDR | BE-EA | Michael LAZZARONI | ORIGIN | HI-ECN3 | Completed | 2/5/2024
Ming LIU | TDR | EN-EL | Eva CANO GONZALEZ | QUEST | HI-ECN3 / NA-CONS | Completed | 2/5/2024
Cristina DURAN GUTIERREZ | TDR | EN-HE | Roberto RINALDESI | ORIGIN | HI-ECN3 | Completed | 1/6/2024
Olin PINTO | TDR | HSE-RP | Claudia AHDIDA | QUEST | HI-ECN3 | Completed | 1/2/2024
Mike PARKIN | TDR | SY-STI | Rui FRANQUEIRA XIMENES | QUEST | HI-ECN3 | Completed | 1/3/2024
Giuseppe MAZZOLA | R2E / FLUKA | SY-STI | Luigi ESPOSITO | QUEST | HI-ECN3 | Completed | 1/2/2022
TBC | BLM | SY-BI | Christos ZAMANTZAS | ORIGIN | HI-ECN3 | ? | ?
TBC | TCSC CONS | SY-STI | Nicolas SOLIERI | QUEST | NA-CONS | ? | ?
TBC | TDC2 / TCC2 | HSE-RP | Helmut VINCKE | QUEST | NA-CONS | 2024 | TBC
Luke DYKS | TDR | BE-EA | Dipanwita BANERJEE | GRAF | HI-ECN3 | Completed | 1/9/2022
Alexander GORN | TDR | SY-ABT | Matthew FRASER | GRAF | PBC / SY | Completed | 1/10/2023
Tamara BUD | ECN3 tasks on request | SCE | John OSBORNE | QUEST | PBC | Completed | 1/1/2024
Francesca LUONI | ECN3 tasks on request | HSE-RP | Claudia AHDIDA | FELL | PBC | Completed | 1/9/2023
Tirsi PREBIBAJ | ECN3 tasks on request | BE-ABP | Hannes BARTOSIK | GRAF | PBC | Completed | 1/3/2023
M. Fraser BDF/SHiP at the HI-ECN3 29th April 2024

## Slide 15: Project Resources: quick reminder (i)
PBC ECN3 Task Force: budget estimate (~ Class 3 - 4)
  Agreed by CERN groups at 324th IEFC meeting 3 March 2023 (no project STAFF M2P)
  Presented to the 244th CERN Research Board 6 March 2023
  Beam Delivery = 14 MCHF
M. Fraser HI-ECN3 Study Project: status update NA-CONS Cost & Schedule Review 6 February 2024
Cost Categories | Resource Context (including M2P) | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | Total
 |  | [kCHF rounded to closest 25k]* |  |  |  |  |  |  |  |  | 
Beam Delivery | Operation Critical (NA-CONS**) and HI specific | 125 | 450 | 1150 | 2525 | 3550 | 2875 | 575 | 225 | 0 | 11475
 | TDR: Engineering & Optimization Phase (GRAD)*** | 550 | 1125 | 1125 | 0 | 0 | 0 | 0 | 0 | 0 | 2800
 | Sub-Total: | 675 | 1575 | 2275 | 2525 | 3550 | 2875 | 575 | 225 | 0 | 14275
C. Ahdida et al., Findings of the Physics Beyond Colliders ECN3 Beam Delivery Task Force, CERN-PBC-REPORT-2023-001
  ** NA-CONS new baseline items motivated by risk to reliability of HI-ECN3 operation after LS3
  *** TDR GRAD request based on same ratio of GRAD/CtC of NA-CONS project working out at ~ 2.8 MCHF or 10 FTE for 3 years
  * Budget profiling is a very rough estimate (peaking after LS3) and needs to be iterated in TDR phase

## Slide 16: Project Resources: quick reminder (ii)
M. Fraser HI-ECN3 Study Project: status update NA-CONS Cost & Schedule Review 6 February 2024
Cost Categories | Resource Context (including M4P) | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | Total | %
 |  | [kCHF rounded to closest 25k]* |  |  |  |  |  |  |  |  |  | 
BDF/SHiP | Civil Engineering | 0 | 100 | 200 | 300 | 500 | 2450 | 3350 | 2450 | 500 | 9850 | 20
 | Target Station & beam dilution | 0 | 200 | 425 | 625 | 1050 | 5250 | 7150 | 5250 | 1050 | 21000 | 42
 | Infrastructure & Services | 0 | 150 | 300 | 475 | 775 | 3850 | 5250 | 3850 | 775 | 15425 | 31
 | Integration, Dismantling, Installation | 25 | 150 | 375 | 825 | 1150 | 925 | 175 | 75 | 0 | 3700 | 7
 | Sub-Total: | 25 | 600 | 1300 | 2225 | 3475 | 12475 | 15925 | 11625 | 2325 | 49975 | 100
PBC ECN3 Task Force: budget estimate (~ Class 3 - 4)
  Agreed by CERN groups at 324th IEFC meeting 3 March 2023 (no project STAFF M2P)
  Presented to the 244th CERN Research Board 6 March 2023
  Beam Delivery = 14 MCHF + BDF/SHiP facility (50 MCHF) → Total = 64 MCHF
  * Budget profiling is a very rough estimate (peaking after LS3) and needs to be iterated in TDR phase
C. Ahdida et al., Findings of the Physics Beyond Colliders ECN3 Beam Delivery Task Force, CERN-PBC-REPORT-2023-001
Synaxis AG, … ECN3 & TCC8 - Report of Preliminary Study, EDMS#2815529

## Slide 17: Project Resources: quick reminder (iii)
PBC ECN3 Task Force: budget estimate (~ Class 3 - 4)
  Agreed by CERN groups at 324th IEFC meeting 3 March 2023 (no project STAFF M2P)
  Presented to the 244th CERN Research Board 6 March 2023
  No significant cost difference between experiment options
  Beam Delivery = 14 MCHF + HIKE/SHADOWS facility (46 MCHF) → Total = 60 MCHF
M. Fraser HI-ECN3 Study Project: status update NA-CONS Cost & Schedule Review 6 February 2024
Cost Categories | Resource Context (including M2P) | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | Total | %
 |  | [kCHF rounded to closest 25k] |  |  |  |  |  |  |  |  |  | 
HIKE / SHADOWS | Civil Engineering (no additional access shaft requested) | 0 | 50 | 125 | 175 | 300 | 1500 | 2025 | 1500 | 300 | 5975 | 13
 | Target Station | 0 | 175 | 325 | 500 | 825 | 4150 | 5650 | 4150 | 825 | 16600 | 36
 | Infrastructure & Services | 0 | 175 | 350 | 525 | 850 | 4300 | 5850 | 4300 | 850 | 17200 | 37
 | Integration, Dismantling, Installation | 25 | 150 | 375 | 825 | 1150 | 925 | 175 | 75 | 0 | 3700 | 8
 | Phase-II Beamline & Infrastructure Changes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 2500 | 6
 | Sub-Total: | 25 | 550 | 1175 | 2025 | 3125 | 10875 | 13700 | 10025 | 4475 | 45975 | 100
C. Ahdida et al., Findings of the Physics Beyond Colliders ECN3 Beam Delivery Task Force, CERN-PBC-REPORT-2023-001
Synaxis AG, … ECN3 & TCC8 - Report of Preliminary Study, EDMS#2815529

## Slide 18: MTP 2023 request
MTP 2023 request of 2.85 MCHF for 2023 & 2024:
  This included additional NA-CONS items deemed critical for the future operation of the HI-ECN3 facility: we requested an increase in the Cost-to-Completion of NA-CONS
M. Fraser HI-ECN3 Study Project: status update NA-CONS Cost & Schedule Review 6 February 2024
S. Prodon, ECN3 High Intensity Study Initial Allocation (MTP 2023), EDMS#2937504
2175
675
3575

## Slide 19: MTP 2023 arbitration
M. Fraser HI-ECN3 Study Project: status update NA-CONS Cost & Schedule Review 6 February 2024
MTP 2023 decision by the DG:
  ‘Allocate 2.5 MCHF for 2023 and 2024 for the preliminary works, waiting for the project to be officially approved.’
Allocated budget per year in [kCHF]
0
0
0
0
0
0
0
0
0
0
0
0
0
0
1100
0
1400
875
875
1825
675
950
1400
1100
950
1100
875
S. Prodon, ECN3 High Intensity Study Initial Allocation (MTP 2023), EDMS#2937504
2500

## Slide 20: Budget Transfer to NA-CONS
700 kCHF was transferred from HI-ECN3 to NA-CONS to advance on many new LS3 critical consolidation items requested for HI-ECN3:
  TCSC (Transfer Line Splitter Collimator) consolidation
  RP support for primary NA zones
  Transfer line magnets (magnetic measurements, spares, etc.)
  Beam instrumentation
M. Fraser HI-ECN3 Study Project: status update NA-CONS Cost & Schedule Review 6 February 2024
S. Prodon, ECN3 High Intensity Study Financial Situation 2024, EDMS#2939799
HI-ECN3 Study Project therefore has a shortfall in 2023/24 of 350 kCHF requested:
  1.8 MCHF approved vs. 2.85 MCHF requested (after items assigned NA-CONS)

## Slide 21: TDR GRAD team budget
M. Fraser HI-ECN3 Study Project: status update NA-CONS Cost & Schedule Review 6 February 2024
Dep | Group | WP | Category | BC Description | Detailed Description | 2023 | 2024 | 2025 | 2026 | Total
SY | SY-STI | 3&4 | QUEST | TDR preparation: SY-STI | Target R&D |  | 82.5 | 110 | 27.5 | 220
EN | EN-ACE | 1 | ORIGIN | TDR preparation: EN-ACE | Planning/Scheduling | 10 | 40 | 30 | 0 | 80
EN | EN-ACE | 1 | ORIGIN | TDR preparation: EN-ACE | Planning/Scheduling |  | 30 | 40 | 10 | 80
HSE | HSE-RP | 6 | QUEST | TDR preparation: HSE-RP | Including 25% RP source term contribution |  | 101 | 110 | 9 | 220
EN | EN-CV | 3&4&5 | QUEST | TDR preparation: EN-CV | TDR |  | 110 | 110 | 0 | 220
EN | EN-EL | 4&5 | QUEST | TDR preparation: EN-EL | TDR |  | 55 | 55 | 0 | 110
EN | EN-HE | 4&5 | ORIGIN | TDR preparation: EN-HE | TDR |  | 60 | 80 | 20 | 160
EN | EN-HE | 4&5 | TEMP | TDR preparation: EN-HE | External Contractor 4 months at average of 30% |  | 11 |  |  | 11
BE | BE-EA | 2 | GRAF | TDR preparation: BE-EA-LE | TDR: Beam Line Support |  | 110 | 110 | 0 | 220
SCE | SCE-PPM | 7 | QUEST | TDR preparation: SCE-PPM | Supporting handover to implementation phase |  | 55 | 110 | 55 | 220
SCE | SCE-SAM | 7 | TEMP | TDR preparation: SCE-SAM | 4-month handover to new PBC FELL |  | 37 |  |  | 37
HSE | HSE-RP | 6 | QUEST | TDR preparation: HSE-OHS-RP | FIRIA - RP Environmental Engineer, FIRIA 25% contribution: |  |  | 27.5 | 27.5 | 55
HSE | HSE-OHS | 6 | QUEST | TDR preparation: HSE-OHS-IB | FIRIA - Fire Safety Engineer, Shared 50:50 with HSE |  | 14 | 55 | 41 | 110
HSE | HSE-OHS | 6 | QUEST | TDR preparation: HSE-OHS-PE | Technical Safety Engineer |  | 101 | 110 | 9 | 220
SY | SY-STI | 3&4&5 | QUEST | TDR preparation: SY-STI | R2E / FLUKA studies |  |  | 110 | 110 | 220
SY | SY-BI | 2 | ORIGIN | TDR preparation: SY-BI | Electronics for BLM work (oBLMS &ICs) |  | 20 | 80 | 60 | 160
BE | BE-EA | 2 | ORIGIN | TDR preparation: BE-EA | Supporting P42 Vacuum upgrade, Shared with PBC and NA-CONS: |  | 27 | 27 |  | 53
SY | SY-BI | 2 | TECH | TDR preparation: SY-BI | P42 BLM Part 2 TECH |  |  | 42 |  | 42
BE | BE-EA | 5 | ORIGIN | TDR preparation: BE-EA | Integration support for dismantling and shielding recovery |  |  | 80 | 80 | 160
BE | BE-EA | 5 | ORIGIN | TDR preparation: BE-EA | Integration support for ICEA |  | 20 | 80 | 60 | 160
Total |  |  |  |  |  | 10 | 872 | 1'366 | 510 | 2'758
Discussion continue with CERN groups: the team is now reaching the 2.8 MCHF TDR GRAD budget request:
DRAFT

## Slide 22: Urgent Items (in view of approval)
M. Fraser HI-ECN3 Study Project: status update NA-CONS Cost & Schedule Review 6 February 2024
DRAFT
Dep | Group | WP | M / P Category | HI-ECN3 Category | BC Description | Detailed Description | 2023 | 2024 | 2025
SY | SY-ABT | 1 | Material | TDR | Project Management |  |  | 150 | 150
HSE | HSE-RP | 2 | Material | Beam Delivery | Additional RP Monitors for Beam Delivery |  | 35 | 10 | 
BE | BE-GM | 4&5 | M+P | Experiment - HIKE/SHADOWS | TDR preparation: BE-GM |  |  | 65 | 65
SY | SY-STI | 3 | Material | Experiment | Target R&D including Prototype Beam Test |  |  | 230 | 470
TE | TE-MSC | 2 | Material | Beam Delivery | Production of Laminated Magnets for T4 Bump and P42 Dump |  |  | 45 | 45
SY | SY-BI | 2 | Material | Beam Delivery | Repayment of P42 BLM Part 1 |  |  |  | 130
SY | SY-BI | 2 | Material | Beam Delivery | P42 BLM Part 2 |  | 0 | 39 | 27
HSE | HSE-RP | 2 | M+P | Beam Delivery | EHN1 ramp Classification RP |  |  | 50 | 100
HSE | HSE-RP | 2 | M+P | Beam Delivery | ECN3 bridge shielding |  |  | 50 | 150
SY | SY-STI | 3 | Material | Beam Delivery | P42 Beam Dump |  | 20 | 180 | 
TE | TE-MPE | 2 | M+P | Beam Delivery | Machine Protection for Beam Delivery |  |  | 100 | 100
SY | SY-ABT | 2 | M+P | Beam Delivery | Low-Z Electrostatic Septa |  |  | 100 | 100
TE | TE-MSC | 2 | Material | Beam Delivery | Production of 11 Laminated MDX for P42 |  |  | 15 | 240
BE | BE-EA | 2 | Material | Beam Delivery | XTAX High Intensity Upgrade - Design |  |  | 10 | 
SY | SY-EPC | 2 | Material | Beam Delivery | Production of 2 POLARIS for T4 Bump and P42 Dump |  |  |  | 150
BE | BE-EA | 2 | Material | Beam Delivery | P42 Vacuum upgrade |  |  |  | 200
SY | SY-ABT | 2 | QUEST | Beam Delivery | Extraction and Beam Transfer |  |  |  | 28
SY | SY-STI | 4 | M+P | Experiment | TT7 shielding recovery |  |  | 200 | 700
SY | SY-STI | 4 | M+P | Experiment | Target and coil handling system |  |  | 25 | 25
SY | SY-STI | 4 | M+P | Experiment | Vacuum Vessel containing target system |  |  | 35 | 55
SY | SY-STI | 4 | M+P | Experiment | Target system integration & R&D |  |  | 50 | 50
BE | BE-EA | 5 | MPA | Experiment | Cable Identification Campaign Pre-LS3 |  |  | 10 | 10
EN | EN-HE | 4&5 | M+P | Experiment | TCC8/ECN3 transfer table refurbishment |  |  |  | 100
EN | EN-HE | 4 | M+P | Experiment | Complete upgrade of the TCC8 crane |  |  |  | 400
SCE | SCE-PPM | 7 | M+P | Experiment | SCE pre-studies needed in 2025 |  |  | 3 | 100
Total |  |  |  |  |  |  | 55 | 1'367 | 3'395

## Slide 23: HI-ECN3 Study Project Budget Request 2024/25
M. Fraser HI-ECN3 Study Project: status update NA-CONS Cost & Schedule Review 6 February 2024
 | 2023 [kCHF] | 2024 [kCHF] | 2025 [kCHF] | … | Project Total [kCHF]
TDR GRADs | 10 | 872 | 1366 |  | -
Reprofile of Urgent HI-ECN3 Items | 55 | 1367 | 3395 |  | -
To NA-CONS | 206 | 495 | 920 |  | 4733
HI-ECN3 Study Project | 271 | 2734 | 5681 |  | 65083
MTP 2023 Request | 700 | 2175 | 3575 |  | 64250
 | -429 | +559 | +2106 |  | +833
DRAFT