## Slide 1: 1T region redesign: bellows assembly progress and August opening timeline
05.2024

## Slide 2: Bellows assembly for the 1T
4K
70K
RT

## Slide 3: Bellows assembly for the 1T

## Slide 4: Bellows assembly for the 1T
Electric elements already at CERN

## Slide 5: Bellows assembly for the 1T

## Slide 6: Bellows assembly for the 1T

## Slide 7: Bellows assembly for the 1T

## Slide 8
Bellows assembly for the 1T

## Slide 9: Bellows assembly for the 1T
Status:
Bellows at CERN
Feedthroughs, rotary flanges… at CERN
Materials in the CERN workshop
Machining of the central ring components is ongoing
Price: ~20K CHF (with leak testing and UHV cleaning)
Lead time: mid-June
To-do
Plastic support for the bellows
Aluminum frame for installation

## Slide 10: Bellows assembly for the 1T
Issues: Getter pumping for the bellow
Original plan: Getter (NEG covered) stainless steel foil inside of the bellow
Heating element, temp sensor, junction module attached/welded to the foil
Heating element compatible with UHV and
cryo conditions very difficult to find

## Slide 11
Bellows assembly for the 1T

## Slide 13: 1T cryostat face modifications

## Slide 14: 1T cryostat face modifications

## Slide 15: 1T cryostat face modifications

## Slide 16: 1T cryostat face modifications

## Slide 17: 1T cryostat face modifications

## Slide 18: 1T cryostat face modifications

## Slide 19: 1T cryostat face modifications

## Slide 20: FACT module management
Challenges:
Move FACT modules aside to make enough space for the GV, anti-sun and anti-sun ports (including CF63 turbo pump)
Respect the FACT fiber lengths (~30 cm from the cryostat face)
Properly support the weight of the modules

## Slide 21: FACT module management

## Slide 22: FACT module management

## Slide 23: FACT module management

## Slide 24: FACT module management

## Slide 25: FACT module management

## Slide 26: FACT module management

## Slide 27: FACT module management

## Slide 28: FACT module management

## Slide 29: FACT module management

## Slide 30: FACT module management

## Slide 31: FACT module management

## Slide 32: FACT module management

## Slide 33: FACT module management
Price estimate:
- (3x) custom LF160 to 2 x KF40 reducer - 400 E
- (6x) short hydraulically formed bellow KF40 – 100 E
- (6x) LF160 to KF40 reducing flange – 250 E
- (1x) custom LF160 tee – 300 E
Total: 3600 E

## Slide 34: Cryo schedule and August opening

## Slide 35: Cryo schedule and August opening
Opening for the 1T bellows installation – beginning of August/end of July
Intervention of min 4 weeks: new 1T MCP mechanism, bellows, FACT module rearrangement, GV1 cleaning, HgHg MCP installation
We should try not to open any more before the LHC run of 2026
We need to have the gravity module (plus the anti-sun) in place by the end of the year

## Slide 37: Thank you for your attention

## Slide 38: Bellows assembly for the 1T
Issues: Getter pumping for the bellow
Possible solution: Getter Waffer
Off the shelf (4-6 weeks lead time)
Price: 3-6K + 3K for the controller