## Slide 1
CERN-FAIR-GSI Collaboration Meeting
26th April 2024
FAIR & GSI Status - April 2024
Jörg Blaurock
Technical Managing Director FAIR GmbH & GSI GmbH

## Slide 2
Agenda
FAIR Phase 0
Beamtime 2024
Development on campus
Campus Infrastructure
Construction of FAIR
FAIR in 2028
FAIR Highlights
FAIR in Construction
FAIR Outlook 2024
Upgrade of existing accelerators

## Slide 3
FAIR phase 0 beamtime 2024
102 days of user beamtime incl. HITRAP commissioning + 15 days for machine studies

## Slide 4
FAIR phase 0 beamtime 2024
4
physics run started on February 7th and ends on June 27th
  Available machines: UNILAC, SIS18, FRS, ESR & Cryring
  total 2448 hours of user operation
  plus 15 days dedicated to machine studies
  including 2 x 11 days for commissioning of HITRAP

## Slide 5
Beam time 2024/2025/2026
2024 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
J |  | F |  | M |  | A |  | M |  | J |  | J |  | A |  | S |  | O |  | N |  | D |  |  |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Machine Commissioning
 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Beam Time
2025 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
J |  | F |  | M |  | A |  | M |  | J |  | J |  | A |  | S |  | O |  | N |  | D |  |  |  |  | Physics Beam Time
 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Commissioning FCC &
 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | UNILAC Controls Upgrade
 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Best Effort User Operation
2026 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
J |  | F |  | M |  | A |  | M |  | J |  | J |  | A |  | S |  | O |  | N |  | D |  |  |  |  | 

## Slide 6
Agenda
FAIR Phase 0
Beamtime 2024
Development on campus
Campus Infrastructure
Construction of FAIR
FAIR in 2028
FAIR Highlights
FAIR in Construction
FAIR Outlook 2024
Upgrade of existing accelerators

## Slide 7: Campus Master Plan - Infrastructure
Perspektive für Endausbau 2030

## Slide 8: FAIR Highlights - FAIR Control Center (FAIR CC)
In accordance with the Campus Master Plan (CMP) the FAIR Control Center building will house the new Main Control Room (MCR) and scientific & technical office workplaces.
Use: MCR, Visitor access
206 Office workplaces
5 levels plus one undergroud level
Constr. period: Q2/2021 – Q3/2025
Commissioning: Q4/2025
FCC

## Slide 9: FAIR Highlights - FAIR Control Center (FAIR CC)
View on the north and south facade View on the main entrance
View on the façade in the MCR

## Slide 10
Agenda
FAIR Phase 0
Beamtime 2022
Development on Campus
Campus Infrastructure
Construction of FAIR
FAIR in 2028
FAIR Highlights
FAIR in Constrcution
FAIR Outlook
Upgrade of existing accelerators

## Slide 11
Thank you for your attention !
Thank you for your attention !
First Science +
MSV completion
Next steps
SIS18
SIS100
Super-FRS
ESR
CRYRING
UNILAC
Continuation of APPA, CBM and NUSTAR experiments in existing facility
APPA, NUSTAR and PANDA investigate options for further experiments at green lines
CBM
NUSTAR HEB
HITRAP
FAIR in 2028

## Slide 12: FAIR Highlights - SIS100
  January 2024
  First Power Supply Units placed in the SIS100 tunnel
  April 2024
  First cryogenic bypass lines SIS100 placed in SIS100 tunnel
  April 2024
  Delivery of SIS100 Dipole magnets in SIS100 tunnel

## Slide 13
© Beata Walasek-Höhne
FAIR Highlights - SIS100
April 2024: First superconducting dipoles and cryo bypass lines were placed in the SIS100 tunnel

## Slide 14: FAIR Highlights - SIS100
  December 2023
  Successfull completion of the first thermal cycle of the SIS100 string.
26th FAIR Machine Advisory Committee took place from 11th - 13th December, 2023.

## Slide 15: FAIR Highlights - HEBT
  March 2024
  Transport of Quadrupole magnets for beam line section T1S2

## Slide 16: FAIR Highlights - Cryo Facility
  April 2024
  6 Helium tanks of the Cryo facility
  were installed on construction site
  April 2024
  Center piece Cold Box of the cooling system for the superconducting magnets. Start of Commissioning in 2025

## Slide 17: FAIR Highlights - Compressor room

## Slide 18: FAIR Highlights - Storage and Logistics
  completed and delivered high-tech components for accelerator & experiments
Storage area Weiterstadt: approx. 9.900 m²
4.195 objects (Components, assemblies, boxes)
SIS100 Dipoles complete
50% of SIS100 components stored
90% of HESR components stored
He-Bypass lines from Poland
Racks from India

## Slide 19: FAIR Highlights - Civil
  February 2024
Start of Interior coating work in Super-FRS Building “L0516A”
  March 2024
Shell construction of Super-FRS Building “L0516A” completed

## Slide 20: FAIR Highlights - Technical Building Installation
  February 2024
  Integration of the emergency power supply units NEA by Natus

## Slide 21
FAIR in construction
NUSTAR LEB
NUSTAR HEB
S-FRS
SIS100
CRYO 2
APPA

## Slide 22
FAIR in construction
Area North

## Slide 23
FAIR in construction
Area South

## Slide 24
FAIR in construction First 2 air coolers installed on the building H0719 A

## Slide 25
FAIR in construction SIS100 Tunnel – Technical Building Installation

## Slide 26
FAIR in construction Transfer building – massive delivery of components of the cooling water system

## Slide 27
FAIR in construction Transfer building – ventilation system installation

## Slide 28
FAIR Outlook
ACC installation started in January 2024
TBI installation works in buildings progressing well aiming at completion and commissioning in 2026
Essential for the ACC installation progress: Continuous delivery of ACC components to secure the timely completion of ES/FS
Essential: Further international Shareholder contributions for the realization of First Science + (Poland, France, Sweden, Romania, India)
Decision in July 2024 on new budget line for commissioning in the years 2025 to 2028 and operation from 2029 onwards as well as on the company model

## Slide 29
3D models - NUSTAR HEB cave

## Slide 30
3D models - SIS100 tunnel

## Slide 31
Thank you for your attention !