## Slide 1
April 2024
IMCC ESPPU Plans
D. Schulte
for the International Muon Collider Collaboration
This project has received funding from the European Union’s Research and Innovation programme under GA No 101094300.

## Slide 2: Council and ESPPU
Council decided deadline for contributions to next ESPPU
  31rst March 2025
  Open Symposium June or July 2025 (tbc)
  Conclusion June 2026
Need to prepare several reports
However, will not be able to address all the work planned for 2026
  Have to see how to describe this in the report

## Slide 3: Comments
In the Roadmap we promised to the next ESPPU
  Evaluation report
    Including cost and power consumption scale estimate
  R&D plan
    This requires some scenarios and timelines
We will have some US process after the ESPPU
  Need to understand which documents are required
  Reference design?
  Initial study for demonstrator?
IMCC should prepare all reports together
  US to help with ESPPU
  Europe to help with US strategy
  Other partners to be also integrated

## Slide 4: Reports
Which reports
  Project evaluation report (promised)
  Report on R&D programme (promised)
  Others, e.g. technologies, … (might be good)
Need probably to prepare several types of reports (guessing from last ESPPU)
  One or more concise documents (maybe 10 pages?)
    Must be submitted at the deadline
  One or more long reports
    Must be useable at the deadline

## Slide 5: Report Writing and Editing
Need to agree on the report structure
  By end of June or August?
  Starting from the Interim Report
Need an editorial team
  Regular meetings
  Active role in writing
    And pushing the other authors
Should have some editing for language and design at the end
  Maybe we can find some native speakers that volunteer to do this
    Could try to see if we can make associate position available
  Can we find graphics support?
Note: Also have to write another parameter document

## Slide 6: Tentative Timeline
Long report(s)
April 2024: Parameter revision is starting
End of June 2024: Parameters updated (to EU October)
September 2024: Overleaf in place for authors to start
End of October 2024: Report ready for content editing
End of December 2024: Draft ready for collaboration and the IAC
End of January 2025: Report ready for copy editing (language)
End of February 2025: Start of signature process
End of March 2025: Report ready
Concise report(s)
End of September 2024: Overleaf in place
End of October 2024: Start of editing to integrate long report
End of December 2024: Draft ready for editing and IAC
February 2025: Start of copy (language) editing
End of March 2025: Report submission

## Slide 7: Cost and Parameters Task Force
Seems reasonable to concentrate things in a single task force
  Parameters
  Cost
  Power consumption
  Timeline
  R&D plans
Core team to keep cost confidential
Core team will work directly with small teams of experts for technologies and areas
  Obtain cost information
  Collect parameters and identify potential conflicts and trade-off needs
Present and discuss findings in a large group with all experts
  Except for the part that is confidential (cost)
  But in particular for R&D plan and timeline

## Slide 8: Examples of Important Parameter Decisions
Beam parameters along the chain
  Some sequences are not yet fully defined
Beam power on target
  We should aim for more than 2 MW
Cooling system chain
  E.g. trade-off points from 6D to final cooling
RCS staging
  Energy swing
Collider ring assumptions
  Magnetic field
How to deal with site specific designs
  Use LHC tunnel?

## Slide 9: Cost and Power
Need to build the cost
Plan is to have full PBS (Project Breakdown Structure)
Fill in what we know
Estimate the other parts
Identify the potential for savings
Need to estimate some envelope for R&D programme cost

## Slide 10: R&D Programme
Identify and agree on the scope of the R&D programme
  Demonstrator
  Magnets
  RF test stand
  …
This is a global effort
  Site for the demonstrator should not preempt the choice of host for the collider
Clarify synergies of the R&D and its facilities
  General technologies (e.g. magnets for fusion reactors)
  Specific technologies (e.g. detector technology for FCC, magnets for FCC-hh)
  Physics programmes (e.g. Mu2e, …)

## Slide 11: Project Timeline
Assumed that minimum timeline is defined by
  Muon cooling technology
  Magnet technology
  Detector design and technology
Need to verify that this is true
Need to check that the timelines for each of these technologies is established
Need to establish other timelines
  In particular also civil engineering
Tightly linked to R&D programme
The site also plays an important part in the timeline

## Slide 12: Conclusion
An exciting time lies ahead
Have to present progress and assess the muon collider potential
Need to put enough focus on R&D programme
Hope that our US colleagues will help with ESPPU
Have to prepare additional documents for the US soon after
  P5 recommended a Panel to follow the European Strategy
And integrate with the rest of the world