## Slide 1
Injectors Technical Stop (ITS1):
Different than in previous years.
At the same time as an intervention in the Swiss power grid to minimize impact on physics of the possible power interruptions.
PROPOSAL for TIMELINE: | 
12.06 at 07:30 | Beams stopped in the accelerator complex. RP cool-down period starts.
12.06 at 08:00 | Intervention in Swiss power network starts.
Between 12.06 at 08:30 and 13.06 at 08:30 | Interventions on a case-by-case basis and only if agreed by RP and EN-ACE.
13.06 at 07:30 | RP survey
Between 13.06 at 08:30 and 14.06 at 16:00 | Access to the machines for the rest of the interventions. Machines ready for restart on 14.06 at 16:00 (Is earlier possible? ~14:00?).
Between 14.06 at 17:30 and 15.06 at 17:30 | Spare time for intervention in Swiss power network. Restart of the machines as soon as intervention in Swiss power network is completed. Progressive restart of the physics program at the different facilities.
F. Pozzi, H. Vincke, M. Albert, S. Di Luca, S. Fleury, F. Pedrosa, R. Steerenberg, J. Nielsen, P. Skowronski, A. Rodriguez - ITS1 Preparation – 21.05.2023