## Slide 1: HEARTS P1 Review Meeting
25 September 2024
https://indico.cern.ch/event/1411185/
Pablo Lopez, WP1, CERN

## Slide 2: Outline
WP1 objectives & main achievements during P1
Overview of WP1 activities in P1
WP1 Deliverables and Milestones in P1
Deliverables and Milestones status in P1 at project level
Use of resources in P1

## Slide 3: WP1 objectives & main achievements during P1
WP1 is Project Management, with CERN as main beneficiary involved in WP1:
  Ensuring the efficient steering and management of the project throughout its duration with the aim of supervising and coordinating the scientific and technical progress of the different Work Packages.
  Taking care of the contractual and administrative implementation and keeping track of the use of resources.
  Supervising the preparation of periodic and final project reports to the European Commission as well as the arrangement of the project annual meetings.
  Taking over the coordination of beam access for users throughout the project and until the frameworks established in WP7-8 are defined.
Overall during RP1, good progress has been made towards the achievement of these objectives, with no delay nor issue to report. We can note the expansion of the Consortium with the inclusion of an additional beneficiary, COSYLAB, during P1, demonstrating interest to HEARTS project beyond our (small) consortium.

## Slide 4: Overview of WP1 activities in P1
Organisation of Kick-off meetings:
  HEARTS Kick-off Meeting, 20 January 2023, at CERN and online
  Advisory Panel Kick-off Meeting, 9 October 2023, online
Organisation of management meetings on a regular basis:
  4 Project Office Meetings (PO Meeting #1, PO Meeting #2, PO Meeting #3, PO Meeting #4)
  1 Governing Board Meeting (GB Meeting #1) and 1 on-line vote submitted to the GB (Sept. 2023, for inclusion of COSYLAB and application to the Hop-on Facility call)
Organisation of Annual Meetings:
  1st HEARTS Annual Meeting and Technical Review Meeting, 6 February 2024, at CERN and online

## Slide 5: Overview of WP1 activities in P1
Organisation of Work Package Leaders meetings:
  5 meetings organised during the period (WPL Meeting #1, WPL Meeting #2, WPL Meeting #3, WPL Meeting #4, WPL Meeting #5).
Coordination of two amendments to the Grant Agreement (GA) and one amendment to the Consortium Agreement (CA)
  GA AMD-101082402-2: Related to minor updates of Annex 1 (addition of CBM vault in WP8 and addition of advisory panel members) and minor changes in Annex 2 (Other goods works and services VS equipment)
  GA AMD-101082402-4 and CA amendment n°1: Related to COSYLAB joining the consortium  addition of beneficiary n°6 and WP9 (Tools and instruments for standardized dosimetry and user experimentation).

## Slide 6: WP1 Deliverables due in P1
Deliv. No. | Deliverable name | Submission date | Status
D1.1 | Assessment of high-energy heavy ion operation in CHARM during CERN proton physics periods | 2024-07-25 | Achieved
The achieved deliverables are available on HEARTS website page:
https://hearts-project.eu/project/deliverables/
The report investigates the feasibility of splitting the 2-3 weeks annual ion run for radiation effects testing purposes in the CERN PS East Area into two slots, as separated as possible in the calendar, with the objective of minimising the time a user has to wait between requesting the beam and being able to execute the experiment. For now, having the HEARTS@CERN ion period at the end of the operational run remains the only viable solution.

## Slide 7: WP1 Milestones due in P1
Milest. No. | Milestone name | Due date | Status
MS1 | Consortium agreement signed | 2023-01-31 | Achieved
MS2 | HEARTS Kick-off Meeting | 2023-02-28 | Achieved
MS3 | Forming of official bodies required by governance | 2023-03-31 | Achieved
MS4 | Appointment of the Advisory Panel | 2023-06-30 | Achieved
MS5 | 1st HEARTS annual meeting and interim technical review | 2023-12-31 | Achieved
The achieved milestones are available on HEARTS website page:
https://hearts-project.eu/project/milestones/

## Slide 8: WP1 Upcoming Deliverables and Milestones
Milest. No. | Milestone name | Due date | Status | Comments
MS6 | 2nd HEARTS annual meeting and interim technical review | 2025-02-28 | Pending | The meeting will take place at GSI in January – February 2025 (TBC).
MS7 | 3rd HEARTS annual meeting and interim technical review | 2026-03-31 | Pending | None
MS8 | HEARTS final meeting | 2026-12-31 | Pending | None
Note: No upcoming deliverables are expected for WP1.

## Slide 9: Deliverables and Milestones status in P1 at project level
Chart: HEARTS Deliverables timeline
| 44957 | 44985 | 45016 | 45046 | 45077 | 45107 | 45138 | 45169 | 45199 | 45230 | 45260 | 45291 | 45322 | 45351 | 45382 | 45412 | 45443 | 45473 | 45504 | 45535 | 45565 | 45596 | 45626 | 45657 | 45688 | 45716 | 45747 | 45777 | 45808 | 45838 | 45869 | 45900 | 45930 | 45961 | 45991 | 46022 | 46053 | 46081 | 46112 | 46142 | 46173 | 46203 | 46234 | 46265 | 46295 | 46326 | 46356 | 46387
Total nb of due DV since M1 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 5 | 5 | 5 | 5 | 5 | 5 | 6 | 6 | 6 | 6 | 6 | 6 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 31
Total nb of delivered DV since M1 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 4 | 5 | 5 | 5 | 5 | 5 | 5 | 6 | 6 | 6

## Slide 10: Deliverables and Milestones status in P1 at project level
Chart: HEARTS Milestones timeline
| 44957 | 44985 | 45016 | 45046 | 45077 | 45107 | 45138 | 45169 | 45199 | 45230 | 45260 | 45291 | 45322 | 45351 | 45382 | 45412 | 45443 | 45473 | 45504 | 45535 | 45565 | 45596 | 45626 | 45657 | 45688 | 45716 | 45747 | 45777 | 45808 | 45838 | 45869 | 45900 | 45930 | 45961 | 45991 | 46022 | 46053 | 46081 | 46112 | 46142 | 46173 | 46203 | 46234 | 46265 | 46295 | 46326 | 46356 | 46387
Total nb of due MS since M1 | 1 | 3 | 5 | 5 | 5 | 6 | 6 | 6 | 6 | 6 | 6 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 10 | 10 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 16 | 16 | 16 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 23
Total nb of delivered MS since M1 | 4 | 5 | 5 | 5 | 5 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7

## Slide 11: Use of EU resources from M1 to M18 per beneficiary (and affiliated entity)
The figure above shows that ADS and COSYLAB are under-using the resources: most of their activities are planned for a later stage in the project.
It is to be noted TAS and TESAT (as affiliated entity to ADS) didn’t submit their Financial Statement in due time.
However, at Consortium level, the use of resources is pretty much in line.
The high value of PM for CERN is mainly due to the fact that some activities under WP7 have been performed by lower-grade staff than initially foreseen, requiring more time than more experienced staff to run the activities.
Chart: 
| CERN | GSI | ADS | TESAT | TAS | UNIPD | COSYLAB | Total
% of budget used | 0.49188 | 0.18536 | 0.056407 | 0 | 0 | 0.31112 | 0.057806 | 0.26768
% of PM used | 0.77397 | 0.18333 | 0.06 | 0 | 0 | 0.36383 | 0.046524 | 0.29461
Flat spending profile | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 | 0.38

## Slide 12: Use of EU resources from M1 to M18 per WP
Some WPs are significantly deviating from the flat spending profile (38%):
WP7 is over-using resources  the facility preparation efforts are not linear, and concentrated in the beginning of the project
WPs 4, 5, 6, 8 are under-using resources  a certain number of tasks are supposed to start at a later stage of the project.
WP9 is under-using resources  accession of COSYLAB in the project in the last third of P1
Chart: 
| WP1 | WP2 | WP3 | WP4 | WP5 | WP6 | WP7 | WP8 | WP9 | Total
% of budget used | 0.47194 | 0.25201 | 0.40845 | 0.11854 | 0.10207 | 0.21947 | 0.68287 | 0.16409 | 0.057806 | 0.2677
% of PM used | 0.26256 | 0.15333 | 0.65303 | 0.15385 | 0.1539 | 0.13333 | 1.4577 | 0.21389 | 0.046524 | 0.2946
Flat spending profile | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 | 0.38 | 0.38

## Slide 13
Thank you for your attention.
Questions?