## Slide 1: HEARTS P1 Review Meeting
25 September 2024
https://indico.cern.ch/event/1411185/
Miha Vitorovič
HEARTS
COSYLAB

## Slide 2: Outline
The outlook of the WP in P1
Deliverables and Milestones in P1
Upcoming Deliverables & Milestones
Critical Risks & Mitigation Measures in P1
Identification of new risks

## Slide 3: The outlook of the WP in P1
Task 9.2: User interface tool for experimentation
  Obtain access to CERN infrastructure
  Test connection to IRRAD/CHARM T8 beamline
  Discuss user requirements and use-cases
  Check means of accessing various FESA properties programmatically
  Preparation of the development environment
  Tool selection – which libraries and frameworks to use
  Proof-of-concept to test the tool selection
Task 9.3: User experiment lifecycle interface
  Not started
  Starts in Sept. 2025

## Slide 4: UI Mock-ups – Overview screen

## Slide 5: UI Mock-ups – DUT screen

## Slide 6: UI Mock-ups – Spill screen

## Slide 7: UI Mock-ups – Optics screen

## Slide 8: UI Mock-ups – Operator screen

## Slide 9: Deliverables and Milestones in P1
WP9 had no deliverables in P1
There were no milestones affecting WP9 in P1

## Slide 10: Upcoming Deliverables & Milestones
Deliv. No. | Deliverable name | Due date | Status
D9.1 | User interface tool for beam experimentation | 2026-05-31 | Pending
D9.2 | User experiment lifecycle interface deployment | 2026-12-31 | Pending
Milest. No. | Milestone name | Due date | Status
MS14 | Achievement of TRL6-7 for electronics testing at the CHARM facility | 2026-05-31 | Pending
MS15 | Achievement of TRL6-7 for electronics testing at GSI | 2026-05-31 | Pending
MS19 | Achievement of TRL6-7 for the SIS18 GCR/SPE simulator | 2026-05-31 | Pending

## Slide 11: Critical Risks & Mitigation Measures in P1
No critical risks affecting WP9 have materialised in P1

## Slide 12: Identification of new risks
No new risks have been identified

## Slide 13: Conclusion
WP9 tasks are proceeding according to plan
We’re still on track for end-of-year prototype testing

## Slide 14
Thank you for your attention.
Questions?