## Slide 1
2024
March
April
July
May
June
Repair leak beam vacuum FPC Cav2
Cold RF test at 2K – *RF powering with IOT (Cav. 2 only)
Repair FCP cavity 1
Cold RF test at 2K- *RF powering with IOT. (Cav. 2 & 1)
Planning RFD-CM M7
N. Valverde, 14.06.2024
Preparation CM for cool down
Preparation CM for cool down
August
Sept.
Dec.
Nov.
Oct.
2023
Reception CM at CERN
Installation M7 Bunker
Inspection and meas. at warm
Welding jumper and safety extension group
Pressure test He 2K circuit
Preparation CM for cool down
Cold RF test- Low RF powering with amplifier (Cav.2)
Oct.
Nov.
Dec
Preparation for transport to SPS