## Slide 2: Technical Galleries Consolidation Program
TG-CONS Schedule

## Slide 3: Agenda
Program status
PLAN
Review of works by Group
Key-take aways

## Slide 4: Program Status - DASHBOARD
Gallery | Drinking water | Firefighting network | Compressed air | Heating pipes | Decabling | Doors, metal frames, roofs, ladders, false floors | Asbestos , led diagnostics | Drain check | Scans | 3D model Integration
835 north | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done
835 south | Done | Done | Done | Done | Done | Done | Done | Done | Done | Done
825 part 4.1 | Done | Done | Done | Done | Done | Partially | Done | Done | Done | Done
825 part 4.2 | Done | Done | Done | Ongoing | Done | Partially | Done | Done | Done | Done
825 part 3 | Ongoing | Ongoing | Ongoing | 2025 + 2026 | Done | Partially | Partially, 2025 + 2026 | TBC | Done | Done
825 part 2 | 2025 - 2027 | 2025 - 2027 | 2025 - 2027 | 2028 | Done | TBC | 2025 - 2028 | TBC | Done | 2024
825 part 1 | 2026 | 2026 | 2026 | 2029 | Done | TBC | 2026 + 2029 | TBC | Done | TBC
833 | 2026 | 2026 | 2026 | TBC | 2025 | TBC | 2026 | TBC | 2024 | 2025
826 | Done | N/A | Done | Ongoing | Done | TBC | Done | Done | Done | Done
827 | Done | N/A | Done | TBC | Done | TBC | Partially | Done | Done | Done
830 | Done | N/A | Done | TBC | Partially, 2024 | TBC | Partially | Done | Done | Partially
836 | Done | N/A | Done | Done | Done | TBC | Done | Done | Done | Done
180 | Done | Done | Done | TBC | Partially, 2024 | TBC | TBC | Done | Done | Partially
183 | Done | Done | Done | N/A | Partially, 2024 | TBC | TBC | Done | Done | Partially
829 | Done | Done | Done | TBC | TBC | TBC | Partially | Done | Done | TBC
831 + 832 | TBC | TBC | TBC | N/A | Done | TBC | TBC | Done | Done | TBC
837 | 2027 | 2027 | 2027 | Done | Done | Partially | TBC | TBC | Done | TBC
821 | 2027 | 2027 | 2027 | 2027 (TL4A) | Done | Partially | 2027 | TBC | Done | Ongoing
LS3 activities
Notes: Done/Partially (Green bold font) – final state of consolidation achieved
N/A – equipment is not present in the gallery
TBC – consolidation needed, no specific date/technical solution foreseen yet
YEAR – consolidation foreseen in the specified year
Partially (blue font) – some consolidation works were already done, more to come

## Slide 5: Program Status
Scanning, 3D models and integration of 5 km of galleries
276 tons of old piping and material removed
4.7 km of old piping replaced by 3.5 km of new piping
343 km of cables removed, 422 m3 of waste
2200 welds and 215 non-destructive tests

## Slide 6: PLAN TOOL
LS3
RUN3

## Slide 7: PLAN TOOL
Courtesy A. Borglund

## Slide 8: Foreseen collaborations with other Groups
Chart: 
| Civil Engineering | Cooling and Ventilation | Electricity | Cryogenics systems | Integration | Project management and other
 | 37710488 | 23425347 | 13120000 | 6840680 | 4380000 | 4346000
SCE-SAM
Civil engineering
Heating network
Drain systems
Normal/ emergency lighting
EN-CV
Water circuits: drinking, raw, firefighting, demineralised, chilled
Compressed air
Gas pipes (incl. He lines)
EN-EL
Cables: HV, LV, optical fibres, controls
Cable trays
Power supplies
Forecast expenditures by system/service

## Slide 9: Heating pipes – accomplished & ongoing
Heating pipes
2022
2023
2023
835
825
2023
836
2024
2024
826
Status:
DONE/
ONGOING

## Slide 10: Heating pipes – future works
Heating pipes
Status:
PLANNED
2025
825
2025/26
2027
2028
821 (TL4A)
825
2029

## Slide 11: CA, EP, EInc – accomplished & ongoing
Drinking Water + Compressed Air
Firefighting Water connections
Status:
DONE/
ONGOING
2022
2023
2023
2023
2022
2023
825
835
830
829
836
827
2024
2023
2023
825
826
183
Notes: Drinking water: 825, 829, 836, 835, 827, 830
Thanks to the firefighting network optimization, only 3 firefighting water connections are left in Meyrin West Area.

## Slide 12: Future possibilities for EN-CV works
CV Networks (EP, AC, EI)
Buried pipes
Status:
PLANNED/
ONGOING STUDY
2025-27
2026
2026
2025
2025
825
833
Water tower
837
821
821
821
821
821
821
821
821
821
2027-28
833
833

## Slide 13: Decabling – accomplished
2022
General decabling
Status:
DONE
2023
YETS 22/23
2023
2023
2022
825
833
818
837
821
835
180
819
847
822
183
832
831
Telecom cable removed
YETS 23/24
847
2023/24
825
835
826
827
836

## Slide 14: Decabling – future works
General decabling
Status:
PLANNED
2024
180
183
2025
833

## Slide 15: Take Aways
TG-CONS is a long-term Program running until LS5, planned in 4 phases
Three main contributing groups: SCE-SAM, EN-CV and EN-EL
Re-engineering / Optimisation/ Priorization / Iso-functional replacement to some extent
LS3 activities will take place on the Meyrin site – central part (ISR up to gallery 833)
EN-EL has anticipated the cabling/decabling activities of phase 2 and will be free during LS3.
During LS3, all TG-CONS activities can be carried out in the shadow of higher priority activities and are not overly invasive
TG-CONS is a backup option for certain groups in the event of unforeseen circumstances/work stopped or blocked on other facilities

## Slide 17: Schedule planning and monitoring
Detailed schedule
Link: EDMS 2705555
Gantt chart viewer
Link: EN-ACE scheduling tools online