## Slide 1: Status of MQXFA magnets
Giorgio Ambrosio - FNAL
with contributions from the whole MQXFA team

## Slide 2: Acknowledgement
US HL-LHC Accelerator Upgrade Project (AUP)
  BNL: K. Amm, M. Anerella, A. Ben Yahia, M. Bornstein, H. Hocker, P. Joshi, F. Kurian, J. Muratore, J. Schmalzle, P. Wanderer
  FNAL: G. Ambrosio, G. Apollinari, M. Baldini, J. Blowers, R. Bossert, R. Carcagno, G. Chlachidze, J. DiMarco, S. Feher, S. Krave, V. Lombardo, C. Narug, A. Nobrega, V. Marinozzi, C. Orozco, T. Page, J. Seyl, S. Stoynev, T. Strauss, M. Turenne, D. Turrioni, A. Vouris, M. Yu
  LBNL: D. Cheng, J. Doyle, P. Ferracin, L. Garcia Fajardo, E. Lee, M. Marchevsky, M. Naus, I. Pong, S. Prestemon, K. Ray, G. Sabbi, G. Vallone, X. Wang
  NHMFL: L. Cooley, J. Levitan, J. Lu, R. Walsh
CERN: HL-LHC Project
  G. Arnau Izquierdo, A. Ballarino, M. Bajko, C. Barth, N. Bourcey, B. Bulat, M. Cruovizier, A. Devred, H. Felice, S. Ferradas Troitino, L. Fiscarelli, J. Fleiter, M. Guinchard, O. Housiaux, S. Izquierdo Bermudez, N. Lusa, F. Mangiarotti, A. Milanese, A. Moros, P. Moyret, C. Petrone, J.C. Perez, H. Prin, R. Principe, E. Ravaioli, T. Sahner, S. Sgobba, P. Tavares Coutinho Borges De Sousa, E. Todesco, J. Ferradas Troitino, R. Van Weelderen, G. Willering

## Slide 3: MQXFA (AUP 302.2) Deliverables
21 Magnets
  20 magnets for 10 Q1/Q3 cryo-assemblies
    2 magnets in each cryo-assembly
  1 magnet to CERN for acceptance of CA01
  Assuming 6 re-assemblies
    = post test re-work
Cryo-assembly
(LQXFA)
Magnet
(MQXFA)
Cold Mass
(LMQXFA)

## Slide 4: MQXFA Status Summary
Main task is magnet assembly.
Supported by 4 reviews / meetings per magnet
Control Account | Component status wrt Baseline* | Comments
Strand procurement & QC (FNAL, FSU) | 96% complete | Procuring spare cond.
Cable fabrication & insulation (LBNL) | 100% complete | 
Coil part procurement (FNAL) | ~100% complete | Completing QC
Coil fabrication (FNAL) | 98% complete | Last coil fabrication
Coil fabrication (BNL) | 100% complete | 
Magnet part procurement (LBNL) | 100% complete | 
Magnet assembly (LBNL) | 58% complete | 
*Will change if additional cables/coils are added to Baseline
MQXFA at BNL after shipment from LBNL
More details in “MQXFA Fabrication Status and schedule” in WP3 MQXF session Wed PM

## Slide 5: Magnet Yield
11 magnets met requirements during vertical test
  3 magnets (MQXFA07/08/13) needed a coil change to meet requirements
  1 magnet (MQXFA17) is waiting for a coil change
  MQXFA05 passed an Endurance Test (7 thermal cycles, 52 quenches, …)
  MQXFA11 demonstrated resilience (after highway crash)
Vertical test is done at BNL by 302.4.01, post-test analysis is done by 302.2.01
MQXFA magnet being moved to vertical test station at BNL
5
More details in “Production testing summary of the MQXFA magnets” in WP3 session Tue PM

## Slide 6: “Endurance” & “Resilience” Demonstrations
All magnets that met requirements demonstrated very good memory and temperature margin:
I_nom @ 4.5 K
+ 2 additional thermal cycles in CA02

## Slide 7: MQXFAs Integral Harmonics at Nominal Curr.
b6 correction introduced in one coil on MQXFA04 and all subsequent coils:
125 um shift toward midplane
Magnetic shims used to correct low order harmonics
More details in “Production testing summary of the MQXFA magnets” in WP3 session Tue PM
Before b6 correction in cross-section

## Slide 8: Lessons Learned from MQXFA07/08 test & analysis
  FE analysis of as-built magnets pointed to “critical area”
  Metallographic analysis by CERN team found the “Smoking gun” (broken Nb3Sn filaments) in this area
  Excellent collaboration!
Lessons learned:
  Asymmetry during assembly may be looked-in by prestress
  2D asymmetry may cause poor preload in the ends
    Seen in MQXFA07 and MQXFA08 (presented in Vancouver)
Preventive action:
  Larger gaps and revised assembly procedure
14th HL-LHC Collaboration Meeting, Oct 7 – 10, 2024
Presented at the
13th HL-LHC Collab. Mtg.

## Slide 9: Lessons Learned from MQXFA13/17 test & analysis
If midplanes in coil ends are “too small” & there is low prestress  risk of excessive strain
Relative differences are more relevant than absolute numbers because of mesh size and de-bonding assumptions
MQXFA13 coil arc-length error
Courtesy of A. Bartkowska
Coil straight section
Coil lead end

## Slide 10: Preventive Actions
Main actions:
  Added Tapered Load Shims in magnet Lead End
    During last step of azimuthal preload
    Added coil dimension measurements in the critical area and FE analysis based on measured coil size
  Set target for minimum loading key size based on coil dimensions  higher pre-stress controlled by dimensions
    Comparison with best magnets
  Increased the maximum allowable stress during preload from 110 to 135 MPa
    Based on feedback from CERN MQXFS program

## Slide 11: Coil Status & Parts
Coils available (fabricated and passed QC) | 38
Coils in production | 1
Coils to be recovered from on-hold – future issues | 1
Coils needed for 10 magnets | - 40
Expected coils balance | 0
Inventory:
  Available: strands for 1 MQXFB cable
  Incoming strands: for 3 MQXFA cables by end of October + for 2 cables by January 2026 (maybe earlier).
  Available parts: 3 full sets (poles + ends + traces)
  Incoming parts: 2 traces
Two risks for additional coils in Risk Register
After 11 magnets met requirements:

## Slide 12: Plans and Schedule
Plans for next magnets:
  MQXFA18 (1st with TLS) is at BNL under test
  MQXFA12b retrofitted with TLS (50 um) is at BNL
  MQXFA16 retrofitted with TLS (50 um) almost complete
  Re-assembly of MQXFA17b has started
Working Schedule
  August update:
All magnets will be vertically tested at BNL
  Only one thermal cycle during vertical test

## Slide 13: MQXFA Summary
11 magnets met requirements, 10 more to go
  3 magnets that did not meet requirements were repaired by changing one coil and met requirement.
  1 magnet is to be repaired
  All magnets will be vertically tested
Major procurements are complete
Last coil is in fabrication at Fermilab
Strands and parts in inventory for up ~5 coils (6 max)
Magnet assembly is at peak production rate
Lessons learned have been implemented in revised design features and assembly specs.
We plan completing the assembly of all magnets around next HL-LHC Collaboration Meeting

## Slide 14: Back up Slides

## Slide 15: MQXFA/B Design
Parameter | Unit | MQXFA/B
Coil aperture | mm | 150
Magnetic length | m | 4.2/7.15
N. of layers |  | 2
N. of turns Inner-Outer layer |  | 22-28
Operation temperature | K | 1.9
Nominal gradient | T/m | 132.2
Nominal current | kA | 16.23
Peak field at nom. current | T | 11.3
Stored energy at nom. curr. | MJ/m | 1.15
Diff. inductance | mH/m | 8.26
Strand diameter | mm | 0.85
Strand number |  | 40
Cable width | mm | 18.15
Cable mid thickness | mm | 1.525
Keystone angle |  | 0.4
P. Ferracin et al., “Development of MQXF, the Nb3Sn Low-β Quadrupole for the HiLumi LHC ” IEEE Trans App. Supercond. Vol. 26, no. 4, 4000207
Nb3Sn Conductor
RRP 108/127
G. Ambrosio et al., “First Test Results of the 150 mm Aperture IR Quadrupole Models for the High Luminosity LHC” NAPAC16, FERMILAB-CONF-16-440-TD

## Slide 16: Low- quadrupole magnets from LHC to HL-LHC
Cold mass OD from 490/420 to 630 mm
More than double the aperture: from 70 to 150 mm
~4 times the e.m. forces in straight section
~6 times the e.m. forces in the ends
MQXB
MQXA
MQXF
Same scale for all 3 plots
State of the art quadrupoles at the time of LHC construction