## Slide 1: HL-LHC Interaction Region Magnets
E. Todesco, D. Duarte Ramos, S. Izquierdo Bermudez, A. Milanese,
G. Ambrosio, S. Feher, T. Nakamoto, Q. Xu, F. Toral, S. Farinon, M. Statera
A. Foussat, J.-C. Perez,
G. Vandoni, I. del Rosario Crespo Garrido, S. Fleury
October 10th 2024, Genova

## Slide 2: Structure update
Thanks to Rosario Principe !
Welcome to Lucie Baudin and to
Ruth Diaz Vez

## Slide 3: MQXFA (see talks by G. Ambrosio, S. Feher)
T0: aperture and cable selection
MQXFAP1: ≥11.6 T, but electrical short
MQXFAP2: ~10 T, broken structure
MQXFA03
MQXFA05
MQXFA06
T0+4
DOE approval
12 magnet tested, 9 more new magnets to test (9,12,16, 18-23)
MQXFA04
MQXFA11
MQXFA08b
MQXFA14
MQXFA13: ~10.7 T
11.6 T: 7 TeV (nominal)
MQXFA15
10 conform magnets
First cold mass limited at 6.8 TeV after test at CERN
30% of NC test, but repair is succesful (coil replacement)
MQXFA07b
2013
2014
2015
2016
2017
2018
2019
2020
2021
2022
2023
2024
2025
2026
2027
MQXFA07: ~10.7 T
MQXFA08: ~9.5 T
CM01
MQXFA10
Project
Program
MQXFA17
MQXFA13b
CM02 (ongoing)
String
String

## Slide 4: MQXFA (see talks by G. Ambrosio, S. Feher)
Assembly of cold masses in FNAL (S. Feher,, et al.)

## Slide 5: MQXFB (see talk by S. Izquierdo Bermudez)
MQXFBP1: ~10.5 T
MQXFBP2: ~11.2 T
7 more magnets to test
T0: aperture and cable selection
MQXFBP3
MQXFB02*
MQXFB03
Green: conform ≥ 11.6 T
Red: non conform
Grey: to come
Light grey: spares
MQXFB04
MQXFB05
(ongoing)
2013
2014
2015
2016
2017
2018
2019
2020
2021
2022
2023
2024
2025
2026
2027
* MQXFB02 had a non conform HV test, will be disassembled
MQXFB06
MQXFB07
MQXFB08
MQXFB09
MQXFB10
MQXFB11
MQXFB12
spares
String

## Slide 6: MQXFB (see talk by S. Izquierdo Bermudez)
MQXFB05 reached requirements in 1st thermal cycle – 3rd new generation magnet
We gain performance, and a bit more virgin training – good bargain
All magnets reach nominal also at 4.5 K (90% of sh. sample): important for HFM
Quench performance of MQXFB04 and 05
(Test eng. F. Mangiarotti, G Willering,, WPE: S. Izquierdo Bermudez, et al.)

## Slide 7: MCBXF (see talk by F. Toral)
MCBXFB09
MCBXFB05
9 magnets to test
T0: aperture and cable selection
MCBXFA1
Green is conform
Red is non conform
2013
2014
2015
2016
2017
2018
2019
2020
2021
2022
2023
2024
2025
2026
2027
Internalization according to plans – MCBXFB06 completed
MCBXFB04
MCBXFB03
MCBXFB02
MCBXFB01
MCBXFAP1
MCBXFBP1c
MCBXFBP1d
MCBXFBP1b
MCBXFBP1
MCBXFBP2
MCBXFBP2b
MCBXFB06
MCBXFB07
MCBXFA2
MCBXFB08
MCBXFA3
MCBXFA4
MCBXFB10
spares
MCBXFA5
String
MCBXFBP2d

## Slide 8: D1 (see talk by T. Nakamoto)
MBXFS1: ~5.6 T
3.5 magnets to test (in KEK)
T0: aperture and cable selection
MBXFS1b: ≥6.1 T
MBXFS2: ≥6.1 T
MBXFS3: ≥6.1 T
Contract
Hitachi
MBXF5 ≥6.1 T
(1st cycle)
Green is conform > 6.1 T
Red is non conform
5.6 T: 7 TeV (nominal)
6.1 T: 7.5 TeV (ultimate)
2013
2014
2015
2016
2017
2018
2019
2020
2021
2022
2023
2024
2025
2026
2027
MBXF2 ≥6.1 T
MBXF5 (2st cycle)
MBXF6
MBXF4
MBXF3
spares
2.5 magnets conform
MBXF5 2nd thermal cycle is pending
Large delay between magnet vertical test and delivery, today the last magnet for installation is MBXF5, ready for installation in mid 2027
String
MBXFP1 ≥6.1 T
(CERN)
MBXFP1: ≥5.9 T
MBXF1 ≥6.1 T

## Slide 9: D2 (see talk by S. Farinon)
6 more magnets to test
MBRDS1: ≥4.8 T, but in one aperture
MBXFS1c: ≥4.8 T,
but retraining
MBRDP1: ≥4.8 T
T0: collaboration
agreement
Contract to ASG
Green is conform
Red is non conform
4.5 T: 7 TeV (nominal)
4.8 T: 7.5 TeV (ultimate)
2013
2014
2015
2016
2017
2018
2019
2020
2021
2022
2023
2024
2025
2026
2027
MBRD2
MBRD3
MBRD1
MBRD4
MBRD5
MBRD6
spares
Coil manufacturing finished
Issues with collaring are being solved
MBRD1 back to CERN in October
MBRD2 at CERN, cold mass assembly ongoing
T0: aperture and cable selection

## Slide 10: D2 corrector (see talk by Q. Xu)
T0: aperture and cable selection
7 more magnets to test
MCBRD01
T0: collaboration
agreement
Contract
to BAMA
Green is conform
Red is non conform
2.8 T: 7 TeV (nominal)
3.1 T: 7.5 TeV (ultimate)
2013
2014
2015
2016
2017
2018
2019
2020
2021
2022
2023
2024
2025
2026
2027
MCBRD11
MCBRD5
MCBRD6
At CERN, the second magnet with Chinese components MCBRD12 still to be completed – test will be in early 2025
MCBRD05 and MCBRD06 completed, but test is lagging
MCBRDP2
MCBRDP1
MCBRDP3
MCBRDP4
MCBRD02
MCBRD03
MCBRD04
MCBRD12
MCBRD7
MCBRD8
MCBRD9
MCBRD10

## Slide 11: Conclusions
Production is advancing well, but far from being finished!
Integration of magnets from three continents is being proved
New baseline for MQXFB coils shows performance reproducibility
US MQXFA production shows ability to recover performance limitations via coil replacement
First magnet installed in the string

## Slide 12: THANKS !