## Slide 1: HL-LHC Crab Cavities: DQW & RFD HOM couplers fabrication challenges
Simon Barrière, CERN
on behalf of the HL-WP4 team
14th HL-LHC Collaboration Meeting – Genoa, Italy – 09th October 2024

## Slide 2: Outline
Scope of Production
Manufacturing Status
Latest Challenges & Lessons Learned

## Slide 3: Production Scope: DQW series
HOM Coupler + Feedthrough
x 36 units*
RF Field Antenna
x 12 units*
*initial scope, quantities for 8 cavities including spares
HF-HOM Coupler
x 12 units*
Fundamental Power Coupler
x 14 units*
  HOM Couplers, HOM Feedthroughs, HF-HOM Couplers and Field Antennas for LHC-series DQW Crab Cavities are being produced at CERN Main Workshop

## Slide 4: Production Scope: RFD series
June 2024: Request from US-AUP to produce at CERN:
  V-HOM Couplers, H-HOM Feedthroughs and Field Antennas for LHC RFD Crab Cavities
H-HOM Coupler still under US-AUP scope (see presentation by N. Huque)
V-HOM Coupler
x 12 units*
RF Field Antenna
x 12 units*
H-HOM Feedthrough
x 12 units*
Fundamental Power Coupler
x 14 units
*in several batches

## Slide 5: Why are these Objects a Manufacturing Challenge?
  (S)RF performance highly dependent on geometry and surface quality
    Final tolerances in few tenths of millimetres after many assembly (welding!) steps
    Machined and welded RF surfaces = specific parameters
  Specific (and expensive!) materials
    Extra-pure niobium, OFE copper, titanium grade 23 (TA6V ELI), stainless steel 316LN
  Multi-Technology components with pressure joints
    ~13 technologies involved and intertwined
    Multiple activities and actors in parallel in different groups
    Advanced follow-up to fulfil HL-LHC quality standards (PED-related normative, MTF steps, traceability)

## Slide 6
  Manufacturing Status
  HOM Couplers & Antennas

## Slide 7: DQW – HOMC and Antennas
Pieces | Qty requested | Qty produced at CERN
HOM Coupler | 36 | 15 done 1 not conform 21 ongoing
HOM Feedthrough | 36 + 12* | 20 done 16 ongoing 12*
HF-HOM Coupler | 12 + 4* | 12 done 4*
Field Antenna | 12 + 4* | 12 done 4*
  * : additional quantities to be produced following last PSM in Sept 2024 (spares)
DQW
HOM Coupler
DQW
HOM FT
DQW
HF-HOM Coupler
DQW
Field Antenna

## Slide 8: DQW – HOMC and Antennas
  Nb Hook Machining
  Welded Hooks Series
  Metrologies (3D Scans)
  HF-HOM Final Weld
  HF-HOM Final Weld
  Field Antenna Assembly

## Slide 9: RFD – HOMC and Antennas (1st set)
Pieces | Qty requested | Qty produced at CERN
H-HOM Coupler | 2** | 2** shipped
H-HOM Feedthrough | 2** + 4 | 2** + 4 shipped
V-HOM Coupler | 2** + 4 | 2** + 4 shipped
Field Antenna | 2** + 4 | 2** + 4 shipped
  ** : prototypes built at CERN for RFD-SPS cryomodule
RFD
V-HOM Coupler
RFD
Field Antenna
RFD
H-HOM Coupler
RFD
H-HOM FT

## Slide 10
RFD – HOMC and Antennas (1st set)
  H-HOM Feedthrough brazed
  V-HOM Final Assembly
  Field Antenna
  Final Assembly
  RF Clamp EB weld
  Field Antenna
  Final Weld
  V-HOM Metrology
  Field Antenna Metrology

## Slide 11: RFD – HOMC and Antennas (2nd set)
Pieces | Qty requested | Qty produced at CERN
H-HOM Feedthrough | 8 | 8 ongoing
V-HOM Coupler | 8 | 8 ongoing
Field Antenna | 8 | 8 ongoing
RFD
V-HOM Coupler
RFD
Field Antenna
RFD
H-HOM FT
  All raw materials received including ceramics, brazing and machining ongoing

## Slide 12
  Manufacturing Status
  FPC

## Slide 13: DQW & RFD – FPC Air Side
Pieces | Qty requested | Qty produced at CERN
Water Antenna | 28 | 28 done
Water Flanges In/Out | 30 | 30 done
Transmission Line (wevaguide, body) | 30 | 30 done

## Slide 14: DQW & RFD – FPC Air Side
  Water Antennas
  Central Body and Cooling Collars
  Aluminum Waveguides

## Slide 15: DQW & RFD – FPC Antenna
Pieces | Qty requested | Qty produced at CERN
DQW Antenna | 14 | 6 done 8 ongoing
DQW Double Tube | 14 | 8 done 6 ongoing
RFD Antenna | 14 | 8 done 6 ongoing
RFD Double Tube | 14 | 8 done 6 ongoing
Vacuum Body | 28 | 28 done
RFD
FPC Antenna
RFD / DQW
Vacuum Body
DQW
FPC Antenna
DQW
Double Tube
RFD
Double Tube
  All missing assemblies are at very latest steps of production

## Slide 16: DQW & RFD – FPC Antenna
  Assembled FPC
  FPC Final Metrology
  3D Laser Scans
  Final EB Weld
  Hook Machining

## Slide 17
  Manufacturing Status
  Coaxial Lines

## Slide 18: DQW & RFD – Coaxial RF Internal Lines
Pieces | Qty requested | Qty produced at CERN
LHCACFRL0195 x2 for 1 CM RFD x1 for 1 CM DQW | 36 | 36 ongoing
LHCACFRL0198 x1 for 1 CM RFD x2 for 1 CM DQW | 36 | 36 ongoing
LHCACFRL0261 x2 for 1 CM DQW | 24 | 24 ongoing
DQW / RFD
LHCACFRL0195
DQW / RFD
LHCACFRL0261
DQW / RFD
LHCACFRL0198
  All pieces needed for 2x DQW cryomodules and 2x RFD cryomodules will be ready in Dec 2024

## Slide 19: DQW & RFD – Coaxial RF Internal Lines
  Assembled Lines & Subcomponents for RFD Prototypes

## Slide 20: Latest Challenges

## Slide 21: Stains
We have been chasing stains (and their origin) the past few months
We have upgraded our procedures with more visual checks, systematic replacement of gloves after touching other objects, extended care and protections for transport
Fingerprints (!)
Old gloves
Chemistry
Drying
Long storage
…
We are questioning ourselves if this is really a problem for RF
Most of the traces appear after the cleanroom processing

## Slide 22: Scratches
Mostly caused by insufficient care during handling & transport between all fabrication steps
New standardized process using silk paper + foam reduces the risk
Visual control between all critical steps
Repair is possible:
When identified after final steps, polishing process defined for removal (polishing stone grit 8000 with isopropyl alcohol)

## Slide 23: Devil is in the Details
x70
x70
  Stainless steel and titanium knives are key element to ensure light tightness in operation and for validation tests at 2 K.
  Cold leaks (at 2 K with superfluid helium) are impossible
  to locate at warm root cause very difficult to assess
  All knives are inspected,
  defects or bumps systematically removed
  DQW HOM Flange
  Bump (depth 0,05 – 0,1 mm)
Repair

## Slide 24: Knives repair
Abrasive blocks with different grits
Polishing stone grit 8000 with isopropyl alcohol

## Slide 25: Conclusions & Lessons Learned
  Level of attention and care should remain the same in prototyping phase and series production, until the last object is built. While many eyes are put on prototypes (= low quantity of items), keeping the same level of attention in series production has proven to be challenging
  Fabrication of RF couplers & antennas in CERN scope is currently on track
  Manufacturing and delivery of high-quality (S)RF couplers requires extended care on all handling and transport operations
  Understand criteria linked to chemistry processes on multi-material objects is of paramount importance: is beautiful the best?

## Slide 26: Many thanks to all the colleagues involved in the production of such beautiful objects!
Special thanks to the EN-MME Manufacturing Team,
and Sébastien, Francesco, Nuria & Eric (SY-RF)

## Slide 28: Spare slides

## Slide 29: Surface treatment of assembled heterogenous materials is a challenge
Courtesy Leonel Ferreira (CERN)
Pre-processing
Brazing
Post -processing
Degreasing / Chemical polishing /
Passivation
Degreasing
Degreasing /
Nickel plating
Copper loses its passivation
Specific solvent degreasing with pickling effect
(copper remains non-passivated)
Reoxidation
Rinsing with water or even ethanol without a fast-drying step
Imperfections at the brazing interfaces leading to unspotted chemicals/water retention
Use pre-processing chemicals is challenging and can make things worse
Mainly effective on copper-based oxidations
Treatment limited to relatively small components size
Case by case choice of surface treatment and sequence
Experienced personnel
Dry processing (PVD) to be considered

## Slide 30: Quality & Documentation
TRAVELLER HOM COUPLERS & FEEDTHROUGHS |  |  |  |  |  | N°WB - __
 | CDD Number / Numéro CDD | Bld./ Lieu | Collaborator / Responsable | Signature | Date | Comments / Observations
Ceamic order number |  | 112 |  |  | __/__/20__ | 
Visual inspection of ceramic discs |  | 112 |  |  | __/__/20__ | 
Degreasing |  | 107 |  |  | __/__/20__ | 
Metalization / Mo/Mn 20-45 µm + Ni 5-10 µm |  |  |  |  | __/__/20__ | 
Visual inspection of ceramic discs |  | 112 |  |  | __/__/20__ | 
Metrology |  | AP |  |  | __/__/20__ | 
Machining Titanium flange (rough) |  | AP |  |  | __/__/20__ | 
Machining Copper part (finishing) |  | AP |  |  | __/__/20__ | 
Thermal stress relief treatment |  | 107 |  |  | __/__/20__ | 
Machining final Titanium flange (finishing) |  | AP |  |  | __/__/20__ | 
Etching flange + tube before brazing |  | 107 |  |  | __/__/20__ | 
Visual control before brazing |  | 112 |  |  | __/__/20__ | 
Vacuum brazing |  | 112 |  |  | __/__/20__ | 
Visual control after brazing |  | 112 |  |  | __/__/20__ | 
Ceramic n° engraving |  | 112 |  |  | __/__/20__ | 
Leak test |  | 864 |  |  | __/__/20__ | 
Sandblasting of ceramic |  | 864 |  |  | __/__/20__ | 
Metrology of antenna’s height |  | AP |  |  | __/__/20__ | 
EB Welding of back pieces |  | AP |  |  | __/__/20__ | 
Visual control |  |  |  |  |  | 
Metrology |  | 100 |  |  | __/__/20__ | 
Inspection finale SY-RF |  | 864 |  |  | __/__/20__ | 
Leak test / Contrôle d'étanchéité |  | 864 |  |  | __/__/20__ | 

## Slide 31: Quality & Documentation
Strong commitment from WP4 teams to fulfil HL-LHC quality standards
  MTF, EDMS, Non-Conformities Reports… but also technical documentation
90+ assets to be followed-up, from materials traceability to all inspections and controls up to last steps. Challenging but of paramount importance!