## Slide 1: WP4-Series cryomodules design 14th HL-LHC Collaboration Meeting, CERN – 7-10 October 2024
Teddy Capelli on behalf of the WP4 collaboration

## Slide 2: Status of drawing packages RFD & DQW – Series
Status of drawing folders for cryomodule internal components :
Extracted from EDMS Docs 2730814 & 2801330
Status drawing folders for cryomodule external components :
* Improvement of the original design
Only needed for LHC
Only needed at CERN

## Slide 3: Summary of drawing status
Cryogenic lines :
  All drawing are released
Beam vacuum equipment:
  All drawing are released
Outer Vacuum Chamber:
  All drawing are released
Thermal screen, thermal intercept
& Multi Layer Insulation :
  All drawing are released
Magnetic shield :
  All drawing are released
Cavity support system:
  All drawing are released
Internal cryogenic support :
  All drawing released
Tuner:
  Improvement for external actuation
  Internal component released
  See presentation K.Artoos
Cryomodule assembly:
  Iterative updates
  Design freeze step by step
  Step 1-6 done
  Step 7-12 on-going
Cryogenic instrumentations:
  Design done and doc. Under review

## Slide 4: Assembly sequence updates
11500 components to be assembled (~950 2D drawings, 3500 3D part models not including tooling)
RFD Sequence : EDMS 3086385
BOM for assembly sequence : EDMS 3020997
DQW Sequence : EDMS 2873730
BOM for assembly steps : EDMS 3020997
Courtesy L.Giordanino
Courtesy J.Dequaire

## Slide 5: Cryogenic biphase support bolted design
Manufacturing advantages:
  Bolted design (no welds required)
  Reduction of cost of manufacturing
  Modular design
Assembly advantages:
  Easier installation on cavities
  Free space for biphase welding
Total maximum deformation : 1.9mm (DQW) / 2.7mm (RFD)
Directional deformation : 1.6mm (DQW) / 2.4mm (RFD) – target 3mm max
(for pressure testing load case)
RFD Cryogenic support strength assessment
EDMS 3063725
Courtesy L.Giordanino
DQW Cryogenic support strength assessment
EDMS 3075772
Courtesy L.Giordanino
Bolt stress
Minimum safety factor for both DQW and RFD design : 1.3 for M5 and 1.9 for M6 fasteners
Stress and Buckling analysis
Maximum stress : stress below limit defined by EN13445-3 for each operating condition
Load multiplier of buckling : >40 for both design
Fastener A80 – not mandatory everywhere but safer to standardize in order to avoid mistake during assembly
Design released ✓

## Slide 6: Cryogenic safety extension for series cryomodules
LHC version
Detailed study of the cryogenic extension for LHC - with new input from CRG expert
  Change of design to protect burst from thermal cycles
  Change the layout of safety valve (under review with TE-CRG)
Definition and integration for the LHC 0 and 180° orientation
SPS version
Design under review
Only needed for LHC

## Slide 7: Safety extension thermal sim.
Thermal evaluation of Cryo. Safety extension (SPS)
See EDMS 2323043
Courtesy E.Cano Pleite
Cryogenic safety extension optimization (LHC) :
DQW : EDMS 3024965
RFD : EDMS 3024966
Courtesy E.Cano Pleite
RFD / SPS design
LHC design

## Slide 8: Cryoline stress assessment and pressure test tooling
Design of a test bench for pressure test representing cryomodule config.
Design of several other tooling for lower lines and 4-20K lines
Analysis performed according to the Annex B of the EN 13445-3 “Design by analysis - Method based on Direct Route”, the testing condition for the Bi-phase line has been separately evaluated (see the full report)
  All the criteria from standard have been satisfied and the results are fully acceptable
RFD
DQW
DQW Cryogenic lines stress assessment: EDMS 3000051
Courtesy J.SWIESZEK
RFD Cryogenic lines stress assessment: EDMS 2477175
Courtesy T.GUILLEN HERNANDEZ – L. DASSA
document update on-going (design is really close to SPS’s)
Design released ✓

## Slide 9: Cavity support DQW & RFD for LHC
Material update for the 3 adjustment sets
Blade connexion head change
Improvement of assembly on CM
Cavity support simulation results are acceptable
  Both report done by E. Cano-Pleite
  to be uploaded on EDMS
  Anticipation of displacement for alignment of cavities
  No significant change in stress WRT previous design
Previous design
(SPS)
New design
(LHC)
Design released ✓

## Slide 10: Cryogenic instrumentation
RFD cryogenic instrumentation : https://edms.cern.ch/project/CERN-0000181755
  https://edms.cern.ch/document/3161276
DQW cryogenic instrumentation : https://edms.cern.ch/project/CERN-0000181671
  https://edms.cern.ch/document/3167444
Design released ✓
List under review
Waiting for CRG validation

## Slide 11
Other design activities
Component | Material spec
Jumper support (LHCACFQC0310) | Cryoline spec EDMS 2093032
4-20k cooling line support LHCACFQC0519 | Cryoline spec EDMS 2093032
Thermal screen ancillaries for thermal screen LHCACFTS0460 + LHCACFTS0425 | Thermal screen spec EDMS 2101922+ only for plate: spec EDMS 790774 (1002)
Cavity support system LHCACFAH0095 & 0101 | Vac vessel spec EDMS 2101924 + Cryoline spec EDMS 2093032 Fasteners in Stainless steel whenever possible
Jumper for LHC LHCACFQC0621 | No UK or Triumf production / CERN spec ONLY for internal use: EDMS 3055177
CWT Supports (LHCACFAH0055) | Vac vessel spec EDMS 2101924
Modification of material requirements
  Lower grades requirement on some components
  Change of material for a better coherence between drawing packages
Follow up NCRs & change request coming from the collaboration
Design of tooling for repairs & assembly
Check report from suppliers & collaboration (metrology, material properties, ISO GPS drawing checks…)
Follow up test and get feedback for potential improvement for series

## Slide 12
Cold test – static heat load @2K measurement
Lhe level in%
The static heat load at cold can be evaluated by stopping the liquid helium supply when all the temperatures are stabilized and checking the variation of the level in the cavities (the 4-20K and 50K thermalization line are kept in circulation)
In our case the level was at 68% when the 2K liquid helium supply was stopped and went down to 34% 105min later
These measurement gives us :
68 to 34% : ~52.5L
Time : 105min
Load on 2K : ~21W
Load estimated : 23.7W
(See EDMS 2310389)
See the presentation by K. Turaj

## Slide 13: SM18 – M7 test T° measurement feedback
Good matching of the temp measured WRT simulation
Robustness of the simulation performed -> validation of design for LHC CMs

## Slide 14: Conclusions
Engineering activities both cryomodules enter final phase
  Assembly BOMs & steps 6-12 -> adaptation for STFC and Triumf
  Follow up manufacturing and evaluation impact of CRs and NCRs
  Definition of missing design for LHC integration (cable rooting, transport, interfaces with surrounding equipment)
Preparation of CERN cryomodule assembly procedures
  Step 1-3 done – further steps are on-going
Update thermal budget evaluation for both cryomodule

## Slide 15: Thank you for your attention

## Slide 16
Design and Sim. Activities for FPC repair
Mechanical simulation : EDMS 2977959 – J.SWIESZEK
Tooling design to repair both cavities : EDMS 2977959 – P.MINGINETTE
courtesy J.SWIESZEK
courtesy P.Minginette
The calculation and the design were iterative and includes the inputs from S.Barrière, L.Prever Loiri and SY/RF (S.Calvo, E.Montesinos)
See the dedicated presentation by Simon Barrières, Joanna Swieszek & Edward Jordan

## Slide 17: Virtual evaluation of deformation FSI Measures – V.Rude
A measure of both the top FPC flange and the lower FPC outer pipe flange (Plane + axis for both) show a deviation as described on the sketches bellow :
Top flange plane
Top flange cylinder used to build axis
Lower plane FPC outer pipe flange
Lower flange cylinder used to build axis
Measured using laser tracker – courtesy V.Rude
CAVITY 1
Equivalent total angle = ~1.6°
Measured using laser tracker – courtesy V.Rude
CAVITY 2
Equivalent total angle = ~0.7°
Fig .5
Fig .6

## Slide 18: Virtual evaluation of deformation Radiographic measures – A.Porret
Set up preview - courtesy A.Porret
Theoretical clash = 0.5mm
(Hook/cavity wall)
3D modelling of the deviation
X-ray confirms our preliminary observations :
  The hook isn’t bended
  The deviation starts from the top
Result of radiographic measure (see full results in EDMS 2995980)- courtesy A.Porret

## Slide 19: Bonus : Test of material for clean room tooling
  Extracted from report EDMS 3141216
  (courtesy Micaela Battista – Nuria Valverde)
 | 0,3µm | 0,5µm | 1µm | 5µm | ISO
Aluminum | 0 | 0 | 0 | 0 | 1
Accura25 | 211 | 194 | 158 | 17 | 5
PLA | 2818 | 741 | 194 | 0 | 5
Results
Accura25 (Polycarbonate)
Non-anodized Aluminum
PLA (Polylactic acid)
Cost of manufacturing :
  the Accura cost of manufacturing is 2 times the cost of the PLA
  Aluminium parts costs 4 times the PLA part
Machining
Additive manufacturing
Discussion about the possibility to use Accura if the part is not close to the working area
(i.e. : close to open SRF/UHV volume)

## Slide 20: Thermal budget RFD
Teddy Capelli CERN/EN-MME
Thermal budget report for RFD:
See EDMS 2310389 - Thermal budget RFD cryomodule
Courtesy J.Swieszek – L.Giordanino
Thermal budget DQW
Thermal budget report for DQW to be updated
Revised estimation using measurements taken during cold tests
DQW/SPS – 2017/2018
Thermal budget estimate
DQW/SPS - 2016
EDMS 1729079
Static loads (estimates)
Static loads

## Slide 21: Alignment / Survey activities during CM build
# | Task Name
0 | CM2
1 | Step Aux.A - Pre-Cleanroom
4 | Alignment of components on the trolley
6 | Step1 - Cleanroom String Assembly
22 | Step Aux.F Top Plate Equipped
23 | Attach fiducials to Top Plate
24 | Install FSI heads
25 | Fiducialization of top plate
33 | Step Aux.*G* Lower OVC
34 | Attach fiducials to lower OVC
35 | Install FSI heads
36 | Fiducialization of lower OVC
38 | Step3 BiPhase & Tuner Frame Assy & FPC Plate Weld
40 | Alignment of FPC plate
60 | Step 5 Top Plate Assy & Interfaces
64 | Alignment of top plate WRT string
72 | Step 6 Load Transfer
76 | Install FSI targets on cavity flanges
98 | Step 10 Lower OVC Integration
101 | Alignment between lower vessel and top assembly
105 | Check alignment of cavities -->Model for the movement of the cavities caused by vacuum and cooling
 | Installation FSI system + Optcal fibers
 | Measurement of the cryomodule + FSI Heads at ambient pressure
 | Intercomparison FSI versus laser tracker
106 | Step 11 OVC Welding & CM Ancillaries
118 | CM2 Acceptance Tests
119 | Pressure Tests
 | Measurement of the cryomodule + FSI Heads under vacuum
120 | Cold Cycling + Tuner Check
 | Measurement of the cryomodule + FSI Heads at cold