## Slide 1: ET-PP WP 7.3
Status and planning
    July 26, 2024 Ilaria Giammarioli

## Slide 2
7.3.3 |  | Consider the most innovative and marketable results from R&D activities being pursued in ET which emerged from the analysis performed in Task 7.1, and carry out technology transfer support actions aimed at achieving an effective industrial exploitation, including technology protection strategy and business model definition. Patent analysis and market research studies may also be needed. |  | 
 |  |  | Which are the selected R&D activities ? | 
 | 7.3.3.1 |  |  | From the outcome of task 7.1 and the first part of sub-task 7.3.2.1, select the R&D activities that will be supported with specific TT services during the time span of the ET-PP European project
 |  |  | What goals will be pursued ? | 
 | 7.3.3.2 |  |  | Define a plan describing the goals to be pursued in terms of IP protection and IP valorization for each the the R&D activities and the actions that will be carried out
 |  |  | Execute the plan for each R&D activities; max 5 R&D activities | 
 | 7.3.3.3 |  |  | IP protection actions (prior art search, patent drafting, patent application filing) - I year
 | 7.3.3.4 |  |  | IP valorisation, exploitation, dissemination - I year
 | 7.3.3.5 |  |  | IP protection actions (prior art search, patent drafting, patent application filing) - II year
 | 7.3.3.6 |  |  | IP enhancement, exploitation, dissemination - II year

## Slide 3: Proposal of WP7.3 activities
Survey
Starting from the members of WG WP7 we are collecting information about R&D activities related to ET-PP
Once selected at least one technology a plan to support TT will be defined
Then We would like to extend the survey to all other Institutions involved
Execution of TT actions
WG WP7 and/or TTO of ETO can play a coordination role among the Insitutions involved
Cooperation with the TTOs of the Insitutions is expected for two reasons: i. they own Intellectual Property rights; ii. Otherwise work load wouldn’t be feasible for the WG

## Slide 4: Status and planning WP 7.3.3
Selection of case studies
WG decided to investigate activities of interest at
INFN
IFAE
Nikhef

## Slide 5: Survey of activities
INFN:
ETIC project
seismic filtering and low frequency control systems for the suspension of ET optics
low-noise cryogenic apparatus for the reduction of thermal noise in the main ET optics
new technologies in the field of photonics, optics and electronics
new materials to make the mirrors
IFAE
instrumented baffle technology
See the attachment to the Agenda
NIKHEF
See the attachment to the Agenda

## Slide 6: INFN: ETIC Project
Newtonian noise for earthquake early warning
  It’s not a new topic
  Other istitutions could be involved
  TRL to be verified
Inertial platforms for industrial plants
  Prosecution of VIRGO
  There is a potential interest of a company

## Slide 7: Next steps September 2024
R&D Survey (tbc)
Selection of the R&D activities to be supported in protection and valorization project
After that, a tailored plan for each selected R&D activities should be defined