## Slide 1: NA-CONS LS3 Readiness Review: Questions to the WPs
Jiva Hill Resort, 20th June 2024

## Slide 2: Schedule related queries
Have you identified any activity which is or may soon be on the critical ?
  BSI WU (4 new units): Studies ongoing , but spill intensity measurement at few % absolute accuracy is on critical path (no clear solution today).
  Fast Spill monitor WU: prototype being commissioned
    DAQ : no evidence of showstoppers
    Detector (OTR-PMT): ultimate performance, reliability and lifetime to be assessed
Have you identified any potential showstopper within your WP which may impact your deliverables ?
  Related to new BSIs WU: 2024 proposal to add in MTP one CCC for BSI cross-calibration
    Not approved --> showstopper

## Slide 3: Resource related queries
Are the pledged resources secured for LS3 ?
  Yes (with exception of CCC)
Are there potential conflicting resource allocations already identified ?
  No

## Slide 4: Logistic & General Services related queries
Have all the logistic and support needs been identified and requested?
    Provide detailed list including ticket numbers, PLAN IDs,
      See next slide
    Integration needs, cabling request (incl. radhard cables), transport, storage, etc…
      For the radhard cables the discussion is ongoing, TB planned on June 20 to regroup requirements and define group strategy.
      DICs are produced (currently using ordinary cables)
      Integration studies to be completed, ECRs to be prepared
      Transport support needed
      Devices are usually stored in our storage

## Slide 5: Logistic & General Services related queries
WU# | Plan Activity | Group | Title | Cabling Ticket | Specifications | ECR
234918 | 12850 | SY-BI | PRIMARY-CONS : BSI 4 new unit | RQF2639957 | Func Specs EDMS 2113420: reach 1% abs accuracy for POT monitoring Eng. Specs: improved BSI versions under study, no solution yet for 1% | Not started
234919 | 13615 | SY-BI | PRIMARY-CONS : BSP replacement with 4 SEM grids units | RQF2484037 | Engineering specs: Doc almost finalized (Federico Overleaf) Functional specs: EDMS 2897766 and 2113420 | In preparation
250767 | 13883 | SY-BI | NA-CONS-HI 3 New SEM grids in TT20-TT25 lines | RQF2484065 |  | In preparation
? | 12957 (?) | SY-STI | Coordination of North Area target stations (T2, T4, T6, T10) consolidation | RQF2484088 |  | -
248568 | 13616 | SY-BI | PRIM-UPGRADE : P42 SEM production: 3 units | RQF2031020 | BSG heads upgrade to new design | In Preparation
234921 | 13617 | SY-BI | Fast spill detector production | not needed yet | Func specs EDMS 3091057 Eng, specs: fiunal draft available (describes installed DAQ) | 2885161
234920 / 248567 | 12859 | SY-BI | BTV NA consolidation /PRIMARY-CONS : BTV230925 upgrade | ? | Func Specs: EDMS 2113420 | In preparation
250769 | NA | SY-BI | NA-CONS-HI SEM Grids Electronics production | None | EDA-03875-V3-1 | None

## Slide 6: LS3 Planning related queries
Indicate the status and deadline for availability of Specifications, Integration and ECRs
  Functional specifications ~clear and documented for all WUs
  Eng specs + ECRs: in final draft or in preparation. Still need to clarify and document details on mechanical designs and integration
Indicate the time slag between your equipment readiness and the corresponding installation date?
  As of today: readiness dates in line with installation dates on APT.
Please give details concerning the commissioning phase of your equipment: earliest start date, minimum duration, required needs (services, resource, etc…)
  IST during installation
  Minimum 1 month is needed for commissioning with beam all instruments
  Commissioning can be completed only with operational beams

## Slide 7: HI-ECN3 related queries
Indicate if your equipment is or may be impacted by potential delays incurred within HI-ECN3 and how this could be mitigated?
  No evidence of any issue

## Slide 8: Risk related queries
Highlight the risk/impact of not being ready and/or requiring more time
  Limited absolute accuracy beam intensity measurement
  Limited resolution beam position and beam size monitoring
Highlight in a more general/strategic way what a shift of LS3 would imply:
  Simple delay will not have any impact as long as LS3 duration is maintained (i.e. not reduced)
    Late LS4,
      ??
    Advantages of maintaining the current start date of LS3 independently from the rest of the injectors
      -??
    What would it imply to extend the scope of LS3 (include a pre/mini-Phase2 phase within LS3): list potential Phase-2/LS4 activities which could be brought forward to LS3
      BI has no manpower available to anticipate Phase2

## Slide 9: Suumary Slide

## Slide 10
Thank You