## Slide 1
HL-LHC Surface Facilities - Integration Approval |  |  |  |  |  |  |  | 
HL-LHC Facility | Phase I |  |  |  | Phase II |  |  | 
 | 3D Model ST Reference | Approval Date | Approval excludes | EDMS | 3D Model ST Reference | Approval Date | Approval excludes | EDMS
SD17 | ST0756787_01 a.08 | APPROVED | Cryogenics | 2798732 | TBD | 30/09/2024 | - | 2922909
SD57 | ​ST0754609_01 a.08 |  |  |  |  |  |  | 
SE17 | ST0986971_01 a.09 | APPROVED | - | 2602649 |  |  |  | 
SE57 | ​ST1077636_01 a.03 |  |  | 2602647 |  |  |  | 
SF17 | ST1120227_01 b.05 | APPROVED | - | 2472392 |  |  |  | 
SF57 | ​ST1120209_01 b.07 |  |  | 2476229 |  |  |  | 
SHM17 | ST1120227_01 b.05 | APPROVED | Cryogenics | 2474871 | TBD | 30/09/2024 | - | 2922909
SHM57 | ST1074362_01 b.05 |  |  | 2474886 |  |  |  | 
SHE17 | ST1223587_01 b.00 | APPROVED | - | 3046036 |  |  |  | 
SHE57 | ST1225860_01 b.00 |  |  |  |  |  |  | 
SL17 | ST1225867_01 b.00 | APPROVED | Cryogenics | - | TBD | 30/09/2024 | - | 2922909
SL57 | ST1316459_01 a.02 |  |  |  |  |  |  | 
SU17 | ST1120220_01 a.03 | APPROVED | - | 2602651 |  |  |  | 
SU57 | ST1120214_01 a.03 |  |  | 2602650 |  |  |  | 

## Slide 2
HL-LHC Underground Facilities - Integration Approval |  |  |  |  |  |  |  |  | 
HL-LHC Facility | Phase I |  |  |  | Phase II |  |  |  | Phase III
 | 3D Model ST Reference | Approval Date | Approval excludes | EDMS | 3D Model ST Reference | Approval Date | Approval excludes | EDMS | Approval Date
UA13 | ST1803909_01 a.00 | APPROVED | Cryogenics and RF | 3061528 | TBD | 30/10/2024 | - | 3018054 | 
UA17 | ST1803916_01 a.00 |  |  |  |  |  |  |  | 
UA53 | ST1803953_01 a.00 |  |  |  |  |  |  |  | 
UA57 | ST1803979_01 a.00 |  |  |  |  |  |  |  | 
UL13 | ST1803907_01 a.00 | APPROVED | Cryogenics and SC Link |  |  |  |  |  | 
UL17 | ST1803823_01 a.00 |  |  |  |  |  |  |  | 
UL53 | ST1803986_01 a.00 |  |  |  |  |  |  |  | 
UL57 | ST1803991_01 a.00 |  |  |  |  |  |  |  | 
UR15* | ST1803674_01 a.00 | APPROVED | Cryogenics and machine related equipment | 3004473 | ST1876975_01 a.00 | APPROVED | Cryogenics, SC Link, and WCC 1R 5R | 3091313 | 14/10/2024
UR55* | ST1805411_01 a.00 |  |  |  | ST1876924_01 a.00 |  |  |  | 
US17 | ST1803787_01 a.00 | APPROVED | Cryogenics | 3004543 | TBD | 30/09/2024 | - | 2804653 | 
US57 | ST1805261_01 a.00 |  |  |  |  |  |  |  | 
UW17 | ST1803787_01 a.00 | APPROVED | - | 2874651 |  |  |  | *See following slide. | 
UW57 | ST1805261_01 a.00 |  |  |  |  |  |  |  | 

## Slide 3
*HL-LHC UR15/UR55 – Intermediary Milestones for Phase III Integration Approval |  |  |  |  | 
HL-LHC Facility | Water manifolds PC (EN-CV) | WCC (EN-EL) | Water manifolds WCC (EN-CV) | Cryogenics (TE-CRG) | SC Link (WP6A)
UR15 Left | 02/09 | APPROVED | 02/09 | 16/09 | 16/09
UR15 Right | 30/09 | 16/09 | 30/09 | 16/09 | 16/09
UR55 Left | 02/09 | APPROVED | 02/09 | 16/09 | 16/09
UR55 Right | 30/09 | 16/09 | 30/09 | 16/09 | 16/09

## Slide 4
HL-LHC Surface and Underground Facilities – Installation Discrepancies |  |  | 
HL-LHC Facility | GIS | 3D Model Reference | Report
SD17 | 3155 | ST0756787_01 a.08 | ​SD17 Report
SD57 | 3555 | ​ST0754609_01 a.08 | SD57 Report
SE17 | 3154 | ST0986971_01 a.09 | SE17 Report
SE57 | 3560 | ​ST1077636_01 a.03 | SE57 Report
SF17 | 3169 | ST1120227_01 b.05 | ​SF17 Report
SF57 | 3569 | ​ST1120209_01 b.07 | SF57 Report
SHM17 | 3168 | ST1074294_01 b.05 | ​SHM17 (Phase I) Report
SHM57 | 3577 | ​ST1074362_01 b.05 | SHM57 (Phase I) Report
SL17 | 3161 | ST1225867_01 b.00 | ​SL17 Report
SL57 | ​3561 | ​ST1316459_01 a.02 | SL57 Report
SU17 | 3180 | ST1120220_01 a.03 | ​SU17 Report
SU57 | ​3580 | ​ST1120214_01 a.03 | SU57 Report
US17/UW17 | 3134 | See Phase I 3D Model ST Reference | US17/UW17 Report
US57/UW57 | 3539 |  | US57/UW57 Report
UR15/UA1X/UL1X | 3124 |  | UR15, UAs and ULs P1 Report
UR55/UA5X/UL5X | 3523 |  | UR55, UAs and ULs P5 Report