## Slide 1: WP CO Progress and Status Q2 2011 June 27th, 2011 Johannes Gutleber
R. Gutleber

## Slide 2: Summary
Development is advancing well with resources
No contingency in schedule
Continuous integration has highest priority
2011 – The year in which we conclude!
Core functionality by end of year

## Slide 3: Progress
Report

## Slide 4: Next Project Milestones
+4m (Oct. 2011) – Control system setup ready for source tests
+6 m (Dec. 2011) - ITS beam from source to spectrometer
+9 m (Mar. 2012) – ITS beam to RFQ
+15m (Sept. 2012) – Control system installation begins
+1.5y (Jan. 2013) – Control system ready for testing
March 2013 – Accelerator ready for commissioning
  Requires complete control system

## Slide 5: Injector Test Stand

## Slide 6: Current Phase (Elaboration)
Focus on requirements consolidation, architecture, design
Implementation of core functionality
Initiate deployment definition

## Slide 7: Project Organisation
Source(s)
Linac
Radio-Frequency
Beam Diagnostics
Vacuum
Power
Controls
Magnets
Special Magnets
Radiation Protection
Integration
Optics/
Dynamics
B. Nicquevert
W. Rupprecht
T. Hauser
F. Luiz
D. Gabriele
P. Landrot
S. Marinics
S. Pelletier
S. Bailly
J. Heimann
G. Magrin
A. Beuret
I. De Cesaris
P. Fraboulet
M. Veenstra
M. Jimenez
G. Hulla
J. Wallner
F. Osmic
A. Gyorgy
S. Schwarz
A. Kerschbaum
M. Repovz
S. Engelhardt
J. Bosser
W. Pirkl
E. Sargsyan
H. Grill
B. Lutzer (10/11)
N. Chatzigeorgiou (9/11)
L. Penescu
Accelerator Management
M. Benedikt, A. Wrulich
Injector Coordination
W. Pirkl
Synchrotron/HEBT Coordination
U. Dorda
IBTS Coordination
R. Mayer, S. Vatnitsky, A. Wrulich
Project Planning and Tracking
A. Fabich
W. Pirkl
G. Kotzian
J. S.-Quesada
Administrative Support J. Schueler
work packages
Consultant
EBG employee
Student
Work package leader
Junior partner
J. Gutleber
R. Moser
M. Marchhart
A. Brett
C. T. De Matos
M. Thonke
M. Hager
H. Pavetits
J. Junuzovic
H. Vincke
E. Feldbaumer
L. Jaegerhofer
Interception Devices
O. Aberle
K. Asvestas
D. Grenier
T. Zickler
M. Stockner
C. Siedler
A. Beaumont
P. Schwarz (8/11)
B. Langenbeck
T. Tortschanoff
Purchasing Officer
S. Mitchell
Risk Management
Technical Safety Officer
Jan Borburgh
T. Kramer
T. Stadlbauer
F. Mueller (???)
O. Nairz
P. Trnkova
O. Nairz
M. Schokker
S. Trovati
M. Palm
S. Vatnitsky
O. Nairz
P. Trnkova
F. Coreth
A. Koschik
U. Dorda
P. Bryant
H. Schönauer
F. Moser
BDS
PAS
MSS
Gantry
Ion Beam Therapy System (IBTS)

## Slide 8: Development on Progress

## Slide 9: Architecture Overview

## Slide 10: Plan until Q4 2011

## Slide 11: Current Status

## Slide 12: Roadmap Towards Commissioning
2012
2013
2014
2010
12/2011 ITS+CRB column
06/2012 Pre-release
12/2012 Functional release
12/2010
Column demo
03/2013 Commissioning
09/2011 ITS intermediary release
2011
07/2012 Start IT installation
10/2012 Start CO installation

## Slide 13: Integration Weeks (iWeek)
Validate components and concepts continuously!
Learn using our system!
Identify gaps!
Run the system!
Test Pilot
Big Success!
To be continued…

## Slide 14: Organization of iWeeks
One week at distance of about five weeks
  Step-by-step integrate all available components
  Operate vertical column (tier 1 to tier 3)
Planning and Execution
  Plan prepared and communicated to entire team
  Integration carried out by core team at CERN
  Results are documented in a record and communicated
  Results must be be taken into consideration for developments

## Slide 15: iWeek Schedule 2011
PR-110328-a-JGU, March 28th, 2011
J. Gutleber
15
15
2
1
3
4
5
6
7

## Slide 16: Column

## Slide 17: Detailed Status

## Slide 18: Operations Concepts
Started with Ion Source
  Idle operation, stability feedback
Initiated specifications on how to operate individual devices
  UDO will compile use-cases
Cycle Configuration Generator
  MHA started to work with MAD-X
  Frequent sessions with UDO on needs
  Start with C# API and library to generate timing/PCO sequences

## Slide 19: Status of Work with Other WPs
WP/Subsystem | Requirements | Design | Implementation | Integration
Power |  |  |  | 
Spec. Mag. (BTS) |  |  |  | 
Vacuum |  |  |  | 
Injector RF |  |  |  | 
Synchrotron RF |  |  |  | 
BDI |  |  |  | 
BID |  |  |  | 
Magnets |  |  |  | 
Sources |  |  |  | 
MSS |  |  |  | 
IBTS (TCS,BDS) |  |  |  | 
Building |  |  |  | 
IT |  |  |  | 

## Slide 20: What we have Today
Completed and frozen frozen architecture
MTS real-time event distribution transport layer
PCC real-time links, custom hardware, Family A PCO
FECOS core and documentation (RT programming framework)
PVSS/C# integrated, additional tools (STEP viewer, libs) done
Virtual Accelerator Allocator implemented to large extent
Generic GUIs (FrontPanel, ScratchPad, VAcc/WSE)
PVSS script libraries for state-driven devices
ProShell architecture and code skeleton
RMS adapted 70% - remain extensions (cable, rack, elements)
RMS importer and exporter for PVSS, OPC

## Slide 21: Planning 2011
Cosylab
  CWO-3 running until July 2011
  Planning for CWO-4 (12/2011) delayed!
Working sessions on schedule with WPs for 2011
  SRC, VAC, PO, INJ/RF done
  Building infrastructure, IT done
  Integration (cabling, racks) many items addressed, but work delayed
  Agreement on principle of development with BD, done
Remain to be defined for 2012
  BTS, Sync/RF, BD, BID, RP, operations, integration
  Interface medical systems
  Ion Beam Therapy System
  what else? – please get in contact!

## Slide 22: Summary and outlook

## Slide 23: Conclusions
Good progress made with continuous integration (iWeeks)
Good progress made in completing requirements
  Sources, injector RF
Schedule remains tight
NEXT STEP - ITS RELEASE 09/2011