## Slide 1
WP9: Innovative superconducting cavities
Oleg B. Malyshev (UKRI) / Claire Antoine (CEA)
WP9 coordinators
IFAST steering committee 21/10/2024

## Slide 2
WP9 objectives
Define a strategy for innovative superconducting RF (SRF) cavities coated with a superconducting film.
  Deposition techniques: PVD and ALD
  Superconducting films: Nb, NbN, Nb3Sn, V3Si (and others) and SIS
  Optimization of flat SRF thin films production procedure
Optimise and industrialise the production of seamless copper cavities and of the deposition techniques.
Produce and test prototypes of SRF (single-cell elliptical) cavities:
  Initially with pre-prototypes with f = 6 and 3 GHz
  Scaling up for f = 1.3 GHz.
Test a new laser treatment of Nb coated cavity.
Main goal:
  Improving the performance and reducing the cost of acceleration systems
    both production and operation

## Slide 3: First the bad news
Delayed Deliveries

## Slide 4
IFAST WP9 Milestones |  | IFAST WP9 Deliverables | 
MS37: International thin film workshop organization (web site) | M28 | D9.1: Thin-Film SRF roadmap report. Summaries of the results obtained within the workpackage and prospective inspired from WP advances as well as discussions at TF-SRF 2022. | M35
MS38: First seamless copper 1.3 GHz cavity produced as substrate for the coating of the SC film (Report) | M12 | D9.2: RF test on coated resonant cavity. Resonant cavity coated and tested with an alternative material to Niobium with a Q0 > 109 at 4.2 K and 1.3 GHz. | M46
MS39: Coating facility built and tested at STFC, USI and INFN (Report) | M12 | D9.3: First 6 GHz cavity coated and characterised. Results from the morphological and SC characterisation of first coated cavity with an alternative material to Niobium. | M36
MS40: Construction and operation of the cavity dedicated ALD system (Report) | M24 | D9.4: Deposition of superconducting multilayers on cavities. 1.3 and 3 GHz Nb and Cu cavities coated and tested with multilayers. | M46
MS41: A facility for laser operation for complex 3D treatment is tested on 1.3 GHz cavity (Report) | M36 | D9.5: 1.3 GHz Nb-coated cavity irradiated by laser in Ar atmosphere and RF tested. Increasing of the field of magnetic flux entry in Nb coated 1.3 GHz cavity irradiated by laser in argon atmosphere. Standard RF testing. | M45
MS42: ARIES samples prepared for renewed SC film deposition | M6 | D9.6: Test of thin-film samples. Four thin film samples reprocessed by 4 different techniques and tested with QPR. | M46
M42
M45
M43
M47
M46
M46

## Slide 5: (Delayed) deliveries:
D9.1 01/25, European road map M45
D9.6 02/25, QPR test on samples M46
D9.4 02/25, 1.3 and 3 GHz Nb and Cu cavities coated and tested with multilayers M46
D9.3 02/25, First 6 GHz cavity coated and characterized with an alternative material to Niobium. M46
D9.5 02/25, 1.3 GHz Nb-coated cavity irradiated by laser in Ar atmosphere M46
D9.2 03/25, RF test on coated resonant cavity M47
_______________
D10.4 12/24 M40
Notes: Microsoft Word - ShinyNb3Sn_June2020_submission_with_supplement.docx (arxiv.org)
Thermal study of a cryogen-less MgB2 cavity - ScienceDirect

## Slide 6: Delayed deliveries, 3 main reasons:
Delays on Copper cavities production
  Absolutely necessary as a substrate for deposition
  Difficulties to get the proper Copper quality supply
  Impact on D9.2, D9.4 and D9.5
Delays on the Nb3Sn development
  Difficulties to achieve the nominal Tc and a “recipe” compatible with deposition on copper (3 years development were necessary)
  Deposition inside 1.3 GHz cavities: no commercial Nb3Sn cylindrical target available, the development had be done “in house” (INFN)
  Impact on D9.2, D9.3, D9.6
Difficulties to access preparation + RF test for R&D prototypes
  (e. g. at Saclay, < 10 tests/ year for R&D, < 3 for IFAST) (D9.2, D9.4 and D9.5)
  … and other unexpected technical difficulties (e.g. D9.5)
Notes: Microsoft Word - ShinyNb3Sn_June2020_submission_with_supplement.docx (arxiv.org)
Thermal study of a cryogen-less MgB2 cavity - ScienceDirect

## Slide 7: D9.1 “Thin film SRF roadmap report”
Reported to January 2025 (M35 => M45)
The date of the workshop had been anticipated in 2019 before the Covid pandemic
Only a small virtual edition in March 2021.
In 2022, the International Scientific Committee decided to resume live editions on even years in order not to overlap with SRF conference years, 10th edition in JLab and 11th in France
In 2024, the workshop, initially foreseen in June, was postponed in September to accommodate teaching constraints of several members of the community (ISC)
A full day session was dedicated to the gathering of information for the Roadmap (with international participation). A survey was answered by ~10 different labs, 3 regions.
It is currently being compiled in order to write a report

## Slide 8: D9.3 “1rst 6 GHz cavity coated and characterized with an alternative material to Niobium”
Reported: M36 => M46. The deliverable is already achieved, but we are trying to push the performances before writing the report
2 cavities were deposited with NbTiN and tested, Tc was correct, however the Q-value was 2 decades lower than what was expected due to film delamination. (6 GHz cavities coating process is cheaper, but more challenging than 1.3 GHz)
We are still in the process of adapting the recipes from samples to cavities
Most delays arise from the difficulties to find the correct deposition parameter (Nb3Sn, NbTiN,…)
In house Nb3Sn cathode not ready yet (technical issues on new inductive system for dipping)

## Slide 9: D9.2 “RF test on coated resonant cavity”
D9.3 must be achieved first (and is slightly delayed)
Coating Recipe defined on planar samples, first test on 1.3 GHz cavities ongoing (STFC). New Coating system with planar commercial Nb3Sn targets ready in December (INFN).
Main limitations are now
  the lack of copper cavities (only a few available up to date for the whole community)  new seamless cavity design by INFN-Piccoli under test (eliminates flange e-beam welding, current bottleneck)
  The delays in RF testing : very small turnover, long delays to assess the results or to know one has to modify them.
No zero risk we don’t test the 1.3 GHz cavity before April
NB 4 deliveries to be reported in Feb., (M46 => M47)
Notes: 4 deliveries to be reported in feb

## Slide 10: D9.4 “1.3 and 3 GHz Nb and Cu cavities coated and tested with multilayers”
2 cavities deposited and tested, but showed delamination
Recent tests have been performed on tubes and large curved samples without exhibiting delamination.
Degassing of the cavity larger surface is suspected, and corrective actions during annealing will be taken
About 6, 1.3 GHz cavities coated by ALD with oxides layers within the last year.
3 GHz Nb cavity sent to KEK for surface chemical treatment and baseline.
Bottleneck : availability of 1.3 GHz copper cavity (1 arrived this week from CERN to be deposited) and delay for cryogenic RF testing.
D9.4 in 02/25 (M46) should hold, but only w. 1 or 2 RF tests (problem solved?)

## Slide 11: D9.5 “1.3 GHz Nb-coated cavity irradiated by laser in Ar atmosphere”
The building of the 1.3 GHz irradiation facility was delayed due to technical difficulties
No successfully deposited cavity is available for now (issue with 1.3 GHz copper cavities supply)
It was tested with deposited parts (tube)
Still expecting a fully deposited cavity from STFC
Reported M45 => M46

## Slide 12: D9.6 QPR test on samples
Four thin film samples reprocessed by 4 different techniques and tested with QPR…
The task in underway, not fully completed yet
  Substrate preparation has been assessed
  Nb and Nb3Sn have been deposited and tested with excellent results
  Other materials/techniques to be tested in the future
No delays announced yet, but turnover of test is impacted like for all cryogenic platforms (prices for Helium and electricity => less tests possible)

## Slide 13: … but some very good news
Delayed Deliveries

## Slide 14: Progress towards objectives :
• 4 Different coating systems for 1.3 GHz were designed and built (1 at INFN, 2 at UKRI, 1 ALD system in CEA).
• Study on Nb3Sn coating parameter effect on Tc concluded.
• Optimized coating recipe for high Tc Nb3Sn defined.
• Nb3Sn coating recipe evaluated on a quadrupole resonator (QPR). Best results in the SRF community! (new sample under testing)
• Deposition with NbTiN and RF evaluation of a 6 GHz cavity was completed by INFN.
• A mock 6 GHz copper cavity with two short copper tubes was deposited with Nb for various deposition parameters and sent to post-treatment.
• Optimum deposition parameters were defined for V3Si, for NbTiN on stainless steel, and for SIS multilayer.
• Atomic Layer Deposition (ALD) was performed on six 1.3 GHz cavities, including test depositions of Al2O3 on Cu coupons for Nb deposition by HIPIMS at CERN, and test depositions of Y2O3 on Cu coupons for Nb3Sn deposition by HIPIMS at CERN.
• A facility for laser operation for complex 3D treatment on 1.3 GHz cavity was tested, initially with pure copper cavity, then with first Nb coated cupper cavity components.
• New green and faster polishing treatment (Plasma Electrolytic Polishing) developed for 1.3 GHz cavities
• New cavity seamless forming process developed

## Slide 15: Conclusion
Most delays originate from external causes
The work has nevertheless brought the IFAST community in a position of technological leadership, especially on Nb3Sn developments
We need more time, not necessarily more money to achieve the IFAST objectives (a lot is going on, but delayed) => prolongation necessary?
We need to prepare “after IFAST”
I hope it will be based on the road map document that we are preparing

## Slide 16: D10.5
Some news from Siberia and Oleg…

## Slide 17: D10.4 First PSD data from NEG coating
3 Samples coated with NEG and studied under Synchrotron radiation
  2 at DLS, 1 at Soleil
  Results are being analyzed now
  More samples will be installed at the next shutdown of both DLS and Soleil (12/24)
  Preliminary results already reported at EVC-17/ECOSS-37 (June 2024, Harrogate) and at the 103th IUVSTA workshop (June 2024, York)
Delayed M36 to M46
  Technical problems to realize the coatings
  Delayed installation on the beam lines (waiting for the shut-downs)
  Delivery report is now being drafted

## Slide 18
Thanks for your attention