## Slide 1
Task 7.3: VAriable Dipole for the Elettra Ring (VADER)
Y. Papaphilippou for the Task 7.3 collaborators
I.FAST - Steering Committee Meeting #13 – 21/10/2024

## Slide 2: Profile Design and Magnet Specifications
Specifications | CLIC DR | VADER
Magnet Gap (mm) | 13 | 18
Max Field (T) | 2.3 | 2.3
Transverse G (T/m) | 11 | 23
Field Quality (Units 1E-4) | ≈ 1 | ≈ 1
Magnet Length (cm) | 56 | 80
Finalised in December 2022 (8 months delay, hiring issue during COVID)
Similar parameters as CLIC DR but…
  Higher transverse gradient (> factor of 2)
  Higher magnetic gap (~40%)
  Longer magnet (~40%)

## Slide 3: Magnetic design challenges
Needed to satisfy field requirements for curved trajectory.
Curved trajectory combined with higher gap and low multipole content for iron dominated magnet that works under saturation, extremely difficult objective
Sagitta much higher than expected
Opera software bugs not present in previous versions, impossible to perform required calculations with curved trajectory
This forced to manually develop in-house code (CIEMAT) to analyse field quality (in both Opera & Matlab)

## Slide 4: Magnetic Design @ CIEMAT
Longitudinal gradient profile achieved
Integrated transverse gradient exceeds specs
Field quality looks reasonable
Fabrication drawings in progress
Hyperbolic pole tips profile
M. Dominguez,
F. Toral
B1 | B2 | B3 | B4 | B5 | B6 | B7 | B8 | B9 | B10
10000 | -807.79 | 4.65 | 6.74 | -1.09 | 0.21 | -0.07 | 2.55E-05 | -0.01 | -0.03
New PM blocks dimensions
New poles
New field regulation design

## Slide 5: Resolving CLIC prototype issues for VADER
Discrepancy in CLIC prototype between simulations vs magnetic measurements with integrated dipolar field 4% lower
Various investigations: missing Armco heat treatment, misalignment, hysteresis, simulation error, etc.
Traced back to Opera simplifications required not reflected in real 3D mechanical model
Any of them alone not capable to explain difference
All three simulated allow model matching almost perfectly magnetic measurements!
Simulated integrated field is now 0.641T vs 0.638 measured
6 mm HF & MF pole base expansion
LF pole extrusion
MF pole extrusion

## Slide 6: VADER: Mechanical Design
Mechanical design started in September. Now is finished and production drawings ready for KYMA
From this…
…to this:

## Slide 7: VADER vs CLIC Prototype: Main differences
Iron yokes formed by 3 main pieces instead of one, screwed from iron to iron across aluminium support block (before first assembly step)
In VADER, same pole adjustments in MF and LF modules present in CLIC except DY (vertical adjustment)

## Slide 8: VADER vs CLIC Prototype: Main differences
PM blocks bigger, meaning higher forces. POM boxes redesigned (longer) and second one to carry block added
Moving parts of field regulation under much higher forces, guides reinforced and regulating screws include bronze ending to avoid fluency with time (instead of plastic in CLIC)

## Slide 9: VADER: Timeline
Material List - by October 2024
  CIEMAT sent list of materials used to expedite procurement and Kyma pre-ordered bulk material with longest delivery times
Final manufacturing drawings - by beginning of November 2024
From mid-November 2024, Kyma proceeds with procurement of all components.
Initial estimates indicate that materials ready and delivered by March-April 2025
Assembly process estimated as follows:
  1 week for mechanical assembly of the modules.
  2 weeks for final assembly.
  1 week contingency.
Latest date for deliverable May 2025

## Slide 10: VADER timeline
Optics work including magnet specifications completed (CERN/Elettra) since end of 2022
  8 months delay in hiring fellow
Magnetic and mechanical design from CIEMAT completed with input from KYMA for fabrication, ready by September 2024
  16 month delay due to early departure of fellow and challenges with magnetic design
Fabrication of the prototype by KYMA started on October 2024 (drawings transmitted)
Prototype ready for acceptance tests by May 2025 (7 months delay in deliverable 7.3)
Acceptance tests will be finalised by June 2025
Milestone MS 26
Deliverable D7.3
Milestone MS 27

## Slide 11
Thank you for your attention!

## Slide 12: VAriable Dipole for the Elettra Ring - VADER
Task 7.3 within I.FAST WP7: High Brightness Accelerators for Light Sources
Partners and collaborators:
Y. Papaphilippou
(A. Poyet)
M. Dominguez
F. Toral
E. Karantzoulis
D. Castronovo
R. Geometrante

## Slide 13: VADER objectives
Fabricate an innovative dipole magnet prototype with longitudinal varying dipole field, including a transverse gradient for the ELETTRA upgrade
Permanent magnet concept with trapezoidal bending radius, 2.3 T peak field and ~10 T/m gradient, already established (CERN/CIEMAT)
Proved the horizontal emittance reduction to ultra-low levels of i.e. ~60 pm @ 2.86 GeV, for the CLIC DR (M. A. Domínguez Martinez et al., IEEE Trans. Appl. Supercond. 28, 1, 2018; S. Papadopoulou et al, PRAB 22, 091601, 2019)
First demonstrator constructed/qualified by CIEMAT

## Slide 14: VADER objectives
Keep the same S6BA-E lattice for Elettra and replace the LG dipoles by VADER ones.
  Implement a trapezoidal profile in bending radius
  Observe a clear emittance reduction
Some constraints:
  Same geometrical layout
  Same total bending angle for each dipole
  Same dipole length
But also some freedoms:
  We set the dipole peak field at 2.3 T (as for the CLIC magnet) instead of the current 1.8 T

## Slide 15: Lattice and optics design
Optics constraints at the ID are matched
Horizontal emittance reduction from 212 to 100 pm (more than factor of 2!)
Tunes: 34.706 / 22.852
Chromaticities: -157/-125
Non-linear optimization: already good on-momentum DA
A. Poyet

## Slide 16: Magnetic Design @ CIEMAT
No changes in philosophy, major changes in poles (90% of the design time)
All NdFeB permanent magnet blocks, including low-field modules
Permanent magnet volume increased around 40% reaching demanded field peak of 2.3 T with magnet gap of 18mm (17+1mm)
New field trimming design implemented
    Yoke completely split in two parts supported by aluminium block
    Sliding parts achieve higher/better regulation than CLIC DR prototype
CLIC DR poles
VADER poles
M. Dominguez,
F. Toral

## Slide 17: CLIC: Preliminary Assembly
A preliminary assembly without permanent magnets (PM) should be done to assure the correct manufacturing and adjustment of all the parts.
Each module is mounted separately, with all the parts except the PM
Testing the modules’ approach system

## Slide 18: CLIC: Preliminary Assembly
HF module is mounted first, with the top and bottom aluminium plates
Then each module is introduced following the bronze guides fixed to the plates
Detail of one pole and how they are fixed in their nominal position using fibre gauges
Full assembly without PM

## Slide 19: CLIC: Assembly with PM
The PM blocks are introduced using a POM box attached to the yoke
The insertion was controlled using these rods and plate…
…that have to be redesigned due to the huge forces involved
This is already implemented for VADER

## Slide 20: CLIC: Assembly with PM
Magnetic measurements are done after each PM is inserted.
Low precision but necessary to assure the correct PM assembly
Once each module has all the magnets in, the controlled approach starts
The process is repeated with each module until the assembly is completed