## Slide 1: LS3

## Slide 2: Table of Contents
  Roadmap towards LS3
  Answer for the moment given by the groups
  Timeline to evaluate the request, considering the wish

## Slide 3: Long-term master schedule

## Slide 4: Injectors Road Map towards LS3
2023 |  |  | 2024 |  |  |  |  |  |  |  |  |  |  |  | 2025 |  |  |  |  |  |  |  |  |  |  |  | 2026 | 2027 | 2028 | 2029
Q3’23 |  |  | Q1’24 |  |  | Q2’24 |  |  | Q3’24 |  |  | Q4’24 |  |  | Q1’25 |  |  | Q2’25 |  |  | Q3’25 |  |  | Q4’25 |  |  | 2026 | 2027 | 2028 | 2029
O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D |  |  |  | 
TS
(E)YETS
LS
End Closure Year
LS3
EYETS 24-25
Master Schedule 24-25 approved
TS1’24 prep.
LS3 preparation
Master Schedule 24-25 Draft 1
End EYETS 23-24
LS3 starts 17/11/25
LS3 coordination
EYETS24-25 Baseline draft version
EYETS 23-24 coordination
TS1’25 prep.
End EYETS 24-25
LS3 Other projects approval
LS3 Baseline fixed
LS3 Baseline draft 2nd version
Last LS3 ECR approved
Master Schedule LS3 approved
Master Schedule LS3 Draft
EYETS 23-24
Meetings with groups (EYETS feedback, EYETS24-25 activities and LS3 activities)
LS3 Baseline draft 1st version
LS3 Work Packages Analysis
EYETS 24-25 coordination
LS3 Integration studies completed
LS3 Readiness Review
EYETS 24-25
LS3
Last EYETS24-25 ECR approved
EYETS24-25 Integration studies completed
EYETS24-25 Baseline for approval
Start LS3 ECR submission
Last EYETS24-25 IST approved
Start LS3 IST submission
Last LS3 IST approved
INTEGRATION STUDIES FOR LS3
FOLLOW-UP
UPDATE
STUDIES FOR EYETS24-25
FOLLOW-UP
UPDATE
TODAY

## Slide 5: News since last week
  LS3 start date:
    LHC: July 2026
    Injectors: September 2026
  NOTE:
  The priority now is:
    1st optimize the LHC to make it fit in 47 months
    2nd fit the restrictions coming from the LHC optimization, and the consequences on the groups resources availability to define the injectors planning (the duration of LS3 in the injectors may change due to this and this is why there is TBD)

## Slide 6: LS3 shift
  LS3 start date:
    LHC: July 2026
    Injectors: September 2026
To be revised

## Slide 7
M. Van Dijk on behalf of the MADMAX collaboration, List of requests received to run during LS3, IEFC, 19.04.2024
FACILITY: MADMAX | 
GOALS & JUSTIFICATION: List of the main objectives that you want to achieve with this request. MADMAX uses a new concept (dielectric haloscope) to search for axion dark matter in a mass range centered around 100 meV, favored by post-inflationary scenarios and not yet explored. A prototype of the final experiment, including a stainless steel cryostat, is presently being build and will be inserted in the Morpurgo magnet of the H8 line. Explain why it needs to be done during the LS3 and the consequences if your request is not approved. The MADMAX prototype run in the Morpurgo magnet requires the complete absence of beam. The stainless steel cryostat was designed to fit in the Morpurgo magnet. | 
SCOPE: Usage of the Morpurgo magnet of the H8 line including the upstream zone of H8B (PPE158) and the platform downstream of the magnet. | 
SCHEDULING: A long run for physics of the order of six months is preferred. Overall if we could stay on the Morpurgo site for one year to prepare (3 months), run (6 months) and dismantle (3 months), that would be great. Include any scheduling constrains that need to be taken into account. The preferred period is Dec. 2025 to Dec. 2026: i) preparation Dec. 2025- Mar 2026, ii) run with Morpurgo magnet at 1.6 T: Apr-Sep 2026, iii) Dismantling: Oct-Nov 2026. | 
SERVICES REQUIRED: More details provided in EDMS 2477727 | 
EN/CV | Mixed water for cooling (required during cooldown of the Morpurgo magnet and the physics run)
TE/CRG | Cooling of the MORPURGO magnet LHe / LN2 storage dewars from Cryolab / external company + recovery lines (He, N2) for cryostat cooldown. 2 vacuum pump units, cryocoolers and 5 compressor units, circulation pump for gHe, water chiller
EP/ADO-SO | Usage of Morpurgo magnet
BE/EA-DC | Crane to install the cryostat and its rails. Working place Tent set-up installation
OTHER RELEVANT INFORMATION: Include any other information that you consider important to evaluate your request. Morpurgo magnet zone is already used by the MADMAX group for tests during the Beam shutdown period since 2022. All installations in this area have already been foreseen to perform the test with the stainless steel cryostat | 
No RP impact

## Slide 8: Unresolved issue – Operation requests

## Slide 9: Summary / Conclusions
  The shift of LS3 has a considerable impact on the preparation
  We don’t know yet how the groups will be affected by the LHC optimization (we need to gain 4.5 months with respect to the actual time needed to perform all the works);
  In the NA we have some works that have to be analysed in detail with the concerned groups before we can confirm that it is possible to provide you all the services in the periods that you want to RUN – some of the concerned groups are the ones that will be the most affected by the LHC optimization
  We would like to keep October 2025 as the deadline to have a solid LS3 planning for the NA-CONS (it will not be the baseline as defined today), and at that moment we should be able to give you a well analysed answer to your request