## Slide 1: Summary of Requirements AMBER
Experiment | Workpackage | User requirment | Sub-work-packages | Planned for | Physics study status | Integration study status | ECR(s) status
AMBER | M2 under vacuum | EDMS 2719043 EDMS 3129053 | MBNV.X0610706 connection to vacuum | YETS 24/25 | Done | No need | EDMS 3169186 in circulation
 |  |  | XVC.X0610731 and XVC.X0610737 with 4 Al windows removal | YETS 24/25 | done | No need | EDMS 3169186 in circulation
 |  |  | MQNFB.X0610745 and MQNFB.X0610748 | YETS25/26 | done | No need | ECR to be done
 |  | EDMS 2798464 | All XCMs under vacuum | LS3 | done | To be done | ECR to be done
 |  | EDMS 2742301 | XCBV exchange with normal XCSV | LS3 | done | To be done | ECR to be done
 |  | EDMS 3012379 | XABS under vacuum (outside of MCWV) magnets | LS3 if budget approved | done | To be done | ECR to be done
 | High Intensity Hadrons |  | Shielding modifications at interface of EHN2/TT84, the access chicane of PPE211 | LS3 | done | done | EDMS 2868386 in circulation
 |  |  | Shielding around the target in EHn2 | LS3 | done | done | EDMS 2868386 in circulation
 |  |  | Additional collimator to be installed (DCUM 300 m) | LS3 | done | To be done | ECR to be done

## Slide 2: M2 -4th Part
Under vacuum in YETS24-25
Removed in YETS24-25
Under vacuum in YETS25-26
Vacuum flexible connection
All XCMs under vacuum in Ls3
XABS under vacuum in LS3?  to be confirmed

## Slide 3: Shielding Modifications AMBER

## Slide 4: Shielding Modifications AMBER
Target Bunker

## Slide 5
Thank you!

## Slide 6: M2 – 1st Part
QPS 112 transition inox chambers to Al
No vacuum elements to be kept like this
Beam instrumentation (XWCM) to be put under vacuum
New vacuum chambers needed
In TCC2 nothing can happen before LS3

## Slide 7: M2 – 2nd Part
XCMV 190 under vacuum in Ls3

## Slide 8: M2 -3rd Part
No vacuum elements to be kept like this
Beam instrumentation (XWCM) to be put under vacuum
New vacuum chambers needed

## Slide 9: M2 -5th Part
XCMH 845 under vacuum in Ls3
XCBV 858  exchange with XCSV normal on rails in LS3

## Slide 10: M2 – 6th Part
All XCMs under vacuum in Ls3
https://edms.cern.ch/document/706972/AC

## Slide 11: MBNV 706 - MBNV.X0610706
LINKS:
Panoramas (cern.ch)
Layout (cern.ch)
YETS 24-25:
Move window upstream (Al -> Mylar)
Clean the chamber
Place MBNV under vacuum

## Slide 12: XVC.X0610731, XVC.X0610737 : removal in YETS24-25
XVC 731 L=1975 mm
XVC 737 L=960 mm
Remove the chambers
remove 4 Al windows 0.2 mm thick (instead of 2.935 m of vacuum)
Vacuum flexible connection between QWL.X0610723 and XVC.X0610757 (around 31m)
Future installation of SS standard chamber in LS3
XCMV.X0610733 to be moved in YETS24-25 for EN-CV intervention ARR EDMS 3139745
Links:
Layout (cern.ch)
Panoramas (cern.ch)

## Slide 13: MQNFB.X0610745 and MQNFB.X0610748
Under vacuum in YETS25-26
Links:
Layout (cern.ch)
Panoramas (cern.ch)
QPL 745-QPL 748