## Slide 1: Building the ETO Roadmap, status, logic and methodology
ETO Meeting, Roma 27/28/11/2024
A.Variola, INFN Roma1

## Slide 2: Roadmap
A roadmap is a strategic plan that defines a goal or a desired outcome and includes the major steps (phases) or milestones needed to reach it.

## Slide 3: ETO Roadmap logic
Scheduling (timeline and correlation) of:
Deliverables : tangible and intangible
Milestones : significant point or event in the project development (usually at zero duration)
Turning points: major decisions leading to different scenarios, characterized by decision-making steps

## Slide 4: ET(O) & ETO
Two different roadmap concepts:
Roadmap for the ET Observatory, needs a project framework and all its managemement tools like the WBS, Schedule (resource loaded), Financial and Procurement plan, Risk response ….
Roadmap for the ET Organization for phase 1, following the coordinators mandate

## Slide 5: Mandate of ETO directors
https://edms.cern.ch/document/3161920/1
l. Set up the organization and the operations of the ETO (see the organization chart in the mandate, fig1: ETO Project Organization during Phase I). This implies defining the structure of the ETO (Phase I), giving mission statements (assignments) and work programs to the work units, naming staff members in the various work units, setting deadlines and quality control criteria.
2. Compare the triangle geometry with the geometry of two L-shaped infrastructures in scientific potential, risk analysis and costs.
3. Develop a budget plan and schedule for the Design and Preparation Phase. Control the budget and account for the funds allocated to the ETO (Phase I) by the ET Coordinators. https://edms.cern.ch/document/3162883/2
4. Steer and oversee the studies and the production of the documentation necessary to the BGR and to the associated working groups in the ministries, for the BGR to be in a position to review, modify, update and approve the report and finally set-up the organization for the construction and operation of the gravitational wave detector.

## Slide 6: From this: roadmap methodology
https://edms.cern.ch/document/3161919/1
Phase 1 has an expected outcome (documentation, existing and approved documents) in a defined time, so it can be see like a project.
Therefore the deliverables are existing and approved documents. In this framework, the definition of the Phase I roadmap and the consequent activities can be made by adopting a ‘project oriented’ approach. This will allow the identification of the needed work actions (WBS) and of the connected responsibilities (Organizational Breakdown Structure OBS).

## Slide 7: Methodology steps
1) Divide Phase I into subphases, each characterized by a report as the final deliverable.
2) Define the content of the reports, (deliverables of subphases, and deliverables for Phase
3) Define the supporting documents representing the intermediate deliverables
4) The lifecycle of the reports and of these intermediate documents, (upgrades, release, verification, validation etc.) must be duly defined.
5) Make a breakdown of the contents of the intermediate deliverables, thus generating a WBS.
6) Make a mapping of the activities already carried out and a survey of the skills present in ETO, ET-PP, ET Collaboration and the local teams, to associate a responsible person with each element of the breakdown (WBS), thus generating the OBS.
7) Associate a schedule, with defined milestones, to the main and intermediate deliverables to build the roadmap.
8) Associate the ETO organizational structure with the management of the activities described in the WBS, and in charge of the profiles defined in the OBS.

## Slide 8: Methodology evolution
1) Divide Phase I into subphases, each characterized by a report as the final deliverable.
2) Define the content of the reports, (deliverables of subphases, and deliverables for Phase
Due to the dynamical context of the definition of the coordinators and the BGR role, the reports requirement is not relevant. In the future?

## Slide 9: Still ongoing
3) Define the supporting documents representing the intermediate deliverables
5) Make a breakdown of the contents of the intermediate deliverables, thus generating a WBS.
6) Make a mapping of the activities already carried out and a survey of the skills present in ETO, ET-PP, ET Collaboration and the local teams, to associate a responsible person with each element of the breakdown (WBS), thus generating the OBS.
7) Associate a schedule, with defined milestones, to the main and intermediate deliverables to build the roadmap.
8) Associate the ETO organizational structure with the management of the activities described in the WBS, and in charge of the profiles defined in the OBS.

## Slide 10: Pending
4) The lifecycle of the reports and of these intermediate documents, (upgrades, release, verification, validation etc.) must be duly defined.
Also, if not associated to the reports the process of verification and validation of the deliverables is still topical

## Slide 11: ET-PP
EU project, coordinated by Mario Martinez that is a component of the ETO directorate
Many of the arguments, answering to the mandate requirements are covered in the ET-PP program, in the context for the different WP
A strong synergy is present and the ETO roadmap shall be aligned with the ET-PP project
ETO is co-leading WP1 (Management and Coordination), WP2 (Organization, Governance and Legal Aspects), WP5 (Project Office and Engineering Department), WP9 (Sustainable Development Strategy)
Strong and visible participation also in WP6 (Technical Design) thanks to the CERN collaboration for Vacuum and the ED effort in the detector studies and in WP10 (Education, Outreach and Citizen Engagement) thanks to all the efforts of the ETO communication office
ET-PP is the ET community ‘postcard’ that we send to EU. We must be aware of the importance of its success.
The reliability of our roadmap will depend on the quality of the ET-PP outcome
Future ET-PP meeting on the subject ‘how can we transfer the WP activities to ETO or ETC ‘ to steer the management process.

## Slide 12: Roadmap status
https://edms.cern.ch/document/3162883/2
Roadmap executive summary, a document that briefly summarize the context, the methodology and the main cornerstones of the ETO roadmap:
Main deliverables -> (that generate the WBS)
Main Milestones
Main turning points

## Slide 13: Deliverables
Deliverable 1 - Document: ETO in phase one
Deliverable 2 - Document: Phase 1 preliminary TDR
Deliverable 3 – Document: Project Management Plan
Deliverable 4 - Document: Organizational chart
Deliverable 5 – Document: Safety agreement
Deliverable 6 – Document: Phase 1 Cost book
Deliverable 7 – Document: Project impact
Deliverable 8 – Document: Configuration analysis
Deliverable 9 – Document: Phase 1 Risk report

## Slide 14: Milestones
The hierarchical lines, and operative rules established between the stakeholders.
Approval of ETO organizational and legal definition.
ETO resources available to steer the transition of the activities to a project context.
Project baseline definition and release.
Project structure implemented. To proceed with the project definition, it is necessary to make a transition from organizational to project-based management, where decision lines are determined.
ET-PP project outcome. Many arguments necessary for the release of deliverables are already developed in the context of the ET-PP project.
The recognition of the ET project in CERN's strategy.
The release of the new ESFRI roadmap.
The bid process definition. This milestone will allow Local Teams to develop the strategy for bid-books’ editing.
The bid-books release. This will eventually trigger the selection process.

## Slide 15: Turning points
Timeline for phase one. Depending on the time constraints defined for phase one, achievable maturity levels in activities and deliverables are defined (at present there is not established deadlines).
Timeline for phase one. It is important to have a decision if the choice of the site and the configuration are synchronized or not (at present we are working in a synchronized scenario).
Configuration. The configuration choice is the first crucial decision to be taken. This also represents an analysis factor for site selection being the two correlated. The final configuration choice will allow to focalize the effort in producing technical solutions, costing, risks and all the other deliverable contents to the selected design.
Site selection (if working in a synchronized scenario point c and d are merging).
Organization. The decision on the type of organization is a precursor turning point to the initiation of the project.
Project financing. The final turning point for phase one and is also a milestone. This is the decision on whether to approve the project and the financial structure to provide the necessary budget (go/no-go turning point).

## Slide 16: WBS-OBS & ET-PP aligment
Excel table, Teams group ETO ALL, Folder General/Documents/RoadmapWBS
Roadmap Deliverables - WBS.xlsx
 |  |  |  |  |  | Please note that text in purple are activities |  |  |  |  |  |  |  | 
 |  |  |  |  | Deliverables (Document), Tier1 | Chapter (Tier 2) | Tier 3 | Tier 4 | Tier 5 | Responsible | Comments | ET-PP Matching, Deliverables | Milestones | ETO manager
1 |  |  |  |  | ETO organization in Phase I |  |  |  |  | tbd |  |  |  | 
Color code :
Black: Documents and Documents Paragraphs. WBS part that should generate the OBS.
Purple: Actions (verbs), intermediate deliverables for WBS build up
Green: Comments
Light Blue: ET-PP inputs
Grey: ETO manager

## Slide 17: Column description
Deliverables (Document), Tier1 | Tier 2 | Tier 3 | Tier 4 | Tier 5 | Responsible | Comments | ET-PP Matching, Deliverables | Milestones | ETO manager
Main Deliverables. Documents. | Documents’ chapters. | Document paragraphs or Actions needed to provide the correct information in the document | Document paragraphs or Actions needed to provide the correct information in the document | Document paragraphs or Actions needed to provide the correct information in the document | Responsible for the task | Generic comments | ET PP project deliverables, connected with this task | ET pp project milestones, connected with this task | ETO responsible for this task

## Slide 18
1 |  |  |  |  | ETO organization in Phase I |  |  |  |  | tbd |  |  |  | 
1 | 1 |  |  |  |  | Define ET Research Infrastructure phases |  |  |  | F.Ferroni, A.Freise, R.Saban | Separate document |  |  | 
 |  |  |  |  |  |  | Coordinators validation? |  |  |  |  |  |  | 
1 | 2 |  |  |  |  | ETO mandate |  |  |  | S.Bentelvsen, A.Zoccoli | Existing document |  |  | 
1 | 3 |  |  |  |  | ETO Phase I Roadmap |  |  |  | A.Freise, F.Ferroni | Separate document |  |  | 
1 | 3 | 1 |  |  |  |  | Establish a common roadmap definition |  |  | A.Freise, F.Ferroni |  |  |  | 
1 | 3 | 2 |  |  |  |  | Interview ISB, OSB, EIB chairs EMR, TETI directors, Collaboration Spokes and vice spokesperson for TDR |  |  | A.Freise, F.Ferroni |  |  |  | 
1 | 4 |  |  |  |  | ETO strategy |  |  |  | tbd | Who is taking care of this? Integrated in another document? Is it necessary in phase 1? |  |  | 
1 | 4 | 1 |  |  |  |  | Establish a strategy for mandate execution |  |  |  |  |  |  | 
1 | 4 | 1 | 4 |  |  |  |  | Definition of the processes for verification and validation of the necessary documentation for the BGR, for all stakehoders |  |  |  |  |  | 
 |  |  |  |  |  |  |  | Strategy for the roadmap definition |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  | Strategy to implement a process for 2L and triangle comparison |  |  |  |  | 
 |  |  |  |  |  |  |  |  | Process to establish a cost estimate for the preparatory phase I. Define the correlation with the local Teams cost analysis. |  |  |  |  | 
1 | 4 | 1 |  |  |  |  |  | Definition and contents of the reports to the coordinators |  |  |  |  |  | 
EXAMPLE

## Slide 19
1 |  |  |  |  |  | ETO Public Affairs Strategy (incl. Communication - to be decided) |  |  |  |  |  |  |  | 
1 | 5 |  |  |  |  | ETO Organization in phase I |  |  |  | R.Saban, A.Variola | Separate document |  |  | 
 |  |  |  |  |  |  | ETO mission |  |  |  | Existing coordinators document |  |  | 
 |  |  |  |  |  |  | ETO Directorate mission |  |  |  |  |  |  | 
1 | 5 | 1 |  |  |  |  | Engineering Department mission |  |  | P.Werneke |  | D5.3 Structure and mandate of the Engineering Department |  | 
1 | 5 | 2 |  |  |  |  | Financial Department mission |  |  | Financial Manager / PD |  |  |  | 
1 | 5 | 3 |  |  |  |  | Project Office mission |  |  | A.Variola |  | D5.1 Structure and mandate of the Project Office |  | 
 |  |  |  |  |  |  |  | PM Tools |  |  |  | D 5.2 Functionalities required from the tools of the Project Management |  | 
1 | 5 | 4 |  |  |  |  | Communication Office mission |  |  | M.Oudenhoven/PD |  | D10.3 Formulate strategic media and communication plan |  | 
EXAMPLE 2

## Slide 20: Civil infrastructures
https://edms.cern.ch/document/3185053/1
Detailed inputs for the roadmap WBS (still to be included in the WBS table), broken down by classes that will ease their integration:
Standards and Formats for Site Studies
Technical Studies for Subsurface Assessment and Risk Analysis
Design and Construction Feasibility Assessment
Cost and Time Estimation
Environmental Impact Assessment, Permits, and Noise Mitigation Measures
Safety and Security Plan
Technical Infrastructure (Underground and Surface)

## Slide 21: What about ET(O) Roadmap?
The two exercises are obviously related. Also if in preliminary form many deliverables documents of ETO Phase 1 requires the definition of the project framework that will define the ET(O) roadmap. So regardless of the operational difficulties, we are defining different tools, analyzing supporting software, and working out procedures.
STARTING/ ONGOING:
PBS -> WBS
Risk assessment campaign
Scheduling tool
Document lifecycle framework
Nomenclature
Design and design task force
Preliminary CI TDR
Detector Layout
Vacuum TDR
System Engineering and MBSE
……………

## Slide 22: What to do next?
Fix the existing dates for milestones and turning points.
Trigger the discussion to fix the remaining ones.
Manage the stakeholders to identify and validate the list of responsible for the all the deliverables’ documents.
Finish the WBS with their contribution and validation.
From the WBS actions provide their duration and their correlations.
Build the schedule.
Check for consistency and coherence between deliverables, milestones and turning points.
Merge deliverables, milestones and turning points to build Phase 1 roadmap.
Have a stakeholders’ analysis to provide a roadmap validation process.
Validate the roadmap.

## Slide 23: And for ET(O)?
Many points are still unclear, undefined or not decided……
But we can build the ‘best project possible’ to manage and master the definition of technical schedule with milestones, deliverables and turning points.
For this we have to build a solid full lifecycle project WBS, and this is what we are starting to do. This should organize the activity of everybody…so this is not an abstract PM concept, but you are involved to make it better...
Lifecycle it means: Initialize (conception), Study (system definition), Design (technical definition), Build, Commission, Operate, Finalize.
From the WBS we can build the schedule, the organizational layers, the cost estimate etc etc. This will provide a first complete scenario of the roadmap (milestones, deliverables and turning points).
It is a ‘big science project’. We must provide the professional tools to manage these efforts and allow the roadmap definition.

## Slide 24: Conclusions
1) Two different Roadmap to be developed with different deadlines
2) ETO has been focused on phase 1.
3) Logic and methodology provided, documents
4) Phase 1 roadmap WBS in construction (mainly needs responsibilities attribution)
5) …but, due to the existing correlation, we are silently working also on the ET(O) roadmap. Preliminary stage.
6) We need everybody contribution….
Discussion