## Slide 1
Constraints for scheduling of REX beam times
SGUI 2011-07-07
F. Wenander and D. Voulot

## Slide 2
Beam setup tasks and time I
ISOLDE setup
- Separator setup (4 h) (ISO operator + FW)
- Basic target test (2-3 h) (ISO operator + FW)
what exact potential the ions are created at
strange beam shapes
beam composition, contaminations , pilot beam to use
scale separator to correct voltage
Day 0
Day 1
Day 2
Day 3
REX setup
- Find presetting with stable beam from EBIS through linac (2-4 h) (DV)
- Beam from ISOLDE separator (1-3 h) (operator / FW)
- Beam through trap (2-6 h) (FW)
standard 2 h, molecular and noble gases 4-6 h
- Pilot beam injection into EBIS and REX separator (2-3 h) (FW)
- Optionally continued linac tuning with stable beam into exp chamber (2-4 h) (DV)
- Determination of A/q, breeding times etc (2 h) (FW)
- Radioactive beam to users (2-3 h) (DV/FW)
depending on beam intensity and exp setup
- General checks and further optimization of beam steering to experimental setup (DV/FW)
In parallel
Spill over
(fuzzy factor 0.5-2)

## Slide 3
Beam setup tasks and time II
In addition squeeze in (Day 0 to 2)
Proton scan on target
Yield tests if required and requested (2-6 h) (target specialists)
RILIS laser tuning with ISOLDE (if applicable) (2 h) (RILIS experts)
* Maintained momentum is the key!
During actual run
Change of isotope 0.5 - 4 h (users, operators, DV/FW)
much depending on beam type, intensity, molecular
Change of energy 2-3 h (DV/FW)
Optimization and verifications (DV/FW)

## Slide 4
Other constraints
Later startup in the spring than the rest of ISOLDE
REX is competing for e.g. RF support with other machines such as Linac2 and Linac4
support for RF and vacuum is still on a good will basis, i.e. no piquet
  (technical problem can cost a lot of time)
- Miniball availability
- Earlier a limitation of 9 runs per year; stated by AB at the time
(only Thomas and Fredrik doing the operation)
- Still one specialist needed to be around – Didier or Fredrik
- Beam sharing of same separator is a nuisance
(different separator voltages, magnet calibrations etc)
Risky to deliver beam on Friday afternoon

## Slide 5
REX improvement list
1. more/better diagnostics = faster and easier set-up (mostly for linac)
-> energy/phase spread measurement after RFQ and directly behind the linac (TOF, Si detector)
-> calibrated beam profile/position monitors: improved MCP system and/or wire scanners
-> bunch length detector for slow extractions - 2011
-> ISOLDE tools for beam purity checks etc – under investigation
2. Improve vacuum in separator and linac injection region
-> might solve a lot of transmission/scaling problems
F. Zocca
3. Still suffer from unreliable not well tested or badly configured equipment
(e.g. collimators displaying wrong position, working-sets showing incorrect/misleading information, interlocks sending false alarms etc)
-> improve tools quality / pay attention to details (no ‘bricolage’)
-> written procedures, documentation?

## Slide 6
What to await from the future
+ REX getting easier – understanding increasing
+ Linac more or less scalable – speeds up things
+ Beam change by the users – tested successfully for the Pb run
(alternative to goodwill bases for weekend changes)
Dependent on CERN ‘standard’ solutions known by a single person
Setting up HIE-ISOLDE – hope that scaling will work correctly…
New cathode with improved life-time – limited progress, manpower clashes
? More beams scheduled already this year – outcome?
? WITCH and REX in co-operation
? Several beam times from one target – risk taking but saves time