## Slide 1: Collider Magnet Systems Cost Estimate
B. Caiffi2, A. Bersani2, S. Farinon2, S. Mariotto3 ,
D. Novelli1,2 , A. Pampaloni 2, T. Salmi4 , L. Bottura5, ...
1Sapienza University of Rome , 2INFN – Genoa , 3INFN – Milan , 4Tampere University , 5CERN

## Slide 2: Magnet requirements
Task 7.4 Collider Ring Magnets (INFN)
Courtesy of Patricia Borges de Sousa
https://indico.cern.ch/event/1250075/contributions/5357594/
Radial Build
4 cm Wabs @ T<10K (LTS) (P<5 W/m)
→ 158 mm magnet aperture
3 cm Wabs @ T=20K (HTS) (P<10 W/m)
→ 138 mm magnet aperture
138 mm
Courtesy of Anton Lechner
10 TeV collider
10 km ring

## Slide 3: Cost Model
Optimization of the cross section still ongoing.
Cost estimate performed on a simplified geometry with a sector coil dipole, iron and steel structure modelled as circular crowns.
R bore, wcoil, wiron and wstruct optimized to fulfill beam optics requirements, margin on the load line, acceptable stress on the conductor and effectiveness of the quench protection [ref])
(FCC-hh [ref])
(as LHC )
where
(D2 HL-LHC as benchmark)
(D2 HL-LHC as benchmark)
Material | 
Sn | 
aspirational value | 
aspirational value | 
Material | 
aspirational value | 
aspirational value | 
Escalated price in 2016
The right value in 2016
Corresponds to the ITER target
The value of today (2023)
A realistic projection for the next years
Bore
Coil
Structures
Iron

## Slide 4: Cost Estimate 10 TeV
Rbore= 70 mm
wcoil= 60 mm
wstruct= 30 mm
wiron= 300 mm
  14T /140 mm (REBCO)
€/kg iron | €/kg struct | €/kg conductor *
8 | 10 | 2500
  *50 €/kAm: 1/3 of today prize (150€/kAm)
  Also based on projection of ref
  A. Molodyk and C. Larbalestier, Science, 2023
Iron [Kg/m] | Structure [kg/m] | Coil [kg/m]
4560 | 213 | 130
Iron cost [k€/m] | Structure cost [ k€/m] | Coil cost [k€/m]
36 | 2.1 | 322
Tot. Material k€/m | 56 | 14%
Tot. Assembly k€/m | 20 | 5%
Tot. Conductor k€/m | 322 | 81%
Tot. Cost k€/m | 400 | 
Dipoles of the arc for the series production
(quadrupoles and IR not included)
TOTAL COST: 2.4 GEur (19.0% overall magnets budget)
100 k€/magnet ( 2FTE)
N units=1200, Length= 5m
Coordination, design and follow-up: 4 FTE x 4 years= 16 FTE-years (1.6 MEur)
Disclaimer: cryostat, specific tooling, W absorber not taken into account
fstruct = 1.5
Tot. Material = (Ciron+ Cstruct)*fstruct
Template geometrical parameter taken for cost estimate
Notes: J=3.5 10^8 A/m2

## Slide 5: A-B plots for Nb3Sn
Summary of cost assumptions:
We use the Nb3Sn aspirational cost 700 EUR/kg (from FCC)
  Today’s price is around 2500 EUR/kg
The starting budget of 400 kEUR/m is roughly double the estimate given by the FCC cost model for each magnet.
  In principle, we can assume a higher budget for each magnet than FCC because we have a smaller circumference and less magnets.
Cryogenic, protection and shielding costs are not taken into account.
Summary of magnet assumptions:
Single sector coil quadrupole
Maximum stress: 150 MPa
FCC design target cable for the Jc fit
Filling factor SC of 0.3
Protection with quench heater
Maximum coil width: 80 mm
Final Focusing: (v 0.8)
  8.1 T, 320 mm
  9.7 T, 320 mm
Arc: (v 0.7)
  16 T, 160 mm
  (140mm @ 20K)
Final Focusing: (v 0.8)
  85 T/m, 280 mm
  85 T/m, 266 mm
  115 T/m, 290 mm
  205 T/m, 204 mm
  242 T/m, 172 mm
  300 T/m, 140 mm
DIPOLES
QUADRUPOLES
The white area is the allowed design space where all constraints of the magnet are satisfied.
The limit curve is an ensemble of the many technological limitations taken into consideration to make the magnet design realistic [ref].
For the 10 TeV and 10 km collider, Nb3Sn falls short of required performance.
Nb3Sn not suitable technology for the 10 TeV collider
Notes: J=3.5 10^8 A/m2

## Slide 6: A-B plots for HTS dipole
Summary of cost assumptions:
We use the ReBCO’s aspirational cost 2500 EUR/kg
  Today’s price is around 8000 EUR/kg
The starting budget of 175 kEUR/m for each magnet is taken from the FCC cost model
  We can assume a higher budget than FCC because we have a smaller circumference and less magnets.
Cryogenic, protection and shielding costs are not taken into account.
Final Focusing: (v 0.8)
  8.1 T, 320 mm
  9.7 T, 320 mm
Arc: (v 0.7)
  16 T, 160 mm
  (140mm @ 20K)
Summary of assumptions:
Single sector coil dipole
Maximum stress: 400 MPa
Fujikura Tape for the Jc fit
Filling factor SC of 0.011
Non-insulated or Metal-insulated cable
Maximum coil width: 80 mm
Notes: J=3.5 10^8 A/m2

## Slide 7: A-B plots for HTS quadrupole
Summary of cost assumptions:
We use the ReBCO’s aspirational cost 2500 EUR/kg
  Today’s price is around 8000 EUR/kg
The starting budget of 175 kEUR/m for each magnet is taken from the FCC cost model
  We can assume a higher budget than FCC because we have a smaller circumference and less magnets.
Cryogenic, protection and shielding costs are not taken into account.
Summary of assumptions:
Single sector coil quadrupole
Maximum stress: 400 MPa
Fujikura Tape for the Jc fit
Filling factor SC of 0.011
Non-insulated or Metal-insulated cable
Maximum coil width: 80 mm
Final Focusing: (v 0.8)
  85 T/m, 280 mm
  85 T/m, 266 mm
  115 T/m, 290 mm
  205 T/m, 204 mm
  242 T/m, 172 mm
  300 T/m, 140 mm
Notes: J=3.5 10^8 A/m2

## Slide 8: Final Consideration
With a proper revision of the optics , 400 kEur/m can be considered a credible maximum budget for the ARC dipoles and quadrupoles ( assuming as baseline HTS @ 20 K).
For the IR magnets, a budget of 800 kEur/m must be taken into account, together with a lower working temperature (T<10 K), which can be estimated more accurately only when the revised optics will be available.
Notes: J=3.5 10^8 A/m2

## Slide 9
Thank you for your attention

## Slide 11: Cost Estimate (3TeV)
Rbore= 79 mm
wcoil= 80 mm
wstruct= 50 mm
wiron=350 mm
  11T /158 mm (Nb3Sn)
€/kg iron | €/kg struct | €/kg conductor *
8 | 10 | 700
* 7€/kAm, FCC target 5€/kAm
Iron [Kg/m] | Structure [kg/m] | Coil [kg/m]
6587 | 450 | 223
Iron cost [k€/m] | Structure cost [ k€/m] | Coil cost [k€/m]
53 | 4.5 | 156
Tot. Material k€/m | 84 | 30%
Tot. Assembly k€/m | 40 | 14%
Tot. Conductor k€/m | 156 | 56%
Tot. Cost k€/m | 280 | 
TOTAL COST: 6.7% O.M.B. (overall magnets budget)
200 k€/magnet ( 2FTE)
Dipoles of the arc for the series production
(quadrupoles and IR not included)
Coordination, design and follow-up: 4 FTE x 4 years= 16 FTE-years (1.6 MEur)
Disclaimer: cryostat, specific tooling (e.g. oven for thermal treatment of Nb3Sn) W absorber not taken into account
fstruct = 1.5
Tot. Material = (Ciron+ Cstruct)*fstruct
Notes: J= 3 e8

## Slide 12: Magnet requirements for Lattice
10TeV collider[ref] - preliminary
Final Focusing
ARC
Several magnet typology needed (dip, quad, combined, etc) , but optimization & definition of requirements still on going
Chromatic correction
Courtesy of Kyriakos Skoufaris

## Slide 13: Cost reduction learning curve
How to rescale for the other steps (pre-series, prototypes, short models, demonstrators)?
Learning curve
Wright's law
Applied to LHC magnets works perfectly! [ref]
b: learning percentage
b=0.8
 | 3 TeV |  | 10 TeV | 
 | N units (cumulative) | cost (A.U.*) | N units (cumulative) | cost (A.U.*)
demostrator | 1 | 3.36 | 1 | 7.13
short model | 11 | 1.55 | 11 | 3.29
proto | 16 | 1.38 | 16 | 2.92
pre series | 46 | 0.98 | 46 | 2.08
series | 246 | 0.57 | 446 | 1.00
*w.r.t. cost of 10 TeV series magnet

## Slide 14: Cost Estimate (3TeV)
Iron cost [k€/m] | Structure cost [ k€/m] | Coil cost [k€/m]
91 | 8 | 269
Tot. Material k€/m | 144 | 30%
Tot. Assembly k€/m | 69 | 14%
Tot. Conductor k€/m | 269 | 56%
Tot. Cost k€/m | 481 | 
Iron cost [k€/m] | Structure cost [ k€/m] | Coil cost [k€/m]
127 | 11 | 377
Tot. Material k€/m | 201 | 30%
Tot. Assembly k€/m | 96 | 14%
Tot. Conductor k€/m | 377 | 56%
Tot. Cost k€/m | 674 | 
Pre-series
Prototypes
Short Models
Demonstrators
Iron cost [k€/m] | Structure cost [ k€/m] | Coil cost [k€/m]
143 | 12 | 425
Tot. Material k€/m | 227 | 30%
Tot. Assembly k€/m | 109 | 14%
Tot. Conductor k€/m | 425 | 56%
Tot. Cost k€/m | 761 | 
Iron cost [k€/m] | Structure cost [ k€/m] | Coil cost [k€/m]
310 | 27 | 919
Tot. Material k€/m | 491 | 30%
Tot. Assembly k€/m | 235 | 14%
Tot. Conductor k€/m | 919 | 56%
Tot. Cost k€/m | 1645 | 
N units | length [m] | N years | cost FTE-y [k€] | Total cost [o.m.b*]
90 | 5 | 4 | 1600 | 1.70%
N units | length [m] | N years | cost FTE-y [k€] | Total cost [o.m.b*]
5 | 5 | 5 | 2000 | 0.15%
N units | length [m] | N years | cost FTE-y [k€] | Total cost [o.m.b*]
10 | 1.5 | 6 | 3000 | 0.11%
N units | length [m] | N years | cost FTE-y [k€] | Total cost [o.m.b*]
1 | 1.5 | 4 | 12000 | 0.03%
*overall magnets bugdet

## Slide 15: Cost Estimate (10TeV)
Iron cost [k€/m] | Structure cost [ k€/m] | Coil cost [k€/m]
75 | 4.3 | 633
Tot. Material k€/m | 116 | 15%
Tot. Assembly k€/m | 42 | 5%
Tot. Conductor k€/m | 632 | 80%
Tot. Cost k€/m | 790 | 
Iron cost [k€/m] | Structure cost [ k€/m] | Coil cost [k€/m]
105 | 6.1 | 888
Tot. Material k€/m | 163 | 15%
Tot. Assembly k€/m | 58 | 5%
Tot. Conductor k€/m | 888 | 80%
Tot. Cost k€/m | 1109 | 
Pre-series
Prototypes
Short Models
Demonstrators
Iron cost [k€/m] | Structure cost [ k€/m] | Coil cost [k€/m]
119 | 7 | 1000
Tot. Structure k€/m | 185 | 15%
Tot. Material k€/m | 183 | 15%
Tot. Assembly k€/m | 66 | 5%
Tot. Conductor k€/m | 1000 | 80%
Tot. Cost k€/m | 1250 | 
Iron cost [k€/m] | Structure cost [ k€/m] | Coil cost [k€/m]
257 | 15 | 2168
Tot. Material k€/m | 397 | 15%
Tot. Assembly k€/m | 143 | 5%
Tot. Conductor k€/m | 2168 | 80%
Tot. Cost k€/m | 2708 | 
N units | length [m] | N years | cost FTE-y [k€] | Total cost [o.m.b*]
90 | 5 | 4 | 1600 | 2.80%
N units | length [m] | N years | cost FTE-y [k€] | Total cost [o.m.b*]
5 | 5 | 5 | 2000 | 0.24%
N units | length [m] | N years | cost FTE-y [k€] | Total cost [o.m.b*]
10 | 1.5 | 8 | 4000 | 0.18%
N units | length [m] | N years | cost FTE-y [k€] | Total cost [o.m.b*]
1 | 1.5 | 6 | 24000 | 0.05%
*overall magnets bugdet

## Slide 16: Tentative Schedule (3 TeV collider)
Models |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Prototypes |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Pre-series |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Series |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040 | 2041
demonstrator (1)
models (10)
3x200 dipole
magnets
R&D and
demonstrators
  ARC DIPOLES 11T/158mm
  (quadrupoles and IR still not included)
+ 4 years
Models |  |  |  |  |  |  |  |  |  |  |  |  | 
Prototypes |  |  |  |  |  |  |  |  |  |  |  |  | 
Pre-series |  |  |  |  |  |  |  |  |  |  |  |  | 
Series |  |  |  |  |  |  |  |  |  |  |  |  | 
 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037
R&D and
demonstrators
demonstrator
models
full length prototypes
3x90 dipole magnets
3x200 dipole magnets
Aggressive time schedule, 13 years from R&D to end of construction
  Initial proposal
  Revised proposal
4 years (+1)
6 years (+ 1)
4 years (+ 1)
5 years (+ 1)
Nb3Sn demonstrator program 6 years
LHC: 13 short models in 11 years, 6 prototypes in 4 years, pre-series 4 years, series 4 years
3 years
5 years
4 years
3 years
4 years
4 years
17 years from R&D to end of construction
3x30 dipole magnets
full length prototypes (5)

## Slide 17: Tentative Schedule (10 TeV collider)
R&D and demonstrators |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Models |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Prototypes |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Pre-series |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Series |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040 | 2041 | 2042 | 2043 | 2044 | 2045 | 2046 | 2047 | 2048 | 2049 | 2050
Specifications and concept development
demonstrator model ( 1 per concept)
models (10)
full length prototypes (5)
3x30 dipole magnets
+3 years
  ARC DIPOLES 15T/138 mm
  (quadrupoles and IR still not included)
  Initial proposal
  Revised proposal
26 years from R&D to end of construction
3x400 dipole magnets
Models |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Prototypes |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Pre-series |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Series |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040 | 2041 | 2042 | 2043 | 2044 | 2045 | 2046 | 2047
Specifications and concept development
R&D and demonstrators
23 years from R&D to end of construction
demonstrator
models
full length prototypes
3x30 dipole magnets
3x400 dipole magnets
3 years
5 years
7 years
3 years
5 years
6 years
4 years (+1)
6 years (+1)
8 years (+1)
4 years (+1)
4 years (-1)
5 years (-1)
More emphasis on demonstrator and short model phase (REBCO or hybrid solutions still to be studied)

## Slide 18: Tentative Schedule (3 TeV collider)
Models |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Prototypes |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Pre-series |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Series |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040 | 2041
R&D and
demonstrators
  ARC DIPOLES 11T/150mm
  (quadrupoles and IR still not included)
4 FTE/y, 0.08 ‰ o.m.b.*
5 FTE/y, 0.19‰ o.m.b.*
4 FTE/y, 0.30‰o.m.b.*
4 FTE/y,16.6 ‰ o.m.b.*
4 FTE/y, 4.31 ‰ o.m.b.*
4 years
6 years
4 years
5 years
4 years
TOTAL: 8.67% o.m.b.*
*overall magnets bugdet

## Slide 19: Tentative Schedule (10 TeV collider)
R&D and demonstrators |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Models |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Prototypes |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Pre-series |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Series |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040 | 2041 | 2042 | 2043 | 2044 | 2045 | 2046 | 2047 | 2048 | 2049 | 2050
Specifications and concept development
  ARC DIPOLES 15T/150 mm
  (quadrupoles and IR still not included)
4 years
6 years
8 years
4 years
4 years
5 years
2 FTE/y, 0.016‰ o.m.b.*
4 FTE/y, 0.09‰ o.m.b.*
5 FTE/y, 0.22‰ o.m.b.*
4 FTE/y, 0.47‰ o.m.b.*
4 FTE/y, 7.06‰ o.m.b.*
4 FTE/y, 47.5‰ o.m.b.*
TOTAL: 22.3% o.m.b.*
*overall magnets bugdet

## Slide 20: Cost Profile
8
0.8
0.08
0.008
*overall magnets bugdet