## Slide 1
Relocation and shielding activities
2011 TS and Xmas break 2011-2012
R2E project meeting, 21rst July 2011
A. L. Perrot

## Slide 2
Activities performed/foreseen during the 2011 TS
Already done
Survey: scans in Point 5 bypass, Pt1(UL14/6)
Point 8: EL cabling activities,
empty racks installation for IT,
preparatory work for the remote reset rack relocation (EL and IT)
Foreseen
Survey: Scans of Pt 7 (TZ76),
Pt 8 (UJ84/UL84/US85/UL86/UJ86)
Pt 4 (UJ44/UL44/US45/UL46/UJ46)
Point 1
cable displacement in view of RB shielding installation
reinforce the floor in the RB (civil engineering team)
Points 5/7
CE visits with firm to prepare future activities (wall dismantling in TZ76, drilling activities in UJ56, bypass)
Point 8
pipes installation in view of fibers installation
ventilation control cabinet relocation from UJ87 to UA87? to be discussed with CV
functionality test of new cables for QURCB by cryo team (under progress)

## Slide 3
Activities foreseen for the Christmas break 2011-2012
Point 1
fire detection relocation to ULs
shielding installation in RBs/UJs
preparatory work by EL (cable trays in the ULs- except those for water cooled cables)
Point 5
fire detection displacement of the pipes in the by-pass, start pipes installation between RR and UJ -> under consideration; discussion with GS/ASE and integration in September
GGPSO installation in bypass
Civil engineering: drilling the 5 or 7 holes in the separating wall (‘mur tympan’)
Point 8
Cryogenics:
- QURCB relocation: under consideration (decision at the end of the new cables tests)
- QURA relocation: under consideration (seems feasible; to be confirmed during Xmas break)
- EYQ01 rack relocation (24VDC distribution rack)
All points
Floor reference points to be installed -> under consideration; discussion with integration and survey in September