## Slide 1: YETS EA Plannings
Bastien Rae

## Slide 2: East Area
Task Name | Duration | Start | Finish | Groups
Stop run physic 2024 (T09-T10-T11) | 0 days | Wed 27.11.24 | Wed 27.11.24 | BE-EA,BE-OP
Maintenance water tower b.355 | 24 days | Tue 10.12.24 | Fri 24.01.25 | EN-CV
Restart Skid | 2 days | Fri 24.01.25 | Mon 27.01.25 | EN-CV
Restart HVAC EA1&EA2 | 0 days | Wed 26.02.25 | Wed 26.02.25 | EN-CV
Switch EA1&EA2 from General to Restricted access | 0 days | Fri 28.02.25 | Fri 28.02.25 | BE-OP,EN-AA
DSO Tests EA1&EA2 (no access the morning) | 4 hrs | Mon 03.03.25 | Mon 03.03.25 | BE-EA,BE-OP,DSO,EN-AA,EN-CV
EA1 & EA2 Beam Permit Sign and zones closed | 0 days | Fri 07.03.25 | Fri 07.03.25 | BE-EA,BE-OP
DSO Tests secondary beam lines (no access the morning) | 4 hrs | Mon 10.03.25 | Mon 10.03.25 | BE-EA,DSO,EN-AA
Hardware commissioning b.352 | 4 days | Wed 12.02.25 | Mon 17.02.25 | 
PS Closure for tests | 0 edays | Sat 22.02.25 | Sat 22.02.25 | EN-ACE
PS ring Hardware commissioning | 6 days | Mon 24.02.25 | Mon 03.03.25 | BE-OP
PS Beam commissioning | 9 days | Fri 07.03.25 | Wed 19.03.25 | BE-OP
Hardware Commissioning 157 | 5 days | Mon 03.03.25 | Fri 07.03.25 | BE-EA
Beam Extraction to F6D + Targets | 4 edays | Fri 07.03.25 | Tue 11.03.25 | BE-OP
T8 & EA Beam + Instrumentations Commissioning | 5 days | Tue 11.03.25 | Mon 17.03.25 | BE-EA,BE-OP,SY-BI
Close T11 Shutter after Beam commissioning (access EA1) | 0.1 hrs | Tue 18.03.25 | Tue 18.03.25 | BE-EA
Users Installation | 1 day | Tue 18.03.25 | Tue 18.03.25 | BE-EA
Start East Area physics 2025 | 0 days | Wed 19.03.25 | Wed 19.03.25 | BE-EA

## Slide 3: North Area (1/2)
Task Name | Duration | Start | Finish | Groups
NA run 2024 | 164 days | Wed 10.04.24 | Fri 29.11.24 | 
Magnet patrol TT81, TT82, EHN1, EHN2, ECN3 239339: magnet on, restricted access | 2 days | Mon 02.12.24 | Tue 03.12.24 | EN-CV,TE-MSC
Magnet patrol TT83, TT84, TT85, TCC8: magnet on, restricted access | 2 days | Wed 04.12.24 | Thu 05.12.24 | EN-CV,TE-MSC
Magnet leak Inspection all zones (inc TCC2 ) | 2 days | Mon 02.12.24 | Tue 03.12.24 | BE-EA,EN-CV,TE-MSC
Testing BIDs | 5 days | Mon 02.12.24 | Fri 06.12.24 | BE-EA
Diagnostic des câble boucle pulsé + stable | 5 days | Mon 10.02.25 | Fri 14.02.25 | EN-EL
ED cooling stations maintenance BA80, BA81 & BA82 / EB BA81 | 4 wks | Mon 03.02.25 | Fri 28.02.25 | EN-CV
Test normal secours - 06h00-06h10 (No access all zones) | 1 day | Wed 08.01.25 | Wed 08.01.25 | EN-EL
Eau glacee BA81 Stop | 12 wks | Fri 06.12.24 | Thu 13.03.25 | EN-CV
Eau Mixte BA82 Stop | 10.4 wks | Fri 06.12.24 | Mon 03.03.25 | EN-CV
North Area Test HV Cable | 5 days | Wed 22.01.25 | Tue 28.01.25 | EN-EL
Test AUG North Area (No access all zones) | 3 days | Wed 15.01.25 | Fri 17.01.25 | EN-EL
ED cooling start BA80 | 0 days | Fri 14.02.25 | Fri 14.02.25 | EN-CV
ED cooling start BA81 | 0 days | Mon 24.02.25 | Mon 24.02.25 | EN-CV
ED cooling start BA82 | 0 days | Mon 03.03.25 | Mon 03.03.25 | EN-CV
Inspection Fuite Aimant BA80 | 1 day | Fri 14.02.25 | Fri 14.02.25 | TE-MSC
Inspection Fuite Aimant BA81 | 5 days | Mon 24.02.25 | Fri 28.02.25 | TE-MSC
Inspection Fuite Aimant BA82 | 5 days | Mon 03.03.25 | Fri 07.03.25 | TE-MSC
BA81 - IST access system (no Access ) | 2 days | Wed 19.02.25 | Thu 20.02.25 | EN-AA
BA80 - IST access system (no Access ) | 1 day | Thu 20.02.25 | Thu 20.02.25 | EN-AA
TCC8 - ECN3 - IST access system (no Access ) | 1 day | Fri 21.02.25 | Fri 21.02.25 | EN-AA
TCC2 + TCC8 Ventilation interlock Test | 1 day | Mon 18.11.24 | Mon 18.11.24 | DSO

## Slide 4: North Area(2/2)
Task Name | Duration | Start | Finish | Groups
HW Commissioning | 34 days | Mon 17.02.25 | Thu 03.04.25 | 
Test alim BA80 | 2 wks | Mon 17.02.25 | Fri 28.02.25 | SY-EPC
Test alim BA81 | 2 wks | Mon 03.03.25 | Fri 14.03.25 | SY-EPC
Test alim BA82 | 1 wk | Mon 10.03.25 | Fri 14.03.25 | SY-EPC
North Transfert Tests | 19 days | Mon 03.03.25 | Thu 27.03.25 | 
Test Magnets BA80 (EIS completed for 15/03) | 2 wks | Mon 03.03.25 | Fri 14.03.25 | TE-MSC
Test Magnets BA81 | 9 days | Mon 17.03.25 | Thu 27.03.25 | TE-MSC
Test Magnets BA82 | 4 days | Fri 21.03.25 | Wed 26.03.25 | TE-MSC
TCC2 + BA81 HWC | 5 days | Mon 17.03.25 | Fri 21.03.25 | BE-EA
HWC rest of NA | 5 days | Fri 28.03.25 | Thu 03.04.25 | BE-EA
DSO Tests | 17.5 days | Fri 28.02.25 | Tue 25.03.25 | 
DSO tests SPS + BA80 + BA81 (North Transfert) No Access | 1 day | Tue 11.03.25 | Tue 11.03.25 | BE-ASR
DSO tests TCC8 -ECN3 no access | 0.5 days | Mon 24.03.25 | Mon 24.03.25 | BE-ASR
DSO tests EHN1 + EHN2 (BA82) no access | 1 day | Mon 24.03.25 | Tue 25.03.25 | BE-ASR
BA80 (TCC2/TDC2) Closed | 0 days | Fri 14.03.25 | Fri 14.03.25 | 
RP Cleaning TDC2 TCC2 (BA80 closed) | 5 days | Mon 17.03.25 | Fri 21.03.25 | HSE-RP
Resart Date | 128 days | Fri 28.03.25 | Wed 01.10.25 | 
Beam Commissioning | 0 days | Fri 28.03.25 | Fri 28.03.25 | BE-OP
BA81 (TT81+TT82+TT83+TT84+TT85) Closed | 0 wks | Fri 28.03.25 | Fri 28.03.25 | BE-OP
TCC8-ECN3 closed | 0 days | Thu 03.04.25 | Thu 03.04.25 | BE-OP
SPS TT20 Beam Commissioning | 5 days | Fri 28.03.25 | Thu 03.04.25 | BE-OP
SY-BI Equipment Commissioning with beam | 10 days | Fri 04.04.25 | Thu 17.04.25 | SY-BI
NA setup | 9 days | Fri 04.04.25 | Wed 16.04.25 | BE-OP
EHN1 physique | 114 days | Mon 14.04.25 | Fri 26.09.25 | BE-OP
EHN2 + ECN3 physique | 114 days | Thu 17.04.25 | Wed 01.10.25 | BE-OP

## Slide 5: No Access by Zones
All North Area
  Tests Normal Secours (6h-6h30)  08.01.25
  AUG Test  15.01.25 and 17.01.25 (limited access on the 16.01.25)
BA80 (TCC2)
  Maintenance access system  20.02.25
  DSO test 11.03.25 + 24.03.25-25.03.25
  CLOSURE  14.03.25

## Slide 6: No Access by Zones
BA81 (TT81, TT82, TT83, TT84, TT85)
  Maintenance access system  19.02.25
  DSO test 11.03.25 + 24.03.25-25.03.25
  CLOSURE  28.03.25
EHN1 + EHN2
  DSO test : 24.03.25 – 25.03.25  depending on the progress
  CLOSURE  04.04.25
TCC8 + ECN3
  Maintenance access system  21.02.25
  DSO test  24.03.25
  CLOSURE  04.04.25

## Slide 7
Experimental Areas Planning Gantt view