## Deinstallation
DSL Translation Steps - Deinstallation Phase | [5 empty] | Order of work taken from here:
Step No. | DSL Movement | Deinstallation/reinstallation steps | Catia Product | Reference Document | Prepatory Steps | https://oss-coordination.web.cern.ch/gantt/latest?baselines=false&dependencies=false&facilities=LHC%2CHL-LHC%2CMaster%20Schedules&forecast=false&groups=&includeArchived=false&locations=&potentialConstraints=false&scale=week&summary=false&worktypeproject=
1 | LS2 YETS22-23 state | N/A | ST1A00092_01
2 | N/A | Beam pipe and beam equipment removed. | ST1A00118_01
3 | Installation of DSL Support | N/A | ST1A01480_01
4 | Disconnection DSL from Magnet | N/A | N/A | EDMS 3230491
5 | DSL disconnected from magnets | D2/Q4 and Q5 removed | ST1A01560_01
6 | Cap exposed ends of DSL connections | N/A | N/A | To be completed
7 | Cut and remove 12.3m section of DSL | N/A | ST1A01711_01 | To be completed
8 | Cap and protect exposed ends of DSL | N/A | N/A | To be completed
9 | Install DSL protection | N/A | ST1A01718_01 | To be completed | Detail design and fabrication of protection. Test with mock DSL branch.
10 | Remove Helium Ring line | Removal of Helium ring line (HRL) Remove compressed air lines Removed up to 212000mm from IP (P5R) - 1m from DSL and QRL cut | ST1A01737_01
11 | Install DSL Rotation Tooling | Options: A) Remove cable trays on ceiling to allow QRL hoist to be fixed to ceiling B) Use cable tray fixings to attach hoist. C) bolt girder to roof with wheels to allow hoisting and translation of DSL in single step (girder would have to be brought in pieces and welded in tunnel). DSL support tables removed. DSL rotation tooling fixed to DSL protection and hoists on roof. | ST1A01954_01 | Design and procedure to be completed | Design of tooling.
12 | Rotate DSL 65 degrees |  | ST1A02581_01 | To be completed | Test with mock DSL branch.
13 | Remove Recovery Line | Removed up to 212000mm from IP (P5R) - 1m from DSL and QRL cut | ST1A02732_01
14 | Cut and remove QRL Interconnections | QRL Interconnections to be cut and removed including internal process pipes | ST1A02792_01 | EDMS 2718015:QRL dismantling functional spec | EN-MME developing tooling.
15 | Remove QRL Pipe Elements | QRL Pipe elements removed during night shift after IC cut. | ST1A02833_01 | EDMS 2874410: EN-HE elements deinstallation database | Method to be defined
16 | Remove Service Modules | QRL Service Modules removed during nght shift | ST1A02850_01 | EDMS 2874410: EN-HE elements deinstallation database | Method to be defined
17 | Rotate DSL down to give access to ancillary services and CV. | Supporting tables for DSL may be put back in position to support DSL and provide working platform **Alternative to remove all ancillary and CV from Q5 to Q6, then translate DSL to allow access to wiring and piping between Q4 and Q5** | ST1A02919_01 | Procedure to be defined
18 | Remove ancillary services and CV from Q4 to Q6. | Assumed services and CV removed up to 22500mm from IP at P5R as per mail from N. Joannan. To be confirmed on 12/02 in DSL co-ordination meeting. | ST1A02992_01 | Design and procedure to be completed
19 | Translate DSL to new position. | Options: A) Use girder and hoist installed in Step 11. B) Use monorail C) Use mobile hoisting system such as engine hoists to lift and slide DSL. Winch fixed to end of DSL pipe to pull it longitudally into position in controlled fashion. | ST1A03029_01 | To be completed | Test to be completed
20 | Rotate DSL for reinstallation. DEINSTALLTION COMPLETE | **Alternative to leave DSL unrotated to allow initial installation of power services** | ST1A03033_01 | Procedure to be defined
21
22
23
24
25
26
27
28

## Reinstallation
DSL Translation Steps - Installation Phase | [6 empty] | Order of work taken from here:
Step No. | Step No. | DSL Movement | Deinstallation/reinstallation steps | Catia Product | Reference Document | Prepatory Steps | https://oss-coordination.web.cern.ch/gantt/latest?baselines=false&dependencies=false&facilities=LHC%2CHL-LHC%2CMaster%20Schedules&forecast=false&groups=&includeArchived=false&locations=&potentialConstraints=false&scale=week&summary=false&worktypeproject=
Final-10 | 1 | DSL Starting Position after Civil Works | N/A | ST1A03821_01
Final-9 | 2 | DSL rotated down. DSL supports installed. | Installation of: - General Services - EN/CV systems - HL-LHC cables - HLS/WPS Pipe - PSS - Monorail | ST1A03815_01 |  | Study of clashes may be needed but not anticipated from model
Final-8 | 3 | N/A | Helium ring line installed excluding section between Q4 and Q5 Due to clash of HRL with roated DSL. Approximately installed up to 185000mm from IP and then section from 203000mm to Q6 | ST1A03794_01 |  | Study to see if WRL can be installed entirely at this step with change to the design of the DSL protection.
Final-7 | 4 | DSL Rotated up 75 degrees and WRL installed | Warm Recovery Line Installation DSL support stands removed | ST1A03785_01 |  | Study: Clash with preliminary DSL protection design - to be refined to avoid clash WRL support under Q4 may require to be moved 2m toward ARC or IP
Final-6 | 5 | N/A | QXL Installation The cable tray along the QXL installed at this point. 70 Degree rotation required to clear valve assemblies | ST1A03774_01 | Reference document required
Final-5 | 6 | DSL Rotated down and Tooling Removed | Tooling removed after DSL rotation Supporting tables for DSL connected placed | ST1A03736_01 | Procedure to be defined
Final-4 | 7 | DSL Protection Removed | N/A | ST1A03718_01
Final-3 | 8 | HRL between Q4 and Q5 installed | Install section of Helium Ring Line between Q4 and Q5 | ST1A03689_01 | Procedure to be defined
Final-2 | 9 | DSL Splice box connected | N/A | ST1A03602_01 | Procedure to be defined | Splice box design to be completed. Assess space constraints with adjacent piping for welding operation
Final-1 | 10 | Magnets connected | Magnets installed ->Magnet aligned DSL Connected QXL/QRL to magnet connections Magnet access platforms | ST1A03581_01 | Updated procedure to be defined. Previous connection procedures here: https://lhc-div-mms.web.cern.ch/Interconnect/Long%20Straight%20Section/
Final | 11 | Final Installed State | Beamline Components connected Ancillary Services installed. | ST1A03569_01