## Slide 1: HI-ECN3 project - WP5 Experimental Area, Experiment Interface & Integration
F. Butin BE-EA

## Slide 2: WP5 proposed structure
Sub WPs | Objects
WP 5.1 - F. Butin – Grad 2 | Technical coordination of the Experimental Area, interface with experiment and accelerator
WP 5.2 - S. Girod / B. Martinez | Design, engineering and Overall 3d integration of the experimental area and related technical infrastructure
WP 5.3 - M. Lazzaroni / Grad 2 | Shielding procurement organization and existing shielding recovery
WP 5.4 - F. Butin / Grad 2 | Supervision and coordination for dismantling of the existing ATS equipment and installation of the new technical infrastructure
WP 5.5 – D. Mergelkuhl | Supervision and coordination for dismantling of the existing ATS equipment and installation of the new technical infrastructure
WP 5.6 – C. Bertone, R. Rinaldesi | Transport - handling

## Slide 3: WP 5.1: Technical coordination of the Experimental Area, interface with experiment and accelerator
Objective: ensure the overall coherence of adaptation of experimental area to the new experiment project -> close contact with the experiment technical coordination
Sub WP 5.1.1: Definition of infrastructure requirements for the experiment, including functional specification of Access structures, Cooling and Ventilation, Specialized transport , Access safety systems, power distribution and signal networks, Vacuum, Cryogenics, Gas distribution systems, IT and controls networks, Power supplies
Sub WP 5.1.2: Definition of interfaces with the accelerator and experiment
Sub WP 5.1.3: Overall master planning of the experimental area, budget control and report to management

## Slide 4: WP 5.2: Design and engineering of the experimental area and 3d integration of the related technical infrastructure
Objective: perform design and engineering of the experimental area ensuring its adequacy and consistency collect all 3d models produced by CERN groups and detectors elements alike to produce an integrated 3d structure. Ensure consistency, respect of the envelopes, and respect of the operability/safety constraints.
Integration of existing and new civil engineering infrastructure, (trenches, pits, galleries etc) with models provided by SCE-SAM
Integration of access structures (lifts, stairs, gangways), including design and procurement in collaboration with EN-MME when needed
Integration of access safety systems, as defined in collaboration with EN-AA
Integration of Experiments 3d models, with models provided by EP

## Slide 5: WP 5.2 continued
Integration of the Proton Beam line up to the target, including optics, instrumentation, and vacuum systems in collaboration with TE-VSC
Integration of the Target station models provided by EN-STI, including shielding
Integration of Handling means and transport corridors
Integration of Electrical services (DC + AC cable trays, optical fibres gulleys), outside of the experiments volume
Integration of Cooling systems: cooling squid and piping, compressed air distribution up to experiment interface
Integration of HVAC systems and ducts, including partition walls with models provided by EN-CV
Integration of gas pipes and distribution systems in collaboration with BE-EA-EC
Integration of RP monitoring systems, as defined in collaboration with HSE-RP

## Slide 6: WP5.3 Shielding procurement organization and existing shielding recovery
Objective: Organization of shielding procurement, assist WP4 for new shielding to be bought, organize recovery of existing unused shielding
Sub WP 5.3.1: TT7 shielding recovery Civil engineering works
Sub WP 5.3.2: Shielding Specific transport activities
Sub WP 5.3.3: Refurbishment and logistics of the recovered shielding elements
Sub WP 5.3.4: Missing shielding procurement. This corresponds to BE-EA-DC activity for procuring the missing shielding elements, the budget corresponding to the missing shielding blocks proper is included in WP4 (Target complex)

## Slide 7: WP 5.4: Supervision and coordination: Dismantling of the obsolete equipment and infrastructure, installation of the required new technical infrastructure
Objective: the preparation / supervision / coordination work for the execution of the on-site activities required to adapt the existing experimental area for the new project, except the civil engineering part.
Work site management and supervision for all works (including WSS) related to the experimental area, in close link with BE-DSO, EP-DSO, EX-SO and TSO, with service groups and the experiment technical coordination.
Ensure the good preparation, sequencing and compatibility of on-site activities, the work site safety conditions, and monitor the conformity of the execution.

## Slide 8: WP 5.4 Continued
Sub WP 5.4.1 : Removal of the K12 beam line elements, downstream of QNL_X1010046 - coordination with NA62 experiment dismantling – supervision and direct costs of the activities are included
Sub WP 5.4.2 : Removal of the obsolete infrastructure elements (mainly decabling, but also cooling, HVAC, gas pipes, alarms, access safety, RP) – supervision and direct costs of the activities are included.
Sub WP 5.4.3: Installation of the new experimental area infrastructure – only work site coordination and supervision costs are included. The resources and budgets corresponding to the study, procurement and installation of the technical infrastructure items, are part of WP7 (F. Pedrosa).

## Slide 9: WP 5.5 : Definition and implementation of survey and alignment systems
Objective: definition, preparation, purchase, installation and operation of the survey/alignment activities required to install the new experimental area, beam delivery system and the new experiment (separate budget).

## Slide 10: Meetings - interfaces
WP5 coordination meetings
(Chair F. Butin)
All concerned service groups
Exp coordination
ICEA meetings
(Chair F. Butin, J-L. Grenard
M. Lazzaroni)
HI ECN3
Project Team meetings
(Chair M. Frazer)
Experiment TC meetings (Chair: Exp TC)
WP 2
WP 3
WP 4
WP 6
WP 7
WP 1