## CMS
FSU | Cable connection point | System | Detector | Time needed [weeks] | Overall time [weeks] | ATLAS activity overlap | Proposed start date | End of activity
Julien [EP-DT-FS] | Cabinets | Plant | TK1 | 0.5 | 20.5 | 6 | 2024-01-06 | 2024-09-20 | 0.5 week per cabinets which cables connection has been started, but not ended yet
|  |  | TK2 | 0.5
|  |  | BTL | 0.5
|  |  | CE1 | 0.5
|  |  | CE2 | 0.5
|  |  | CE3 | 0.5
|  |  | CE4 | 0.5
|  |  | ETL | 0.5
|  |  | Plant 9 | 0.5
|  | Manifold | TK1 | 2
|  |  | TK2 | 2
|  |  | BTL | 1
|  |  | CE1 | 1
|  |  | CE2 | 1
|  |  | CE3 | 1
|  |  | CE4 | 1
|  |  | ETL | 2
| DEMO Inheritance |  |  | 5
Additional FSU (50%) | Skids | Plant | TK1 | 1 | 8 | 6 | 2024-01-06 | 2024-07-10
|  |  | TK2 | 1
|  |  | BTL | 1
|  |  | CE1 | 1
|  |  | CE2 | 1
|  |  | CE3 | 1
|  |  | CE4 | 1
|  |  | ETL | 1
|  |  | Plant 9 | DONE
Additional FSU (50%) |  | Accu | TK1 | 1 | 8 | 6 | 2024-01-06 | 2024-07-10
|  |  | TK2 | 1
|  |  | BTL | 1
|  |  | CE1 | 1
|  |  | CE2 | 1
|  |  | CE3 | 1
|  |  | CE4 | 1
|  |  | ETL | 1
Marc [EP-DT-DI] |  | Manifold | TK1 | 2 | 17 | NOT FORESEEN | 2024-01-06 | 2024-06-20
|  |  | TK2 | 2
|  |  | BTL | 1
|  |  | CE1 | 1
|  |  | CE2 | 1
|  |  | CE3 | 1
|  |  | CE4 | 1
|  |  | ETL | 2
| Cabinets | Accu | TK1 | 1
|  |  | TK2 | 1
|  |  | BTL | 1
|  |  | CE1 | 0.5
|  |  | CE2 | 0.5
|  |  | CE3 | 0.5
|  |  | CE4 | 0.5
|  |  | ETL | 1
Formulas:
End of activity = WORKDAY([Proposed start date],7*([Overall time [weeks]]+[ATLAS activity overlap]))
End of activity = WORKDAY([Proposed start date],7*(2*[Overall time [weeks]]+[ATLAS activity overlap]/2))