## Slide 2: An introduction to the HI-ECN3 project
BDF Target Advisory Committee #1
M. Fraser (SY-ABT-BTP) and C. Ahdida (HSE-RP-AS) on behalf of the HI-ECN3 project team
CERN, Geneva, Switzerland, 4 - 6th March 2025
https://hiecn3.web.cern.ch

## Slide 3
A brief history of BDF/SHiP…
2013: EOI with SHiP @ SPS North Area in a new underground area (ECN4)
2015: Technical Proposal with ~700 pages by SHiP theorists, experimentalists, and CERN accelerator, engineering, and safety departments
2016: Recommendation by SPSC to proceed to Comprehensive Design Study and CERN management launch of Beyond Collider Physics study group
2018: European Particle Physics Strategy Update contribution submitted by SHiP and BDF
2019: CDS reports on BDF and SHiP at ECN4 submitted to SPSC
2020: CERN launches continued BDF R&D with SHiP MoU
2021: BDF/SHiP WG identified ECN3 as post-LS3 option: motivated PBC ECN3 Task Force
2023: HI-ECN3 Study Project established
2024: CERN Directorate select SHiP in March 2024 with approval of HI-ECN3 Project
BDF/SHiP in ECN3

## Slide 4
P42 Beam Dump
EHN1
EHN2
ECN3
BA82
BA81
BA80
P42 Beam Line
TCC8
TT20 Beam Lines
TCC2
inc. T4
SPS LSS2
TT20 Beam Dump (TED)
ECN3 Bridge over River Lion
BDF/SHiP in ECN3
TCC8
B918
B911
Beam Dilution System + several changes in P42 beamline
New Target
Service Building
ECN3
Beam from SPS
BDF’s Target Complex
containing a high-Z target (W)
New
Access Shaft
(material only) 8x8 m2
Existing
Access Shaft
48 m2
Magnetised Hadron Stopper
iron shielding magnetised by a coil
Muon Shield
chain of SC/NC magnets
Spectrometer Magnet
Decay Vessel

## Slide 5
BDF Design Parameters
Nominal Design Parameter | Value
Beam type | proton
Beam momentum [GeV/c] | 400
Beam pulse intensity [1013 p] | 4.0
Spill length [s] | 1
Beam pulse power [kW] | 2560
Average beam power [kW] (7.2 s) | 356
POT [1020 p over 15 years] | 6.0
Nominal Design Parameter | Value
Beam type | proton
Beam momentum [GeV/c] | 400
 | 4.0
Spill length [s] | 1
Beam pulse power [kW] | 2560
Average beam power [kW] (7.2 s) | 356
 | 6.0
Beam size = 8 mm (𝝈)
Dilution freq. = 4 Hz
Sweep rad. = 50 mm
SFTSHiP
To ECN3
SFTPRO
To TCC2 (EHN1 / EHN2)
356 kW
232 kW
Beam power
on BDF target
7.2 s
15.6 s
W target ~ 1500 – 2000 mm
Diameter ~ 250 mm
H2O or He-cooled
Target
Vacuum Containment Vessel
Magnetised Hadron Stopper
Target Complex
Shielding Bunker
Excavated floor with
reinforced shielding

## Slide 6
Study Project Approved Project
Upgrade of beam intensity at North Area and SHiP beam-dump (BDF/SHiP) experiment approved recently…
… with ~ 62 MCHF (over 7 years) reserved for the High Intensity upgrade of ECN3 (HI-ECN3) project in CERN’s Medium-Term Plan ratified by CERN Council in June 2024.
Approved together with ~ 170 MCHF for consolidation of the North Area (NA-CONS project)
The HI-ECN3 project is a part of CERN’s…
“…broad diverse scientific programme, complementary to the collider and carried out mainly at the injectors: continuously upgraded and expanded (e.g. recently the ECN3 beam intensity upgrade at the North Area).”
Fabiola Gianotti

## Slide 7
Francesco VELOTTI & Laurie NEVAY
Rui FRANQUEIRA XIMENES
Jean-Louis GRENARD
Francois BUTIN
Claudia AHIDIDA
Project Safety Officer (PSO): Melania AVERNA
Project & Experiment Safety Support (PESS) Correspondent: Jamie CURRIE
Fernando PEDROSA
Luigi ESPOSITO
Experiment Project Leader: Richard JACOBSSON
SHiP Experiment Safety Correspondent: Letizia DI GIULIO
PL: Matthew FRASER
DPL: Claudia AHDIDA
HI-ECN3 Project Structure

## Slide 8
HI-ECN3 Work Breakdown Structure
DRAFT

## Slide 9
HI-ECN3 TDR GRAD Team
Person | Role | Group | Supervisor | Programme | BC Description | PRQ | Start Date
Ixone VAQUERO | Planning & Coordination | EN-ACE | Fernando PEDROSA | ORIGIN | HI-ECN3 / NA-CONS | Completed | 1/10/2023
Xavier PALLE | Planning & Coordination | EN-ACE | Fernando PEDROSA | ORIGIN | HI-ECN3 / NA-CONS | Completed | 1/3/2024
James CURRIE | TDR | HSE-OHS | Simon MARSH | ORIGIN | HI-ECN3 | Completed | 1/2/2024
Rahul JANARDHAN | FIRIA | HSE-OHS | Oriol RIOS | QUEST | HI-ECN3 / HSE | Completed | 1/9/2024
Guillaume CNUDDE | TDR (& implementation) | SCE-PPM | David GOMEZ | QUEST | HI-ECN3 | Completed | 1/10/2024
Nikola ZARIC | TDR | EN-CV | Roberto BOZZI | QUEST | HI-ECN3 | Completed | 1/2/2024
Angelo PETRELLESE | Secondary Vacuum | BE-EA | Miguel SANTOS | ORIGIN | HI-ECN3 / NA-CONS / PBC | Completed | 1/4/2024
Fabian METZGER | TDR | BE-EA | Laurence NEVAY | GRAF | HI-ECN3 | Completed | 1/4/2024
TBC | TDR / LS3 prep | BE-EA | Francois BUTIN | ORIGIN | HI-ECN3 | Pre-LS3 | Q3 2026
Beatriz MARTINEZ SUTIL | TDR | BE-EA | Michael LAZZARONI | ORIGIN | HI-ECN3 | Completed | 2/5/2024
Ming LIU | TDR | EN-EL | Eva CANO GONZALEZ | QUEST | HI-ECN3 / NA-CONS | Completed | 2/5/2024
Cristina DURAN GUTIERREZ | TDR | EN-HE | Roberto RINALDESI | ORIGIN | HI-ECN3 | Completed | 1/6/2024
Olin PINTO | TDR | HSE-RP | Claudia AHDIDA | QUEST | HI-ECN3 | Completed | 1/2/2024
Mike PARKIN | TDR | SY-STI | Rui FRANQUEIRA XIMENES | QUEST | HI-ECN3 | Completed | 1/4/2024
Patrick CURRAN | TDR | EN-MME | Stefano SGOBBA | QUEST | HI-ECN3 | Completed | 1/2/2025
Gemma HUMPHREYS | TDR | SY-STI | Jean Louis GRENARD | QUEST | HI-ECN3 | Completed | 1/12/2024
Giuseppe MAZZOLA | R2E / FLUKA | SY-STI | Luigi ESPOSITO | QUEST | HI-ECN3 | Completed | 1/2/2022
Anna HUNCIKOVA | TDR | BE-GM | Camille VENDEUVRE | QUEST | HI-ECN3 / NA-CONS | Completed | 1/12/2024
TBC | BLM | SY-BI | Christos ZAMANTZAS | ORIGIN | HI-ECN3 | TBC | Q3 2026
TBC | BLM | SY-BI | Christos ZAMANTZAS | TECH | HI-ECN3 | TBC | Q3 2026
Panagiotis MENACHILIS | TCSC CONS | SY-STI | Nicolas SOLIERI | QUEST | NA-CONS | Completed | 1/10/2024
Iasonas CHATZIGEORGIOU | XTAX CONS | BE-EA | Miguel SANTOS | QUEST | NA-CONS | Completed | 1/2/2023
Giorgio GARLASCHELL | TDC2 / TCC2 | HSE-RP | Helmut VINCKE | QUEST | NA-CONS | Completed | 1/9/2024
Alexander GORN | TDR | SY-ABT | Matthew FRASER | GRAF | PBC / SY / HI-ECN3 | Completed | 1/10/2023
Tamara BUD | ECN3 tasks on request | SCE | John OSBORNE | QUEST | PBC | Completed | 1/1/2024
Francesca LUONI | ECN3 tasks on request | HSE-RP | Claudia AHDIDA | FELL | PBC | Completed | 1/9/2023
Tirsi PREBIBAJ | ECN3 tasks on request | BE-ABP | Hannes BARTOSIK | GRAF | PBC | Completed | 1/3/2023

## Slide 10
Project Master Schedule
TDR
extension?
Long Shutdown 3 (SPS)
Upgrades with NA-CONS
LS4
Critical path:
CE procurement & works
Dismantling
Beam on BDF Target
TDR Phase
(Facility)
Below freezing design for SCE!
(Detailed design for consultant before contractor Invitation to Tender)
July 2026

## Slide 11
HI-ECN3 TDR
Aiming for TDR publication mid-2026: with updated cost & resource estimates of project baseline
Timeline:
  September 2025 (Q3 2025): Frozen design* as part of completion of IRP Design Study needed for consultant Invitation to Tender (IT)
  Scope, with loads & volumes needed in 2025
  Choice of target technology (H2O vs. He) must not impact envelopes for civil engineering:
    Final validation of He-cooled design will not be available until after the beam tests in 2025 and 2026
  The Service Cell must not impact civil engineering
  December 2025: Preliminary design for consultant
  July 2026: Detailed design for consultant
  October 2026: Launch contractor IT: significant cost impact and delay with any further changes
  *Frozen design = volumes, loads & structural definition (small openings and internal integration have some flexibility)

## Slide 12
HI-ECN3 Operation
Operation out to late 2040s:
beyond HL-LHC
(frequency & length of LS’s TBC)
HI-ECN3
Commissioning
HI-ECN3
Operation
Today
NA available exclusively for EHN1/2 from mid-2029:
Test-beam users & other POT demanding experiments
(e.g. AMBER, MuonE)
ECN3 beam to dump in P42 for commissioning of TCC2
whilst construction ongoing
CERN Accelerator Schedule
NA-CONS
NA-CONS Phase II
(TBC)
NA-CONS Phase I
M. Lamont, Updated schedule for CERN’s accelerators, CERN Bulletin, 4 October 2024
HI-ECN3
TDR Phase

## Slide 13
NA-CONS Phase 1
NA-CONS Phase 2
Commissioning High Intensity for ECN3
The commissioning of HI-ECN3 can be grouped into two phases:
  Commissioning TCC2 (2029 – 30, ~ 2 yr) with NA-CONS: inc. SPS, slow extraction
  Commissioning of ECN3 (2031 – 32, ~ 1.5 yr): inc. BDF in TCC8, beam transfer from TCC2 to TCC8, before ramping up to nominal operation together with SHiP before end 2032
Commissioning of SPS and NA (TCC2) for HI-ECN3
Q3 2031:
Beam on BDF Target
BDF commissioning
(flexible with SHiP installation)
YETS30/31:
Remove P42 beam dump & reconfigure beam line
Operation of
BDF/SHiP
@ 41019 POT
Commissioning of SHiP:
ramping intensity
Upgrades of TCC2 for HI-ECN3

## Slide 14
CERN Operation
Operation:
  30 to 35 weeks (~200 days per year) of protons on target (depending on ion run) per year
  Yearly Year End Technical Stops of about ~ 3 - 4 months
  1 or 2 Injector Technical Stops during the year for a few days
  Wednesday Machine Development < 10 per year (10h each): some MDs will need to use the BDF target and send beam to ECN3
  BDF POT @ 41019 / year:
  POT will be competitive and scarce in the future
  POT computed assuming a machine availability of 80%
  Operation for SHiP will not be stopped outside of planned access/maintenance periods, unless unforeseen maintenance is absolutely needed
BDF TSAC #1 4 – 6th March 2025

## Slide 15
Let’s have a productive few days…!
Any questions…?