## Slide 1: HiRadMat facilities presentation SPS Planning meeting for YETS 2024-25 & LS3 preparation, No.05
A. Ebn Rahmoun, A. Goillot, B, Rae
17 December 2024

## Slide 2: Overview HiRadMat facilities
Technical/Service gallery
Transfer line
From Ba7&TA7
Primary beam line
Experimental Area
Dump TED

## Slide 3: YETS 2024-25 & LS3
LS3 activities, all major activities were completed in YETS23-24 and moved forward to YETS24-25.
This list is not exhaustive.
Thanks to all the groups who involve in the annual maintenance.
Activity YEST2024-25 | Contact | Duration | Group involved
Handling Iron blocks from TT61&TNC to Isolde | A-P. Bernardes | 1 month | EN-HE; SY-STI; BE-EA
The replacement of the BTV 660528 | S. Burger; J. Albertone. | 2 weeks | SY-BI; EN-HE; BE-GM; BE-EA
Painting access door TT61-TCC6 YDPS02.012058=TT61 | D. Vaxelaire | 1 week | SCE-SAM;
Management user & control cables | A-M. Goillot | 1 week | BE-CEM; BE-EA
HiRadMat lab. renovation | A. Ebn Rahmoun | 2 months | BE-EA

## Slide 4
Thanks all groups involved

## Slide 5: Feedback YETS 2023-24
Ba.7 :
  HiRadMat lab. The renovation is progressing well, with the aim of having the same layout of the stands installed in both the tunnel and the preparation lab.;
TNC & TT61:
A few activities have started before the YETS to prepare for the major events.
  TED dump, has been modified, extended tube , new window & collimator installed;
  BPKG relocated and new BTV has been installed;
  New vacuum system installation & modification end of line TT66;
  The GSM cables have been replaced;
  TT61, new electrical & grounding circuits have been installed for the users.
  *The list is not exhaustive, thanks to all the groups who involved in the annual maintenance and installation activities.
Minor points:
  We experienced a 4 days delay with the installation of the BTV and BPKG. After discussions with BE-OP and EN-ACE, we managed to find this time during the SPS HC period to complete it;
  The activities of TJ7, which serves as a hub for HRM, TCC6, TI2, and SPS.