## Slide 1: Final Annual Meeting Tuesday 6 May 2025 Prague
WP7: Gaseous Detectors
Burkhard Schmidt (CERN)

## Slide 2: Task Overview
Task 7.1: Coordination and Communication (S. Dalla Torre, BS)
Task 7.2: RPC sector 3 tasks
                - 7.2.1: Multi-gap RPCs (MRPCs) for fast timing (C. Williams)
                - 7.2.2: Shower development in SDHCAL (Mary-Cruz Fouz)
                - 7.2.3: Eco-friendly gas mixtures for RPCs (B. Mandelli, D. Piccolo)
                Task 7.3: MPGD sector, Technology and engineering 2 tasks
                - 7.3.1: Development of resistive electrodes for MPGDs (P. Verwilligen)
                - 7.3.2: Industrial engineering of high-rate μ-RWELLs (G. Bencivenni)
                Task 7.4: Large volume gaseous detectors 2 tasks
                - 7.4.1: A 4-channel electronic board for cluster counting (F. Grancagnolo)
                - 7.4.2: High pressure gas TPC for neutrino physics (X. Lu, D. Gonzalez Diaz)
Task 7.5: PID sector 1 task
- Photon detectors for hadron Particle ID at high momenta (S. Dalla Torre)
2

## Slide 3: Milestones & Deliverables
Deliverables and Milestones in the 2nd and 3rd year:
Milestone MS26: Production of DLC with ion beam deposition and pulsed laser deposition, due in M23 and has been achieved on time.
Deliverable D7.3: Production with industry of small-size prototypes of μ-RWELLs, due in M30, has been delayed to M33 and achieved.
Milestone MS27: Build a 0.3×0.3 m2 prototype and the readout plane with the new structure, was due in M36, has been delayed to M40 – and achieved.
Deliverable D7.2: Characterisation of small size MRPC prototypes for fast timing and high rates, due in M36, has been achieved.
Milestone MS28: Identification of a gas mixture for neutrino physics in an optical TPC, due in M36, has been achieved.
4
1st PRM
2nd PRM





## Slide 4: Milestones & Deliverables
Deliverables and Milestones in the 4th year :
Milestone MS27: Build a 0.3×0.3 m2 prototype and the readout plane with the new structure, delayed to M40, achieved
Deliverable D7.5: Small-size prototype of a MPGD single photon detector for compact RICH detectors due in M44, achieved.
Deliverable D7.2: Validation of the eco-friendly gas mixtures for RPCs at GIF++, due in M45, achieved.
Deliverable D7.4: A small-scale TPC prototype with hybrid charge/optical read-out and a hydrogen rich gas mixture with high scintillation yield, due in M46, achieved in M47.
Milestone MS29: Design electronics for cluster counting and production of a 4-channel prototype, due in M46, achieved in M48
        All Milestones and Deliverables have been achieved
4
2nd PRM









## Slide 5: Goal of the Meeting
This is the Final Annual Meeting, in which we would like to review together the achievements of AIDAinnova WP7 over the past 4 years.
Some Tasks had early Milestones or Deliverables, which had the side effect that the activities slowed down ones the Milestone resp. the Deliverable had been achieved…
Nevertheless, let us try to summarize our achievements as good and clear as possible, also in the view of the final report, to be prepared in the coming months.
Furthermore, any conclusions to be drawn and advice to give for the planned follow-up programme of AIDAinnova would be much valued.