## Slide 1: Preparations for Run 2b dismantling and update on Run 2c
AWAKE Collaboration meeting – Eloïse Guran
24-26 March 2025
AWAKE Collaboration Meeting - 24-26 March 2025

## Slide 2: Outline
Global planning
Run 2b dismantling & decabling preparations
Update on Run 2c schedule and milestones

## Slide 3: Global planning
Run 2b removal: 10th of June to mid-September 2025
Decabling: Mid-September to mid-November 2025
CTD: December 2025
AWAKE Run 2c installation: March 2026

## Slide 4: Run 2b dismantling - planning
Photocathode test: 02/06
Dismantling start = Tuesday 10th of June
End = 19th of September
Duration ~3.5months
Several co-activities to coordinate

## Slide 5: Run 2b dismantling - sequence
Main steps of the dismantling:
Optics removal - 1 week
Plasma cell + RF - 4 weeks
Removal of electron bunker and TCC4 shielding - 3 weeks
TT43 electron line removal (magnets, BI, girders) - 2 weeks
TT41/TCC4 proton line removal (magnets, BI, girders) - 2 weeks
Support from vacuum team during all steps (except step 3)

## Slide 6: Run 2b dismantling – what’s next
Dedicated meetings (detailed planning, transport, safety, etc)
Collect your needs in terms of pallets
Check all storage locations are defined
77
DAYS LEFT
Tuesday 10th of June
START

## Slide 7: Run 2b decabling
Cable lists for decabling defined
Pre-identification on-site
Next  Final identification with purple tape on both end + disconnection of cable on both end
Monday 22nd of Sept.
START

## Slide 8: Surface building for CTD
Civil engineering completed
  end of April
Building ready to use
  mid-July
November 2024
26th February 2025
19th March 2025
3D rendering of building 697 (courtesy of Antoine Kosmicki)

## Slide 9: Global planning

## Slide 10: Run 2c schedule
Wishful planning:
~10months for services
~13months for equipment
~13.4months for HWC
Planning currently being updated
Rack area
Klystron area
Plasma cells
Electron sources
Proton line

## Slide 11: Run 2c – Constraints for installation / planning
Availability of resources during LS3
Cabling
Vacuum (especially for bake-out)
Transport
Sequence of install
Crane limitations (7.5T)
Restart for beam commissioning
Need DSO tests for electron beam
Need services (cooling, access system, etc) fully functionnal
EPC (MEXICO converters)

## Slide 12: Milestones – studies & procurement
Services status:
EN-CV: On-track. User requirement documents to be sent for approval on edms this summer
TE-VSC: On-track. /!\might have lack of resources for the bake-out of photo-injectors needed in 2027/2028, especially if it falls at the same time as LHC bake-out /!\
EN-MME: on-track
EN-EL / infrastructure: on track  needs update on electric requirements for equipment to be able to perform detailed studies /!\ might have space issue for new transformer /!\
EN-EL / cabling: on track for start of studies /!\ need cable lists to start studies /!\
Equipment status:
Laser: on-track
Plasma cell (MPP): On-track
RF: on-track
Proton & electron line: on track, Beamline design almost finalised
BI: On-track
EPC: /!\ MEXICO converters ready for install Q1 2029  very tight for Awake schedule
Globally on-track  need to maintain momentum to stay that way

## Slide 13: Run 2c – cabling requests
Cabling requests (DICs) well defined
EN-EL studies
Cable rooting
Cost & feasibility
Cabling campaigns
2027 & 2028
Input needed as soon as possible
Else, cabling campaigns will be delayed

## Slide 14: Summary
Run 2b dismantling/decabling preparations are progressing smoothly  on-time for a start on 10th of July
Run 2c planning currently being updated  ramping up meetings and discussion to progress
Milestones for Run 2c still on time, but need to maintain the momentum
- Some critical issues, such as the injection region design, still need to be resolved
 Essential to maintain momentum
- Need to continue progress in the integration studies
77
DAYS LEFT
Tuesday 10th of June
START