## Slide 1
Commissioning planning

## Slide 2
2024 reviews
LNO section – 2024 commissioning breakdown https://indico.cern.ch/event/1406933/
LMC – 2024 linear optics outcomes https://indico.cern.ch/event/1448059/contributions/6097636/
LMC – 2024 nonlinear optics outcomes https://indico.cern.ch/event/1448059/contributions/6097637/
2022 commissioning IPAC report (F.C.) https://accelconf.web.cern.ch/ipac2023/pdf/MOPL015.pdf
2023vs2024 commissioning IPAC report (T.H.B.P) https://accelconf.web.cern.ch/ipac2024/pdf/MOPC12.pdf

## Slide 3
Pre-commissioning tasks
Guess Corrections:
Local coupling  Felix.S.
Local IR  Ewen
Local arc  Yannis
Beta-waist knobs  Felix.C.
Injection b3/a3  Sasha/Ewen
BBLR  Sasha
IRb4?  Ewen
Tool development/checks
SbS  Josch
Kmod Q source  Felix.C.
Kmod integration  Felix.C
OMC3 json  Josch
NLgui  Ewen
IR a4  Sasha
New Multiturn  Ujani/Andrea?
Nlchroma GUI  Mael?
OMC3  everyone
Training / reference measurements
2023/4 injection virgin/corrected
2023/4 30cm EOS virgin/local/final
2023/4 SbS for IP1/5
Started preparing a list of tasks to be completed before commissioning: volunteers wanted!

## Slide 4
Commissioning planning
Draft schedule in preparation by Jorg  looks quite optimistic w.r.t. OMC (1 shift less than 2024!)
 should pass feed-back to OP  LBOC Mid-march but should give plans well before
Please fill in newdle of rough availability:
https://newdle.cern.ch/newdle/c56D8kLF
https://docs.google.com/spreadsheets/d/1GKSzG9yVtknviEWBun4ZuqdUQdKcvR7pMqhB1jFyRRY/edit?pli=1&gid=803367188#gid=803367188
Shifts |  |  | 
Team | hours | shifts | 2024
OMC | 92 | 11.5 | 12.5
RF | 32 | 4 | 4
ADT | 24 | 3 | 2
COL | 88 | 11 | 12.5
ABT | 48 | 6 | 7.5
BI | 0 | 0 | 1
TOTAL | 284 |  | 

## Slide 5
Fri 4/4/25 |  |  |  |  |  | 
 | M | 4 |  | OP |  | LBDS and BIS MP tests, dry injection tests
 | M | 4 |  | OP |  | LBDS and BIS MP tests, dry injection tests
 | A | 4 |  | OP |  | TI2 & TI8 beam tests
 | A | 4 |  | OP |  | TI2 & TI8 beam tests
 | N | 4 |  | OP |  | 
 | N | 4 |  | OP |  | 
Sat 5/4/25 |  |  |  |  |  | 
 | M | 4 |  | OP |  | First circulating beam
 | M | 4 |  | OP |  | Closed orbit, BI checks, rough collimator setup
 | A | 4 |  | OMC | BCM | Optics measurements at injection
 | A | 4 |  | OMC | BCM | Optics measurements at injection
 | N | 4 |  | OMC | BCM | Optics measurements at injection
 | N | 4 |  | OP |  | 
Sun 6/4/25 |  |  |  |  |  | 
 | M | 4 |  | OP |  | Ramp to 6.8 TeV
 | M | 4 |  | OP |  | Ramp to 6.8 TeV, coarse coll @ FT, squeeze to 18cm
 | A | 4 |  | OMC | BCM | Optics measurements along the squeeze
 | A | 4 |  | OMC | BCM | Optics measurements along the squeeze
 | N | 4 |  | OP |  | Precycles and decay measurements
 | N | 4 |  | OP |  | Precycles and decay measurements
Mon 7/4/25 | 1 |  |  | WEEK | 15 | 
 | M | 4 |  | OP |  | Ramp to 6.8 TeV vdm
 | M | 4 |  | OP |  | Ramp to 6.8 TeV vdm
 | A | 4 |  | OMC | BCM | Optics measurements and corrections at injection
 | A | 4 |  | OMC | BCM | Optics measurements and corrections at injection
 | N | 4 |  | OMC | BCM | Optics measurements
 | N | 4 |  | OP |  | BLM interlock tests with beam
Tue 8/4/25 | 2 |  |  |  |  | 
 | M | 4 |  | OP/ADT |  | Flat reference orbit / ADT commissioning - nominal bunch
 | M | 4 |  | OP/ADT |  | Flat reference orbit / ADT commissioning.
 | A | 4 |  | OMC | BCM | Optics commissioning 6.8 TeV
 | A | 4 |  | OMC | BCM | Optics commissioning 6.8 TeV
 | N | 4 |  | OP |  | Precycles and decay measurements
 | N | 4 |  | OP |  | Precycles and decay measurements
Wed 9/4/25 | 3 |  |  |  |  | 
 | M | 4 |  | OP |  | BLM (MP test) and exp. splashes
 | M | 4 |  | RF/ADT |  | RF setup with probes and nominals, ADT commissioning
 | A | 4 |  | RF/ADT |  | RF setup with probes and nominals, ADT commissioning
 | A | 4 |  | OP |  | Orbit bumps at injection
 | N | 4 |  | OP |  | Orbit bumps at injection, ramp to FT with bumps
 | N | 4 |  | OP |  | 
Thu 10/4/25 | 4 |  |  |  |  | 
 | M | 4 |  | OP |  | Access
 | M | 4 |  | OP |  | Access
 | A | 4 |  | OMC | BCM | Optics commissioning 6.8 TeV - NL optics
 | A | 4 |  | OMC | BCM | Optics commissioning 6.8 TeV - NL optics
 | N | 4 |  | OP |  | Precycles and decay measurements
 | N | 4 |  | OP |  | Precycles and decay measurements
Fri 11/4/25 | 5 |  |  |  |  | 
 | M | 4 |  | OP |  | ALICE and LHCb magnets on
 | M | 4 |  | COL |  | Collimator alignment at injection
 | A | 4 |  | COL |  | Collimator alignment at injection
 | A | 4 |  | OP/OMC | BCM | VDM cycle to 6.8 TeV, optics check - bumps on
 | N | 4 |  | OP/OMC | BCM | VDM cycle to 6.8 TeV, optics check
 | N | 4 |  | OP |  | 
Sat 12/4/25 | 6 |  |  |  |  | 
 | M | 4 |  | COL |  | Injection aperture
 | M | 4 |  | COL |  | Injection aperture
 | A | 4 |  | ABT |  | TDIS, TCLI alignment and validation at injection
 | A | 4 |  | ABT |  | TDIS, TCLI alignment and validation at injection
 | N | 4 |  | ABT |  | TDIS, TCLI alignment and validation at injection
 | N | 4 |  | OP |  | 
Sun 13/4/25 | 7 |  |  |  |  | 
 | M | 4 |  | OMC | BCM | Optics commissioning at FT
 | M | 4 |  | OMC | BCM | Optics commissioning at FT
 | A | 4 |  | OMC | BCM | Optics commissioning at FT
 | A | 4 |  | OP |  | 
 | N | 4 |  | OP |  | 
 | N | 4 |  | OP |  | 
Mon 14/4/25 | 8 |  |  | WEEK | 16 | 
 | M | 4 |  | COL |  | ATLAS horizontal muons (from 9am)
 | M | 4 |  | COL |  | Collimator alignment at FT (including angular alignment)
 | A | 4 |  | COL |  | Collimator alignment at FT (including angular alignment)
 | A | 4 |  | COL |  | Collimator alignment at FT (including angular alignment)
 | N | 4 |  | OP |  | 
 | N | 4 |  | OP |  | 
Tue 15/4/25 | 9 |  |  |  |  | 
 | M | 4 |  | OP | LUMI | VDM cycle collisions at 6.8 TeV (Single_2b_1_1_1) - NO stable beams
 | M | 4 |  | ADT |  | ADT setup
 | A | 4 |  | ADT |  | ADT setup
 | A | 4 |  | ABT |  | TDIS, TCLI alignment and validation at injection
 | N | 4 |  | ABT |  | TDIS, TCLI alignment and validation at injection
 | N | 4 |  | OP |  | 
Wed 16/4/25 | 10 |  |  |  |  | 
 | M | 4 |  | OP |  | Access
 | M | 4 |  | OP |  | Access
 | A | 4 |  | OMC | BCM | Optics commissioning at FT
 | A | 4 |  | OMC | BCM | Optics commissioning at FT
 | N | 4 |  | OMC | BCM | Optics commissioning at FT
 | N | 4 |  | OP |  | 
Thu 17/4/25 | 11 |  |  |  |  | 
 | M | 4 |  | RF |  | RF setup
 | M | 4 |  | RF |  | RF setup
 | A | 4 |  | ABT |  | Injection and dump aperture
 | A | 4 |  | ABT |  | Injection and dump aperture
 | N | 4 |  | ABT |  | Injection and dump aperture
 | N | 4 |  | OP |  | 
Fri 18/4/25 | 12 |  |  |  |  | 
Easter | M | 4 |  | OP |  | First test of ion cycle
 | M | 4 |  | OP |  | First test of ion cycle
 | A | 4 |  | ABT |  | TCDQ alignment at FT
 | A | 4 |  | ABT |  | TCDQ alignment at FT
 | N | 4 |  | OP |  | LMs at injection
 | N | 4 |  | OP |  | LMs at injection
Sat 19/4/25 | 13 |  |  |  |  | 
Easter | M | 4 |  | OMC | BCM | Optics commissioning at FT
 | M | 4 |  | OMC | BCM | Optics commissioning at FT
 | A | 4 |  | OMC | BCM | Optics commissioning at FT
 | A | 4 |  | OP |  | Running throught the beta* levelling (no collisions!)
 | N | 4 |  | OP |  | Running throught the beta* levelling (no collisions!)
 | N | 4 |  | OP |  | 
Sun 20/4/25 | 14 |  |  |  |  | 
Easter | M | 4 |  | OP/ABT |  | MKI8 & MKI2 waveform - splashes in LHCb/ALICE
 | M | 4 |  | OP/ABT |  | MKI8 & MKI2 waveform - splashes in LHCb/ALICE
 | A | 4 |  | OP |  | 
 | A | 4 |  | OP |  | 
 | N | 4 |  | OP |  | 
 | N | 4 |  | OP |  | 
Mon 21/4/25 | 15 |  |  | WEEK | 17 | AWAKE !!

## Slide 6
Commissioning planning
Starting to put together plan based on 2024 experience:
Before commissioning: ACD+MKA HW tests
Injection 1
ACD and BPM checks
Local coupling with guess corrections
Virgin measurement
Global correction
Total phase correction
injection2
Global corr iteration after tot-phase
Sextupole RDT corrections
NL chroma checks
Detuning references
Injection filler
MO response
Optics/coupling/RDT decay
Any investigations proposed for Dy?
IP4 kmod?
Arc-by-arc coupling at injection? No other times in Run3
 Trimmed in in ramp

## Slide 7
Commissioning planning
Starting to put together plan based on 2024 experience:
Top energy 1-2
First measurements through squeeze
First coupling checks through ramp & squeeze
Measurements at end of squeeze
Energy correction with virgin optics  comment by Felix
Checks/iteration of guess local corrections
Arc bump correction
IR-b4 correction
Need to decide setup of knobs:
Reuse: old/predicted local corrections IP1258
Reuse: 2022 local coupling
Reuse: 2022 arc-by-arc coupling
Reuse? 2022 IP1 collinearity? In physics but not squeeze no IP5 or IP2 in history
Reuse? 2022 arc bumps 81 and 45
Reuse? IRb4
Top energy 3  too optimistic for 1 shift?
Measurements through squeeze with local corrections/arc bumps incorporated
Validation of 2023 global corrs at beta*>physics
End of squeeze – a3,b3,a4,b6 corrections
Top energy 4
Beta waist – testing before global correction
Global corrections at 60,30,18 with crossing scheme applied  to discuss: initial correction at flat? Or just all at once?
Top energy 5-6
Global incorporation / validation
Kmod/beta-waist

## Slide 8
Commissioning planning
Starting to put together plan based on 2024 experience:
Top energy 7
Global iteration after beta-waist
Top energy 8
Final validation of ramp and squeeze and Kmod
Extra1 : wire optics checks?
Extra2 : even lower beta?
Extra3 : LRBB corrections?
Extra4 : dispersion investigations
Extra5 :
Top energy 9
Local IR coupling in collision
Special1 : VDM validation
Special2-? : ION commissioning