## Slide 1: Magnet installation and Interconnections Plan
LMF, 12/02/2025

## Slide 2: IT String : interconnection naming
DFX
DFXI
DCM
LDQD
D1
LBXFC
CP
LCXFC
Q2b
LQXFJ
Q3
LQXFF
Q1
LQXFE
Q2a
LQXFG
QQQIF.1SF
QQQIF.A2SF
QQQIF.B2SF
QCQIF.3SF
QBCIF.3SF
QDBIX.4SF
QDDIX.4SF
QQSJF.2SF
QQSJF.3SF
QQSJF.4SF
Cell1
Cell2
Cell3
Cell4
7 interconnections
3 Jumpers
e-MIP structure in progress (~ WISH during LS1 / LS2)

## Slide 3: Present configuration
Jumper interfaces to be fixed by TE/CRG (feb)
Installation of Q3 : 28/02/25.
DFX
DFXI
DCM
LDQD
D1
LBXFC
CP
LCXFC
Q2b
LQXFJ
Q3
LQXFF
Q1
LQXFE
Q2a
LQXFG
Installation planned ~ 2 months
Installation planned end of february

## Slide 4: Before starting
After magnet installation
  Check jumper connection TE/CRG & TE/MSC
  Remove transport equipment (if still any)
  Installation of the anchors
    Anchors to ground ( with concrete !) : EN/ACE
    Anchors to cryo-magnets : TE/MSC
  ElQa test of the magnet
  Magnet alignment
DFX
DFXI
DCM
LDQD
D1
LBXFC
CP
LCXFC
Q2b
LQXFJ
Q3
LQXFF
Q1
LQXFE
Q2a
LQXFG
Fake PIM in CP-Q3 and Q2b-Q2a
General inspection before starting
  Phase 3 complete TE/MSC
    Check that electrical test was done before
    Cable identification done
    Line N leaders
    Sleeves (Line M2N, L)
    W bellow + O rings properly protected (and with spares)
    18kA cable in Q2a
    Endoscopy + lyra inspection
    Jumper gimbal in place
    Endoscopie ligne N1-N2 des cryo-aimants
First week of March
Formation securite ?

## Slide 5: N lines insertion
DFX
DCM
D1
CP
Q2b
Q3
Q1
Q2a
Insertion of N2 line (pulled from Q1)  ElQa test
Insertion of N1 line (pulled from Q2a if possible)  ElQa test
Installation of D1 swan neck vacuum vessel
Installation of DCM Frame
Installation of D1 module
Welding of D1 module
 ElQa test of N1 and N2 ( no magnet connection)
In parallel : stabilisation of lines N in D1-Q2a
QC : end of cables

## Slide 6: First blank assembly & splice soldering
Splices blank assembly from CP to Q2a
  QC of blank assembly
 ElQa test from QDBIX on QCQIF, QQQIF.B, QQQIF.A
Splices soldering 18kA
  QC : visual inspection
  QC : splice resistance
Splices soldering 2kA
  QC : visual inspection
  QC : splice resistance
Splices insulation 18kA and 2kA
  QC
 ElQa test from QDBIX on QCQIF, QQQIF.B, QQQIF.A
DFX
DFXI
DCM
LDQD
D1
LBXFC
CP
LCXFC
Q2b
LQXFJ
Q3
LQXFF
Q1
LQXFE
Q2a
LQXFG
Installation of the DCM
Alignment of the DCM

## Slide 7: First blank assembly & splice soldering
Installation of insulation box
  QC
 ElQa test
Eccobon injection (?)
  QC
 ElQa test
DFX
DFXI
DCM
LDQD
D1
LBXFC
CP
LCXFC
Q2b
LQXFJ
Q3
LQXFF
Q1
LQXFE
Q2a
LQXFG

## Slide 8: Second blank assembly & splice soldering
Sleeves welding
  Visual inspection EN/MME
Jumpers welding
  Visual inspection EN/MME
DFX
DFXI
DCM
LDQD
D1
LBXFC
CP
LCXFC
Q2b
LQXFJ
Q3
LQXFF
Q1
LQXFE
Q2a
LQXFG
Splices blank assembly of QDDIX and QDBIX
  QC of blank assembly
 ElQa test from DFHX
Splices soldering +Vtaps
  QC visual inspection
  QC splice resistance
  Vtaps connection
   ElQa continuity
Splices insulation
 ElQa test from DFHX + Vtaps checks
…..

## Slide 9: Third blank assembly & splice soldering
Splices blank assembly of Q1
  QC of blank assembly
 ElQa test from DFHX
Splices soldering 18kA
  QC : visual inspection
  QC : splice resistance
Splices soldering 2kA
  QC : visual inspection
  QC : splice resistance
Splices insulation 18kA and 2kA
  QC
 ElQa test from DFHX
Sleeves welding
  Visual inspection EN/MME
DFX
DFXI
DCM
LDQD
D1
LBXFC
CP
LCXFC
Q2b
LQXFJ
Q3
LQXFF
Q1
LQXFE
Q2a
LQXFG
WIB (WP6a)
Sleeves +E lines welding
Visual inspection EN/MME

## Slide 10: Leak test
Ready for leak test : first estimation beg of May (if start 2nd week of March)
If all OK : inspection before W closing
MLI + thermal shields
W closure
Ready for global test and pressure test
DFX
DFXI
DCM
LDQD
D1
LBXFC
CP
LCXFC
Q2b
LQXFJ
Q3
LQXFF
Q1
LQXFE
Q2a
LQXFG