## Slide 1: SM18 vertical test bench planning
2025.02.18

## Slide 2: Update since last meeting
Cluster D | HFM | Siegtal | Long | Diode
MCBXFB07 -- finished | MQXFS8b – ongoing* | SMC108-eCLIQ -- finished | Sushi -- finished | DR_FFC01_06 -- finished
MCBRD06 -- ongoing |  |  |  | IT-diode 1 – in preparation
Other magnets waiting in SM18 for tests:
3x MSCB, MQ
* MQXFS8b delayed due to EN/MME work in the LHC

## Slide 3: HFM program table by Gerard
Institute | Magnet | Outer diameter | Nominal current | First Test foreseen | Test station
Ciemat | ISAAC conf1 ISAAC conf2 DAISY | ? ? ? | 16.3 19.4 ~ 15.5? | Summer 2025 January 2027 | HFM? Cluster D? HFM?
CEA | R2D2 FD F2D2 | 480 650 650 | ~16 11.4 9 | End 2025 Beginning 2026? | HFM HFM HFM
INFN/CERN | Falcon M1 Falcon M2 Falcon M3 | 640 640 720 | 19.9 20.2 20.4 | Q3 2026 Q4 2027 Q2 2028 | Cluster D Cluster D Cluster D
CERN | Bond #1-SA Bond #2 - SA Bond #3-DA | 640 640 780 | 20.2 20.2 19.6 | Q2 2026 Q3 2026 End 2026 | Cluster D Cluster D Cluster D
PSI | SMCC2 SMACC |  | 9 12.7 | 2025 2026? | Siegtal? Siegtal?
CERN TDP MQXFS | 8b 4f 8c 4g 4h 4i |  |  | Feb 2025 Mar 2025 May 2025 June 2025 Sept 2025 Dec 2025 | HFM HFM HFM HFM HFM HFM
CERN TDP SMC | 2G 109 2G 110 2G 106 2G 201 2G 107c 2G 202 2G 203 |  |  | Mar 2025 Apr 2025 May 2025 June 2025 Jul 2025 Sept 2025 Dec 2025 | Siegtal Siegtal Siegtal Siegtal Siegtal Siegtal Siegtal
HTS by MSC-HSD | Multiple coils Three double layer racetracks 5.8 T |  |  | March 2025 and onwards May 2025 | Diode/CVT Diode/CVT or HFM?
HTS IRIS | I consider these are tested in Italy |  |  |  | 
CEA | long” MI Racetrack HTS |  |  | Send to CERN May 2025 | Diode/CVT?
LBNL | HD3 |  |  | Spring 2025? | HFM

## Slide 4: Magnets from SMT
MQXFS4f ?
SMC 109 ?
RMM2 ?
Fusillo ?
Others that I missed?

## Slide 5: Magnets from HSD
DR_FFC01_08: arrival second week of March
  Does it include Carlo’s MM system?
Three coils in a frame: last week of April
Second Three coils in a frame: last week of May
Common Coil configuration: around September
Scale UP – 2 year program, TBD

## Slide 6: Magnets from LMF / WP3
MgB2 200mm radius bending test – to 163?
MSCB
EESD phase 3
MCBXFA2: arrival mid March
  I think this should be the next one in Cluster D
MCBRD05 (tested) and MCBRD07 (virgin): will arrive beginning of March.
MCBRD08 (virgin): May 2025
MCBRD09 (virgin): July 2025.
MCBRD10 (virgin): September 2025.
MCBRD11: Former expected in March, magnet in May.

## Slide 7: Magnets from collaborations
PSI – SMCC2 ?
CIEMAT – ISAAC 1?
AUP – HD3: shipping end of February
CEA – HTS EuCARD2 ?
CEA – MI long racetrack HTS ?
INFN – Falcon D: probably not this year