## Slide 1: Bond
N. Lusa and J. Ferradas Troitino
18/02/2025
Mock-up design of sliding reaction tooling

## Slide 2
Updates w.r.t. the last meeting (04/02/25)
  Linear ceramic bearings test set-up
    Drawings signed
  Circular ceramic bearings set-up
    Drawings signed
  Is the intermediate heat treatment needed? Let’s see the result of the here below strategy
    First machining of the titanium plate (CRNMHF0ST0039) and of 2 shorter components (CRNMHF0ST0049) done
    Parts already cleaned
    In-house metrology (Faro arm and dial gauge) ongoing
    Heat treatment under vacuum at EN-MME facility at about 700°C for 70h and slow cool-down inside the oven (planned in the second half of the week) prior to perform a second metrology and the finishing pass
    About 600 CHF/day of cycle
  Displacement measurement based on high temperature capacitive sensors or other measurement device
    Meeting with EN-MME on 03/12/2024 to activate a collaboration aiming at finding the appropriate measuring device for our case
    We expect to have soon (within end of February) a tentative timeline for
      Feasibility study
      Purchasing of one or more measurement systems
      Calibration
      Implementation and integration of the measurement system in a dedicated mock-up
    In parallel mechanical system will be implemented to measure the maximum displacement during RHT, once the cycle is finished
Test set-up
EDMS 3227341

## Slide 3
Will the HT cycle have an impact on the final shape of the components (deformations)?
  Based on titanium material certificate, the raw material was already subjected to 650°C for 120 min air cooling (AC)
    Our cycle will be at around 660°C and will last longer → additional stress relieving may occur
Strategy
  Rough machining of few components → metrology
  Heat treat them at 700°C for 70h and slow cool-down inside the oven
  Check any deformation that may have occurred prior to perform the finishing pass
Manufacturing schedule
If NO DEFORMATIONS
  Final manufacturing of all components without intermediate HT cycle
  Manufacturing process is less time consuming
If DEFORMATIONS
  Rough manufacturing with intermediate HT cycle is needed
  Manufacturing becomes trickier and very long in terms of time required

## Slide 4
Manufacturing schedule
Scenario A (no deformations after HT cycle)
Scenario B (deformations after HT cycle)

## Slide 5
  The plate is checked both with Faro arm and with dial gauge (here below dial gauge result)
    The plate has a belly shape with a maximum of about 0.280 mm towards the middle
    It is not something local, but the deformation is general
Metrology of the plate prior HT
Courtesy of A. Vieitez Suarez

## Slide 6: Test set-up: Linear ceramic bearing
Courtesy of B. Pellet

## Slide 7
Test set-up: Circular ceramic bearing
Courtesy of B. Pellet

## Slide 8
Updates w.r.t. the last meeting (04/02/25)
    3D model completed
      Detail drawings of the mold completed
      Integration of the sliding system to be finalized within the end of the week
      Drawings sent to N. Peray for a first check
    Meeting with P. Moyret about the manufacturing of the components
      The parts will be manufactured in the main workshop with an intermediate heat treatment at 950°C for 2h for detensioning
      Delay: 05/2025 → drawings need to be signed by the end of 02/2025
    MQXFB insulated cable leftovers for the winding, about 15m for the test
      Cable with keystone angle → suggestion of making lateral shims with a compensation angle
  Design of a test set-up with one flared end coil mock-up
    Coming soon, using N. Peray coil design as input for the coil end
    Take advantage as much as possible of the components manufactured for the racetrack coil mock-up
Racetrack coil mock-up test set-up

## Slide 9
Racetrack coil mock-up
Tests can be done to validate/explore different scenarios
  1 pole fixed and 1 pole completely free (just pinned to the base plate to ensure alignment) with gap between poles and 2-parts mold
    Assuming free sliding of the coil inside the mold, the sliding system should not move
  Both poles fixed to the base plates (and pinned for alignment) with gap between poles and 2-parts mold
    Simulation of the fix point caused by the flared end, the sliding system should move accordingly to the cable expansion/contraction
A
A
Sez. A-A
Courtesy of B. Pellet

## Slide 10
Racetrack coil mock-up
Set-up suitable for both sliding systems (linear and circular ceramic bearings)
Courtesy of B. Pellet

## Slide 11
Racetrack coil mock-up
Set-up suitable for both sliding systems (linear and circular ceramic bearings)
Courtesy of B. Pellet

## Slide 12
Racetrack coil mock-up
Courtesy of B. Pellet
EDMS 3234739

## Slide 13: Spare slides

## Slide 14: Test set-up
0.6m long bar
(SS 304)
  At 650°C:
A 0.6m long bar of SS 304 is enough to have a differential displacement of about 2.8 mm

## Slide 15: 1st option Linear ceramic bearing
Purchasing of 1 set CRZ-3075x10AA-SI:
  4 pcs ZrO2 rails (Si3N4 rails available upon request and for a MOQ)
  2 pcs stainless steel roller cage and Si3N4 rollers

## Slide 16: ZrO2 properties (supplier datasheet)

## Slide 17: 2nd option Circular ceramic bearing
Based on actual full Si3N4 bearing stock, they can propose us only bearings without cage
  In principle for temperatures between 500-900°C a GH4099 nickel-based alloy cage could be used
Price for 6 bearings CCSI-698 (chosen randomly for the mock-up manufacturing)
  26.97 £/piece (30.48 CHF/piece)
  12 bearings in stock
COMMENT: The use of this type of bearing could be more challenging w.r.t. another system
  Fitting shaft/bearing must be careful check both at ambient and high temperatures to
    Ensure the alignment of the mold parts during the whole reaction cycle
    Make sure that interference fits due to differential thermal expansions do not reduce the radial play of the bearing to an unacceptable level (or shaft and housing fits should always accommodate differences in expansion coefficients)

## Slide 18: Racetrack coil mock-up
Insulated cable reference parameters in the table below from drawing LHCMQXFBC0057
Based on expansion coefficient assumptions:
  4.5% azimuthal
  1.2% radial
18.36mm (reacted bare cable)
1.594mm (reacted bare cable)
18.65mm (insulated reacted cable)
1.884mm (insulated reacted cable)

## Slide 19
For the first-order assessment of the required gaps, we follow a similar logic than for TFD (see J.L. Rudeiros presentation).
Some comments on gaps
Cable
Table center
Table extremity
Pole center
Pole extremity
Central plane
Central plane
Contraction due to the relaxation of winding tension (about 0.05% - 0.1% ?)
Contraction due to reaction (about 0.35% - see next slide)
Expansion of the cable at 650 °C (about 0.2 % - see next slide)
Main parameters
Pole
Table
Assuming SS 316
* Courtesy of Jose Luis Rudeiros
** Without considering the change in coil length after releasing winding tension

## Slide 20
Some comments on gaps

## Slide 21: Reaction mold – Motion during reaction cycle
Because of non homogenized material choice in coil/mold component, relative movement will occur during the reaction process.
For transverse dimension change, the mold will expand more than the pole and the conductor. And the cavity is design with the reacted cable dimension to anticipate its growth during reaction.
For the longitudinal direction it is a different story. The “angle” between the straight section and the head creates a kind of fixed point that restrain the straight section to live its life freely.
* Slide from N. Peray

## Slide 22: Reaction mold – Central pole fixed point
Fixed point
Screwed cap
Conical section
Cylindrical section
Pin interface in the mold
Nice, but what happen with the layerjump ?
Pins or part of it might be removed during reaction
* Slide from N. Peray

## Slide 23: Reaction mold – Motion during reaction cycle
If we assume that the end-pole is fixed to the tooling and the curvature imposes a fixed point as well to the cable…
All displacement is then happening in the head. Would we need to cut the end region to introduce a gap (magenta dashed line) as well?
A way of looking at it is to assume that the ends are kind of a SMC/RMC case,