## Slide 1: Feedback on Past Experience
Julia Bentchikou
CERN Procurement Officer

## Slide 2: IT-4916/EP/CMS: Supply of Lead Sandwiches
Documentation was of good quality and clear on the requirements. Alternative standards were allowed for flexibility.
Similar prototypes were produced in the past
One valid bid was received, which was four times more expensive than expected.
An additional unofficial offer was received from an already declining Bidder, which was of a similar price as the bid received.
Price estimation was unrealistic and too optimistic, even when a price for prototypes was available.
Price estimation: even when a prototype price is available, consult preliminarily the industry for series prices, and the impact of economies of scale (to not overestimate them).
When companies decline and there is a minimum suspicion that a Bidder could change their mind based on their answer, consider making a call and insist.
Revised the strategy: if only two companies qualified to the MS ( Memo)
Notes: Special considerations: The Supply is complex in terms of tolerances and nature, as not many sandwiches of these materials are produced.
Strategy: only two UK companies

## Slide 3: IT-4678/SY: Production and Testing of HL-LHC 2kA-10V Power Converters
In the Technical Specification, there was a mention of the upgrade of the pre-series to the series in case of changes.
Many changes to be done which implied 20% of extra cost (600K CHF).
The cost of upgrades were not taken into account by CERN in the offer.
 An additional DO was prepared to cover the extra cost in order to not go to FC without a good justification.
The Contractor shall conform to what is written in the Technical Specification.
If modification needs to be done, detailed price breakdown can be requested as part of the bid.
Notes: 600K too much – 340K
After contract placement, they decided to change a lot of things

## Slide 4: IT-4961/EN: Supply, Installation and Commissioning of High-Voltage Equipment in Two Different 66/18 kV Air Insulated Substations
The Technical Specification mentioned that the Contractor winning the IT-4961 shall gives feedback directly to the Contractor winning the civil engineering Contract.
Spotted during SC.
Explain to the Technical Officer in charge about the legal involvement and the rules that must be followed.
CERN is the responsible Party for both Contracts and shall not ask another Contractor to take those responsibilities.
Notes: The substation has to be installed on a platform (civil engineering contract).
In the documentation the TO requires that the contractor gives feedback directly to the civil engineering contractor.
This triggered very long discussion at the SC (I mean, VERY long).
Whenever there is a similar case, CERN is the responsible for both contracts and cannot demand to another contractor to get the responsibility.

## Slide 5: DO-34528/TE (MS-4994/TE): Supply of Two Sets of Coils for a Quadrupole Magnet
Documentation was of good quality and clear on the requirements.
Seven known companies invited to participate to the Price Enquiry.
One valid bid was received, which was four times more expensive than expected.
The Coils are quite complex to produce and some of the suppliers did not want to take the risk to manufacture it.
As many tenders have been dispatch for magnets, some of the companies are at full capacity.
We discuss with the suppliers to understand their decline, and to raise interest to propose an estimation of the prices.
We plan different strategies: doing it in-house or relaunch a new price enquiry.
Group similar request in the same tender to avoid spamming the suppliers.

## Slide 6: General Remarks:
Pay attention to Bidder that might participate. Always better to have more offers ( Memo);
Foresee and evaluate the cost of a change;
Do not forget to take into account the rules/ laws that shall be followed;
Clear distribution of responsibilities;
Pay attention to the schedule in the tender documents. Can it be relaxed?

## Slide 7: PROCESS IMPROVEMENT
Removal of the pre-greenlight
Use of CERNBox
Very useful and efficient that all comments can be collected in a single document. As a result, we arrive at the SC better prepared and the TO no longer have to do a tedious post-SC work. As a result, the post-SC document are more mature. However, it shall no exempts the buyer and chair of a careful final reading.
One change that shall be beneficial would be for the chair to download the CERNBox documents just before the SC, and use them in Word version, which will avoid formatting discrepancies and make work during the SC much easier.
        Floris
Less confusion with the several version of the documents with CERNBox.
Faster and less confusing for a new PO without pre-greenlight. Julia
I prefer it now, easier to proceed without the pre-greenlight and with CERNBox.
        Andrea
The CERNBox procedure is smoother.
Nordine

## Slide 8
Thank you